## To Do List
Project To Do List
Project Name
Date Created
Project Manager
Task ID | Description | Assigned To | Priority | Start Date | End Date | Status | Comleted % | Dependencies | Notes
1 | Finalize plumbing rough-in | Clive | Medium | 2025-01-01 | 2025-01-31 | In Progress | 0% |  | Awaiting inspection
2 | Order kitchen cabinets | Jason | Low | 2025-01-10 | 2025-01-31 | Closed | 100% | 1 | Lead time 2 weeks
3 | Install dry wall | Marshal | High | 2025-01-05 | 2025-01-22 | To Be Confirmed | 50% |  | Check level 3 finish
4 | Paint master bedroom | Cinthiya | Medium | 2025-02-01 | 2025-03-03 | Open | 75% | 3 | Client approve
5 | Finalize garden layout | Robert | Low | 2025-02-04 | 2025-02-27 | In Progress | 25% |  | Awaiting layout
Sign-Off Section:
Contractor Approval
Client Approval
Remarks

## Settings
Status | Priority
Open | Low
Closed | Medium
In Progress | High
To Be Confirmed