## Project Financial Statement
PROJECT FINANCIAL STATEMENT
Project Name
Project Manager
Start Date
End Date
Date | Type | Supplier | PO# | Description | Revenue Requested | Revenue Received (IPO) | Commitment | PO Amount | Payment Made | Project Balance (Forecast) | Project Balance (Actual) | Variance
2024-01-15 | Software | TechSolutions Inc | PO-24-105 | Cloud Infrastructure Lic | 50000 | 50000 | 45000 | 45000 | 22500 | 27500 | 27500 | 0
2024-01-22 | Services | ConsultPro Ltd | PO-24-108 | Implementation Services | 75000 | 60000 | 70000 | 70000 | 35000 | 40000 | 25000 | 15000
2024-02-05 | Hardware | GlobalHardware | PO-24-121 | Server Equipment | 30000 | 30000 | 28000 | 28000 | 28000 | 1800 | 2000 | -200
2024-02-18 | Training | SkillMaster Acad | PO-24-133 | Team Certification | 15000 | 15000 | 12000 | 12000 | 6000 | 9000 | 9000 | 0
2024-03-03 | Marketing | BrandVision | PO-24-156 | Campaign Development | 40000 | 40000 | 38000 | 38000 | 19000 | 21000 | 21000 | 0
|  |  |  | TOTAL | 210000 | 195000 | 193000 | 193000 | 110500 | 99300 | 84500 | 14800