## Task Manager
Project
[Project Name]
Project Manager
[Name]
Date
[Date]
Updated on
[Date]
Task ID | Task Name | Description | Assigned To | Start Date | Due Date | Priority | Status | Completion Date | Remarks | Overdue | Overdue Days | Aging
1 | Website Redesign | Redesign homepage and product pages | Sarah Lee | 2025-01-01 | 2025-02-15 | High | In Progress |  | Awaiting client approval | Yes | 46 | Above 25 days
2 | UI Mockups | Create Figma prototypes for new layout | Alex Wong | 2025-01-01 | 2025-03-05 | High | Completed | 2025-07-05 | Client approved V2 | No
3 | Mobile Optimization | Implement responsive design for mobile | Jamie Chen | 2025-01-08 | 2025-03-12 | Medium | Not Started |  |  | Yes | 21 | 20 to 25 days
4 | Marketing Campaign | Launch Q3 social media campaign | Marketing Team | 2025-01-10 | 2025-07-30 | High | In Progress |  | Budget: $5,000 | No
5 | Content Creation | Write blog posts and social media copies | Priya Patel | 2025-01-10 | 2025-07-20 | Medium | In Progress |  | 3/5 posts done | No
6 | Database Migration | Move customer data to new AWS server | IT Team | 2025-01-05 | 2025-03-25 | Critical | Blocked |  | Waiting for security clearance | Yes | 8 | 5 to 10 days
7 | Backup Existing Data | Create full backup before migration | Ryan Kim | 2025-01-05 | 2025-07-07 | High | Completed | 2025-07-06 | Verified backup integrity | No
8 | Employee Training | Conduct GDPR compliance training | HR Department | 2025-01-15 | 2025-08-15 | Low | Not Started |  |  | No
9 | Schedule Sessions | Book rooms and send invites | Olivia Smith | 2025-01-15 | 2025-03-18 | Medium | In Progress |  | 2/4 sessions scheduled | Yes | 15 | 15 to 20 days
10 | Quarterly Audit | Review financial records for Q2 | Finance Team | 2025-08-01 | 2025-08-30 | High | Not Started |  | External auditor involved | No
Formulas:
Overdue = IF(Table5[[#This Row],[Start Date]]="","",IF(Table5[[#This Row],[Status]]="Completed","No",IF(Table5[[#This Row],[Due Date]]<IF(Table5[[#This Row],[Completion Date]]="",TODAY(),Table5[[#This Row],[Completion Date]]),"Yes","No")))
Overdue Days = IF(AND(Table5[[#This Row],[Status]]<>"Completed",Table5[[#This Row],[Due Date]]<=TODAY()),TODAY()-Table5[[#This Row],[Due Date]],"")
Total Tasks
10
TASK MANAGER TEMPLATE

## Settings
Overdue Days | Aging | COUNT | Priority | COUNT | Status | COUNT | Overdue Days | COUNT | Total Tasks
0 | 0 to 5 days | 0 | High | 5 | In Progress | 4 | Yes | 4 | 10
5 | 5 to 10 days | 1 | Medium | 3 | Completed | 2 | No | 6
10 | 10 to 15 days | 0 | Critical | 1 | Not Started | 3
15 | 15 to 20 days | 1 | Low | 1 | Blocked | 1
20 | 20 to 25 days | 1
25 | Above 25 days | 1