## PERT Chart
|  | PERT CHART TEMPLATE | [10 empty] | PERT CHART DIAGRAM
|  | Project | Project Name
|  | Date | 2025-01-01
|  | Prepared by | Trevor
Time (Days)
No. | Task Name | Dependency | Description | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Time (TE) | Standard Deviation
1 | A |  | Task 1 | 2 | 3 | 5 | 3 | 0.5 |  | Task | A |  | Task | C |  | Task | E
2 | B |  | Task 2 | 1 | 2 | 3 | 2 | 0.33333 |  | Duration | 3 |  | Duration | 6 |  | Duration | 4
3 | C | A | Task 3 | 4 | 6 | 8 | 6 | 0.66667 |  |  |  | Node 1 |  |  | Node 3
4 | D | B | Task 4 | 3 | 4 | 6 | 4 | 0.5 | [10 empty] | Task | G
5 | E | C | Task 5 | 2 | 4 | 6 | 4 | 0.66667 | [10 empty] | Duration | 7
6 | F | D | Task 6 | 4 | 7 | 9 | 7 | 0.83333 | Start | [8 empty] | Node 5 |  |  | Node 6
7 | G | E,F | Task 7 | 6 | 7 | 8 | 7 | 0.33333
[12 empty] | Node 2 |  |  | Node 4
[10 empty] | Task | B |  | Task | D |  | Task | F
[10 empty] | Duration | 2 |  | Duration | 4 |  | Duration | 7
Note on C9: Auto calculated column

## Read Me
What is a PERT Chart?
A PERT Chart (Program Evaluation Review Technique) is a project management tool used to schedule, organize, and coordinate tasks within a project. It is particularly useful for analyzing the time required to complete each task and identifying the minimum time needed to complete the entire project. PERT charts are commonly used in complex projects where tasks are interdependent and time-sensitive.
A PERT chart is a network diagram that consists of nodes (representing tasks or milestones) and arrows (representing dependencies between tasks). Each task is associated with time estimates, including optimistic, pessimistic, and most likely durations.
Key Components of a PERT Chart:
1. Nodes (Circles or Rectangles): Represent tasks, milestones, or events.
2. Arrows: Represent dependencies between tasks.
3. Time Estimates: Each task has three time estimates:
- Optimistic Time (O): The minimum possible time required to complete a task.
- Most Likely Time (M): The best estimate of time required to complete a task.
- Pessimistic Time (P): The maximum possible time required to complete a task.
4. Critical Path: The longest path through the chart, which determines the minimum project duration.
Steps to Build a PERT Chart:
1. Define Tasks and Milestones
- Break down the project into smaller tasks or activities.
- Identify milestones (key points in the project).
2. Determine Task Dependencies
- Identify the sequence of tasks and their dependencies (which tasks must be completed before others can start).
3. Estimate Time for Each Task
- For each task, estimate three durations:
- Optimistic Time (O)
- Most Likely Time (M)
- Pessimistic Time (P)
- Calculate the Expected Time (TE) for each task using the formula:
TE = | O + 4M + P
6
4. Draw the PERT Chart
- Use nodes to represent tasks or milestones.
- Use arrows to show dependencies between tasks.
- Label each task with its expected time (TE).
5. Identify the Critical Path
- Determine the longest path through the chart (the sequence of tasks that determines the project's total duration).
- Tasks on the critical path have no slack time (delay in these tasks will delay the entire project).
6. Analyze and Optimize
- Review the chart for potential bottlenecks or delays.
- Adjust resources or task dependencies to optimize the schedule.
What Is the PERT Chart Standard Deviation?
- Use the formula below to find the PERT chart standard deviation. The larger your results, the less confidence you have in your estimate, and vice versa.
(P-O) / 6
Dependencies:
- Task A must be completed before Task B and Task C can start.
- Task B and Task C must be completed before Task D can start.
PERT Chart:
Start → A → B → D → End
A → C → D
Critical Path:
- The critical path is the longest path: A → C → D (3.17 + 6 + 4.17 = 13.34 days).
Advantages of PERT Charts:
- Helps visualize task dependencies and project flow.
- Identifies the critical path and potential bottlenecks.
- Provides a clear timeline for project completion.
Disadvantages of PERT Charts:
- Can become complex for large projects.
- Requires accurate time estimates, which may be difficult to predict.
By following these steps, you can create a PERT chart to effectively plan and manage your project!