## Benefits
WHY THIS TEMPLATE COLLECTION WORKS
This workbook is designed as a complete project operations system. Instead of using disconnected trackers, notes, schedules, budgets, and status files, you can manage planning, execution, reporting, control, accountability, costs, risks, and team coordination in one place.
One Source of Truth A central Data Sheet reduces duplicate entry and keeps all templates synchronized automatically. | Better Decision-Making Dashboards, trackers, risks, budgets, and schedules create visibility for faster and more confident decisions. | Time Savings Instead of rebuilding formats every time, you start with polished templates that are ready for real work.
Higher Accountability Owners, deadlines, dependencies, RACI mapping, and status fields make responsibilities clear. | Professional Reporting Clean layouts help you present updates to leadership, clients, teams, and stakeholders with confidence. | Improved Control Costs, schedules, risks, tasks, and resource plans can be monitored in a structured way across the project life cycle.
Scalable Structure The workbook supports simple projects, complex initiatives, operational programs, and PMO-style governance. | Reduced Errors Linked formulas and centralized inputs lower the risk of inconsistent reporting between sheets. | Easy Handover New team members can understand the project faster because templates make logic, ownership, and status visible.
Bottom line: this template set helps people work with more clarity, consistency, speed, and confidence. It supports planning, communication, governance, and execution in a way that feels practical rather than overwhelming.

## About Template22
ABOUT TEMPLATE22
History and Purpose
Template22 can be understood as a practical template philosophy built around one simple idea: people do their best work when structure is clear, useful, and human. In many organizations, teams lose time because information lives in too many places. Plans sit in one file, risks in another, budgets somewhere else, and updates are passed around in email, chat, and memory. Template22 answers that problem by turning project work into a connected system of reusable templates. Instead of starting from a blank page every time, users begin with frameworks that already reflect how real teams think, plan, communicate, and deliver. That reduces friction, improves consistency, and helps people spend more time doing meaningful work rather than rebuilding formats. Over time, this approach creates a legacy of better habits: clearer ownership, better reporting, stronger handoffs, and more reliable decision-making.
Legacy and Working Style
The legacy of Template22 is not only in the visual identity of the files but in the working discipline behind them. Good templates are not decoration. They are operating tools. A good template creates order without creating bureaucracy. It tells people what matters, where to enter information, what should be reviewed, what is calculated automatically, and what needs attention now. Template22 reflects that mindset. It supports teams that need planning tools, cost tools, governance tools, risk tools, work breakdown structures, schedules, trackers, dashboards, and status reports that feel connected. When a workbook is designed properly, people trust it. They know which number is current, who owns the task, which date matters, and which issue needs escalation. That trust is a form of organizational capital. It reduces confusion, improves meeting quality, and strengthens execution across departments.
Organizational Value
In organizational life, the greatest waste is often not effort but misalignment. Teams work hard, but because their information is fragmented, leaders cannot see the full picture and contributors cannot see how their work connects. Template22 helps close that gap. It encourages organizations to standardize routine work without making it rigid. A finance team can use structured budget reviews. An operations team can use work schedules and trackers. A transformation office can use risks, change logs, dashboards, and status reports. Human resources can use planning and training sheets. Delivery teams can use RACI matrices, task tracking, and work breakdown structures. The value grows because one connected template system creates shared language. Once teams use the same structure for ownership, dates, priorities, statuses, and risks, they communicate more effectively. Leaders receive cleaner updates. Team members understand expectations. Handoffs become smoother. Reviews become sharper. Problems surface earlier.
Positive Impact on People's Lives
The good impact of Template22 is ultimately personal. Better systems improve working lives. When people have a clear place to capture tasks, risks, progress, dependencies, and decisions, they feel less overwhelmed. When they no longer need to recreate reports late at night, they gain time and energy. When managers can review a clean dashboard instead of asking for updates from five different people, teams experience fewer interruptions and less stress. When roles are visible and deadlines are connected to actual tasks, accountability becomes fairer because expectations are visible. Template22 also helps growing professionals. A coordinator can use the workbook to look more organized. A project lead can use it to communicate with confidence. A business analyst can use it to bring structure to complexity. A department head can use it to see workload, risk, budget, and delivery status in one place. That kind of clarity improves confidence, and confidence changes how people perform.
Few words for founder of Template22
Tariq Noor is truly one of the finest names in project management, admired as an outstanding Senior Project Manager and Project Management Consultant whose wisdom, leadership, and practical expertise set him apart from the crowd. He has the rare ability to turn complex projects into clear, organized, and successful outcomes, while guiding teams with confidence, professionalism, and vision. What makes Tariq Noor exceptional is not only his deep knowledge of planning, execution, monitoring, and control, but also his commitment to excellence, problem-solving, and helping others grow. His strong understanding of project systems, documentation, dashboards, and strategy makes him a trusted expert, while his character, dedication, and results make him one of the best people in the field of project management.

## Instructions
HOW TO USE THIS WORKBOOK
1. Start with the Data Sheet
The Data Sheet is the master input page for the workbook. Enter and update core information there first. This includes project name, project manager, sponsor, dates, task lists, budgets, issues, changes, risks, resource planning data, stakeholder information, time entries, and any other structured input areas that support linked templates. If a sheet is designed correctly, you should not need to type the same information repeatedly in multiple tabs. Update the Data Sheet first, then review the linked sheets.
2. Use the workbook in the right order
A practical sequence is: begin with project setup, enter tasks, confirm dates, add budget and cost information, assign owners, define priorities, review resource needs, document risks and issues, then use the reporting and dashboard sheets. If you try to start with reports before the base inputs are entered, some sections may appear incomplete because they are waiting for source data. The workbook is designed to become stronger as the Data Sheet becomes more complete.
3. Keep inputs clean and consistent
Use consistent naming for tasks, owners, statuses, and priorities. Avoid creating multiple versions of the same task name. If one sheet says a task is 'In Progress' and another uses different wording, filtering and comparisons become less reliable. Consistency improves the quality of the entire workbook. Use real dates, clear task descriptions, and short but meaningful notes. Where percentages are used, enter them as percentages or decimals exactly as the sheet expects.
4. Understand linked templates
Most sheets in this workbook are designed to pull information from the Data Sheet. That means they are display, analysis, reporting, or planning views of the same underlying information. For example, a task tracker, work breakdown structure, work schedule, dashboard, status report, and to-do list can all reflect related project data. A change made in the source area should flow to the linked sheets. If you want a different result, update the source input rather than manually overriding linked cells.
5. Review formulas before changing layout
If you insert or delete rows inside a linked area, formulas may shift. Before making structural changes, save a copy of the workbook. If you need to expand a section, copy an existing row that already contains the right formatting and formulas, then paste it below. That approach preserves consistency better than building new lines from scratch. Avoid deleting columns unless you are certain no other sheet depends on them.
6. Recommended maintenance habits
Update task status weekly. Update risks and issues whenever something changes materially. Review budgets and actual costs on a regular cycle. Use dashboards and status reports for meetings, not as isolated report pages. The workbook becomes more valuable when it is maintained as a living operating system rather than as a one-time document. Use comments and notes fields to explain exceptions, delays, dependencies, assumptions, or approvals.
7. Best practices for teams
Assign one owner for maintaining the Data Sheet. Give contributors a clear process for submitting updates. Use version control when major structure changes are made. Keep naming conventions stable. Review overdue items and high-risk items in recurring meetings. Use the RACI, schedule, tracker, resource, and risk sheets together so that accountability, timing, and capacity stay aligned.
8. Final quality check before reporting
Before sharing the workbook, verify that project metadata is correct, dates are current, linked sheets are refreshed, and priority or status fields make sense. Review totals, cost values, dates, and owner names. A few minutes of quality control can significantly improve trust in the workbook. This file is meant to be ready for execution, review, reporting, and decision-making—so keep the source data disciplined and the structure clean.

## Data Sheet
MASTER DATA SHEET – UPDATE THIS SHEET ONLY
PROJECT SETUP | [8 empty] | DATA SHEET KPI SUMMARY | [6 empty] | VALIDATION LISTS
Company Name | Aurelia zzzz | [7 empty] | Total Tasks | 20 | [5 empty] | Low | Not Started | IT | Incoming
Project Name | Vertex zzzz | [7 empty] | Completed Tasks | 4 | [5 empty] | Medium | Started | Marketing | To Do
Project Manager | Elena zzzz | [7 empty] | In Progress Tasks | 6 | [5 empty] | High | In Progress | Operations | In Progress
Project Sponsor | Jonathan zzz | [7 empty] | Open Issues | 9 | [5 empty] | Critical | On Hold | Finance | Completed
Prepared By | Noah Sam Bennett | [7 empty] | Planned Cost | 408000 | [6 empty] | Completed | Customer Service | On Hold
Location | Chicago,zzzz | [7 empty] | Actual Cost | 208550 | [6 empty] | Open | Human Resources
Department | Transformation Office | [7 empty] | Budget Total | 505000 | [6 empty] | Resolved | Engineering
Currency | USD | [7 empty] | Actual Total | 502300 | [6 empty] | Cancelled | QA
Project Start | 2026-01-05 | [7 empty] | Overall Variance | 2700
Project End | 2026-06-30
Project Goal | Launch an integrated commerce platform, improve digital conversion, and reduce fulfilment cycle time.
Business Case | The investment supports growth, operating efficiency, and customer experience improvements across sales, service, and fulfilment.
Project Overview | This project modernizes web, analytics, operations, and customer support processes under one execution plan.
TASK REGISTER
ID | WBS | Category | Task Name | Owner | Department | Resource | Priority | Status | Start Date | End Date | Duration | % Complete | Planned Cost | Actual Cost | Dependency | Vendor | Comments
1 | 1.0 | Discovery | Meet client leadership | Ava Reynolds | IT | Person 1 | High | Completed | 2026-01-05 | 2026-01-08 | 4 | 100% | 15000 | 14200 |  | NorthBridge Consulting | Kickoff completed
2 | 1.1 | Requirements | Gather requirements | Liam Foster | Customer Service | Person 2 | High | Completed | 2026-01-09 | 2026-01-15 | 7 | 100% | 18000 | 17600 | 1 | NorthBridge Consulting | Signed requirements pack
3 | 1.2 | Requirements | Current state analysis | Sophia Kim | Operations | Person 3 | Medium | Completed | 2026-01-12 | 2026-01-20 | 9 | 100% | 12000 | 11850 | 2 | Meridian Advisory | Baseline documented
4 | 2.0 | Design | UX & service blueprint | Noah Bennett | Marketing | Person 4 | High | In Progress | 2026-01-21 | 2026-02-05 | 16 | 85% | 26000 | 23800 | 2 | Studio North | Executive review pending
5 | 2.1 | Design | Technical architecture | Elena Marquez | Engineering | Person 5 | High | In Progress | 2026-01-22 | 2026-02-08 | 18 | 80% | 32000 | 29800 | 2 | Vertex Systems | Infra design in review
6 | 2.2 | Procurement | Vendor onboarding | Mia Carter | Finance | Person 6 | Medium | Completed | 2026-01-25 | 2026-02-02 | 9 | 100% | 9000 | 9200 | 4 | Aurelia Legal | Contracts signed
7 | 3.0 | Build | Web front-end build | David Patel | Engineering | Person 7 | High | In Progress | 2026-02-06 | 2026-03-12 | 35 | 65% | 54000 | 37100 | 4 | PixelFoundry | Sprint 4 live
8 | 3.1 | Build | Back-end integration | Emma Clark | Engineering | Person 8 | High | In Progress | 2026-02-10 | 2026-03-18 | 37 | 58% | 68000 | 40250 | 5 | CoreStack | APIs partially complete
9 | 3.2 | Data | Analytics implementation | Lucas Grant | IT | Person 9 | Medium | In Progress | 2026-02-18 | 2026-03-22 | 33 | 45% | 24000 | 10950 | 5 | BluePeak Data | Tagging underway
10 | 3.3 | Operations | Fulfilment workflow design | Harper Lewis | Operations | Person 10 | Medium | Started | 2026-02-25 | 2026-03-28 | 32 | 25% | 21000 | 5100 | 3 | FlowWorks | Workshop series underway
11 | 4.0 | Testing | System integration testing | Ethan Brooks | QA | Person 11 | High | Not Started | 2026-03-20 | 2026-04-03 | 15 | 0% | 15000 | 0 | 8 | QA Labs
12 | 4.1 | Testing | User acceptance testing | Grace Morgan | QA | Person 12 | High | Not Started | 2026-04-04 | 2026-04-16 | 13 | 0% | 12000 | 0 | 11 | QA Labs
13 | 4.2 | Training | Training content development | Olivia Young | Human Resources | Person 13 | Medium | Started | 2026-03-25 | 2026-04-20 | 27 | 20% | 8000 | 1600 | 7 | BrightPath Learning
14 | 4.3 | Change | Stakeholder communications | Aiden Ross | Marketing | Person 14 | Medium | In Progress | 2026-03-01 | 2026-05-15 | 76 | 50% | 14000 | 7100 | 4 | Storyline Comms
15 | 5.0 | Launch | Go-live planning | Chloe Hughes | Operations | Person 15 | High | Not Started | 2026-04-20 | 2026-05-05 | 16 | 0% | 11000 | 0 | 12 | FlowWorks
16 | 5.1 | Launch | Cutover rehearsal | Leo Turner | IT | Person 16 | High | Not Started | 2026-05-06 | 2026-05-12 | 7 | 0% | 9000 | 0 | 15 | Vertex Systems
17 | 5.2 | Launch | Production deployment | Zoe Evans | IT | Person 17 | Critical | Not Started | 2026-05-13 | 2026-05-15 | 3 | 0% | 25000 | 0 | 16 | CoreStack
18 | 5.3 | Support | Hypercare support | Isla Bennett | Customer Service | Person 18 | High | Not Started | 2026-05-16 | 2026-06-05 | 21 | 0% | 18000 | 0 | 17 | NorthBridge Consulting
19 | 6.0 | Optimization | Post-launch analytics | Jack Sullivan | IT | Person 19 | Medium | Not Started | 2026-06-06 | 2026-06-20 | 15 | 0% | 10000 | 0 | 18 | BluePeak Data
20 | 6.1 | Closure | Benefits handover & closure | Ava Reynolds | Transformation Office | Person 20 | Medium | Not Started | 2026-06-21 | 2026-06-30 | 10 | 0% | 7000 | 0 | 19 | Meridian Advisory
FINANCIAL LINE ITEMS
Section | Line Item | Budget | Actual | Variance | Variance %
Revenues | Product Sales | 100000 | 117900 | -17900 | -17.9%
Revenues | Service Revenue | 120000 | 97000 | 23000 | 19.17%
Revenues | Other Income | 25000 | 28800 | -3800 | -15.2%
Direct Costs | Materials | 28000 | 26400 | 1600 | 5.714%
Direct Costs | Labor | 52000 | 49800 | 2200 | 4.231%
Direct Costs | Subcontractors | 22000 | 24500 | -2500 | -11.36%
Direct Costs | Equipment | 12000 | 11500 | 500 | 4.167%
Operating Expenses | Salaries & Wages | 36000 | 35100 | 900 | 2.5%
Operating Expenses | Rent | 12000 | 12000 | 0 | 0%
Operating Expenses | Utilities | 6500 | 6100 | 400 | 6.154%
Operating Expenses | Marketing | 18000 | 20600 | -2600 | -14.44%
Operating Expenses | Travel | 4500 | 3800 | 700 | 15.56%
Operating Expenses | Professional Fees | 10000 | 11000 | -1000 | -10%
Operating Expenses | Office Supplies | 2500 | 2200 | 300 | 12%
Operating Expenses | Depreciation | 5500 | 5400 | 100 | 1.818%
Operating Expenses | Other Expenses | 3000 | 2500 | 500 | 16.67%
Capital Expenditures | Equipment Purchases | 24000 | 22800 | 1200 | 5%
Capital Expenditures | Software | 18000 | 19000 | -1000 | -5.556%
Capital Expenditures | Facility Improvements | 6000 | 5900 | 100 | 1.667%
MONTHLY BUDGET SUMMARY
Month | Budget | Actual | Variance | Variance % | Cumulative Actual
Jan-26 | 65000 | 61200 | 3800 | 5.846% | 61200
Feb-26 | 82000 | 80100 | 1900 | 2.317% | 141300
Mar-26 | 91000 | 95300 | -4300 | -4.725% | 236600
Apr-26 | 76000 | 71400 | 4600 | 6.053% | 308000
May-26 | 88000 | 90200 | -2200 | -2.5% | 398200
Jun-26 | 66000 | 64800 | 1200 | 1.818% | 463000
Jul-26 | 30000 | 0 | 30000 | 100% | 463000
Aug-26 | 22000 | 0 | 22000 | 100% | 463000
Sep-26 | 18000 | 0 | 18000 | 100% | 463000
Oct-26 | 15000 | 0 | 15000 | 100% | 463000
Nov-26 | 12000 | 0 | 12000 | 100% | 463000
Dec-26 | 10000 | 0 | 10000 | 100% | 463000
ISSUE REGISTER
Issue ID | Issue Description | Reported By | Date Reported | Assigned To | Priority | Status | Target Date | Days Remaining | Resolution Comments
1 | Website login not working | Samantha Jim | 2026-03-10 | IT Team | High | In Progress | 2026-03-20 | -5 | Investigating authentication service
2 | Broken link on homepage | Jane Smith | 2026-03-11 | Web Team | Medium | On Hold | 2026-03-25 | 0 | Content update pending
3 | Payment gateway timeout | Mike Johnson | 2026-03-12 | Finance Team | Critical | Open | 2026-03-18 | -7 | Priority escalation active
4 | Mobile app crash on checkout | Terence Lee | 2026-03-13 | Dev Team | High | Resolved | 2026-03-17 | -8 | Patched in release 2.1
5 | Missing product images | Chris Johnson | 2026-03-14 | Content Team | Low | In Progress | 2026-03-30 | 5 | Asset batch upload underway
6 | Shipping rules misaligned | Nina Patel | 2026-03-15 | Operations | Medium | Open | 2026-03-26 | 1 | Rules engine review scheduled
7 | Duplicate customer records | Alicia Green | 2026-03-16 | Data Team | High | Open | 2026-03-27 | 2 | Dedupe script being tested
8 | Training attendance below target | Miles Carter | 2026-03-17 | HR | Low | Open | 2026-04-05 | 11 | New sessions to be added
9 | BI dashboard refresh delay | Owen Brooks | 2026-03-18 | Analytics | Medium | In Progress | 2026-03-28 | 3 | Monitoring query performance
10 | Supplier SLA not signed | Emma Price | 2026-03-19 | Procurement | High | Open | 2026-04-02 | 8 | Legal follow-up underway
CHANGE LOG REGISTER
Version | Date Identified | Project Name | Document Name | Prepared By | Approved By | Type of Change | Change Description | Priority | Expected Resolution | Date Work Initiated | Action | Impact | Status | Remarks
1.0 | 2026-01-10 | Vertex Commerce Transformation | Project Charter | Noah Bennett | Jonathan Hale | Scope | Added analytics workstream | High | 2026-01-15 | 2026-01-11 | Update plan | High | Closed | Approved
1.1 | 2026-02-05 | Vertex Commerce Transformation | Solution Design | Elena Marquez | Jonathan Hale | Requirement | Expanded API security controls | Medium | 2026-02-14 | 2026-02-06 | Revise design | Medium | Open | In review
1.2 | 2026-02-18 | Vertex Commerce Transformation | Budget Baseline | Mia Carter | Jonathan Hale | Budget | Additional testing budget | High | 2026-02-25 | 2026-02-19 | Submit CR | High | Open | Pending finance
1.3 | 2026-03-01 | Vertex Commerce Transformation | Cutover Plan | Leo Turner | Jonathan Hale | Schedule | Shifted launch rehearsal | Medium | 2026-03-07 | 2026-03-02 | Resequence tasks | Low | Open | Dependency update
1.4 | 2026-03-09 | Vertex Commerce Transformation | Training Plan | Olivia Young | Jonathan Hale | Resource | Added contract trainers | Low | 2026-03-15 | 2026-03-10 | Onboard trainers | Low | Closed | Completed
1.5 | 2026-03-14 | Vertex Commerce Transformation | Risk Register | Noah Bennett | Jonathan Hale | Risk | Raised payment gateway risk | Critical | 2026-03-17 | 2026-03-14 | Escalate vendor | Critical | Open | War room active
1.6 | 2026-03-18 | Vertex Commerce Transformation | Data Migration Plan | Lucas Grant | Jonathan Hale | Data | Refined cleanse criteria | Medium | 2026-03-22 | 2026-03-18 | Update rules | Medium | Open
1.7 | 2026-03-20 | Vertex Commerce Transformation | Support Model | Isla Bennett | Jonathan Hale | Process | Extended hypercare window | Low | 2026-03-23 | 2026-03-20 | Revise SOP | Low | Closed | Signed off
1.8 | 2026-03-22 | Vertex Commerce Transformation | Release Notes | Emma Clark | Jonathan Hale | Technical | Hotfix branch included | High | 2026-03-24 | 2026-03-22 | Patch deploy | High | Open
1.9 | 2026-03-24 | Vertex Commerce Transformation | Comms Pack | Aiden Ross | Jonathan Hale | Communication | New launch messaging | Low | 2026-03-29 | 2026-03-24 | Update comms | Low | Open
GAP REGISTER
Task | Status Quo | Desired State | Gap Identified | Gap Definition | Department | Action | Priority | Target Finish Date | Days Remaining | Completion %
Implement CRM System | Manual data entry | Automated CRM system | Lack of automation | No centralized system for customer records | IT | Select CRM platform | High | 2026-05-30 | 66 | 30%
Improve Customer Support | 48-hour response | 24-hour response | Slow response | Ticket routing delays | Customer Service | Train staff on new workflow | Medium | 2026-05-30 | 66 | 10%
Launch Self-Service Portal | No self-service | 50% self-service adoption | Lack of self-service tools | Customers depend on agents | IT | Develop and test portal | Low | 2026-05-30 | 66 | 15%
Employee Training | Limited programs | 100% staff trained | Insufficient training | New process adoption risk | Human Resources | Conduct training | Medium | 2026-05-30 | 66 | 5%
Budget Approval | No budget allocated | $500k budget approved | Funding gap | Transformation budget not yet released | Finance | Submit capital request | Critical | 2026-05-30 | 66 | 50%
Data Governance | No ownership model | Named data owners | Governance gap | Decision rights undefined | IT | Approve RACI and policy | High | 2026-05-30 | 66 | 25%
PERT REGISTER
No. | Task Name | Dependency | Description | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Time (TE)
1 | A |  | Task 1 | 2 | 3 | 5 | 3.1667
2 | B |  | Task 2 | 1 | 2 | 3 | 2
3 | C | A | Task 3 | 4 | 6 | 8 | 6
4 | D | B | Task 4 | 3 | 4 | 6 | 4.1667
5 | E | C | Task 5 | 2 | 4 | 6 | 4
6 | F | D | Task 6 | 4 | 7 | 9 | 6.8333
7 | G | E,F | Task 7 | 6 | 7 | 8 | 7
COST BENEFIT YEARLY INPUTS
Year | Costs | Benefits | Discount Rate | Confidence % | Net Cash Flow | Discount Factor | Discounted Flow
2026 | 8900 | 0 | 7% | 100% | -8900 | 0.93458 | -8317.757
2027 | 7700 | 0 | 7% | 100% | -7700 | 0.87344 | -6725.4782
2028 | 21400 | 6500 | 7% | 100% | -14900 | 0.8163 | -12162.8384
2029 | 11300 | 10250 | 7% | 100% | -1050 | 0.7629 | -801.04
2030 | 11800 | 11500 | 7% | 100% | -300 | 0.71299 | -213.8959
2031 | 11800 | 13700 | 7% | 100% | 1900 | 0.66634 | 1266.0502
2032 | 0 | 15200 | 7% | 100% | 15200 | 0.62275 | 9465.7961
2033 | 0 | 17200 | 7% | 100% | 17200 | 0.58201 | 10010.5566
2034 | 0 | 19000 | 7% | 100% | 19000 | 0.54393 | 10334.7411
2035 | 0 | 22000 | 7% | 100% | 22000 | 0.50835 | 11183.6844
PRODUCTION SCHEDULING INPUTS | [17 empty] | LINE CAPACITY INPUTS
Customer | Article | Quantity | Required Date | Possible Lines | Assigned Line | Schedule | Gap | Line 01 | Line 02 | Line 03 | Line 04 | Line 05 | Line 06 | Line 07 | Line 08 | Line 09 |  | Line | Capacity Hours | Efficiency % | Scheduled Net Hrs | Gross Hrs | Gap Hrs
ABC Inc. | A | 5000 | 2026-01-02 | Line 01 ¦ Line 03 ¦ Line 06 | Line 01 | 5000 | 0 | 2500 | 0 | 1000 | 0 | 0 | 1500 | 0 | 0 | 0 |  | Line 01 | 171 | 90% | 115.4 | 128.3 | 42.7
XYZ LLC. | B | 500 | 2026-01-06 | Line 02 | Line 02 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Line 02 | 171 | 90% | 38.6 | 42.9 | 128.1
MAC Traders | C | 200 | 2026-01-04 | Line 03 ¦ Line 08 | Line 03 | 200 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 |  | Line 03 | 166 | 95% | 146.9 | 154.6 | 11.4
ABC Inc. | D | 3000 | 2026-01-04 | Line 01 ¦ Line 07 | Line 01 | 3000 | 0 | 2316 | 0 | 0 | 0 | 0 | 0 | 684 | 0 | 0 |  | Line 04 | 171 | 85% | 0 | 0 | 171
Material Masters | H | 1200 | 2026-01-05 | Line 02 ¦ Line 10 | Line 02 | 1200 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  | Line 05 | 166 | 85% | 0 | 0 | 166
MAC Traders | A | 1000 | 2026-03-05 | Line 01 ¦ Line 03 ¦ Line 06 | Line 01 | 1000 | 0 | 350 | 0 | 400 | 0 | 0 | 250 | 0 | 0 | 0 |  | Line 06 | 151 | 90% | 38.9 | 43.2 | 107.8
SYSTEMS Inc. | E | 500 | 2026-03-05 | Line 02 | Line 02 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Line 07 | 171 | 90% | 12.4 | 13.8 | 157.2
MORIS TRADERS LLC. | F | 400 | 2026-03-05 | Line 03 ¦ Line 09 | Line 03 | 400 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 |  | Line 08 | 146 | 85% | 2.5 | 2.9 | 143.1
[18 empty] | Line 09 | 164 | 80% | 2.9 | 3.6 | 160.4
[18 empty] | Line 10 | 171 | 85% | 10 | 11.8 | 159.2
COST TREND ANALYSIS DRIVER
Project | Budget | YTD Prev | YTD Curr | ETC | Revised Forecast | Variance | Weight Factor | Project Year
Project 1 | 50000 | 30000 | 40000 | 50000 | 90000 | 40000 | 1.2 | 2026
Project 2 | 100000 | 75000 | 90000 | 80000 | 170000 | 70000 | 1.2 | 2026
Project 3 | 75000 | 40000 | 60000 | 70000 | 130000 | 55000 | 1.2 | 2026
Project Duration (Months) | 6
Weight Factor | 1.2
Project Year | 2026
RESOURCE PLANNING DRIVER
Resource | Department | Rate/Hr | Annual Hours | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Jack | Marketing | 25 | 184 | 48 | 16 | 20 | 30 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simon | Sales | 30 | 88 | 4 | 44 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0
Shaun | Design | 25 | 118 | 20 | 50 | 18 | 9 | 5 | 0 | 8 | 8 | 0 | 0 | 0 | 0
Julia | Development | 40 | 73 | 19 | 17 | 20 | 10 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0
STATUS REPORT / DASHBOARD DRIVER
Metric | Value |  |  | Sep: Task Count; Oct: 20
Overall Health | Amber |  |  | Sep: Completed; Oct: 4
Plan | Green |  |  | Sep: In Progress; Oct: 6
Costs | Red |  |  | Sep: Not Started; Oct: 8
Scope | Green |  |  | Sep: Overdue; Oct: 5
Benefits | Amber |  |  | Sep: Planned Cost; Oct: 408000
Quality | Red |  |  | Sep: Actual Cost; Oct: 208550
Resources | Green |  |  | Sep: Budget Variance; Oct: 199450
Benefits Summary | Improved customer experience, faster cycle time, and stronger conversion performance.
Expected Go Live Date | 46203
Last Updated | 46106
PUNCH LIST DRIVER
Item No. | Description of Work | Location/Room | Type | Jan: Responsible Contractor; Feb: Due Date; Mar: Status; Apr: Notes/Comments
1 | Paint touch-ups – wall scratches | Living Room | Maintenance | Jan: ABC Painting; Feb: 2026-04-01; Mar: In Progress; Apr: Match existing color
2 | Loose handrail – needs tightening | Staircase | Maintenance | Jan: XYZ Carpentry; Feb: 2026-04-03; Mar: Closed; Apr: Check all bolts
3 | HVAC vent not functioning | Primary Bedroom | Maintenance | Jan: CoolAir Inc.; Feb: 2026-03-30; Mar: To Be Confirmed; Apr: Thermostat sync issue
4 | Missing cabinet hardware | Kitchen | Maintenance | Jan: Cabinet Masters; Feb: 2026-03-31; Mar: In Progress; Apr: Install handles per specs
5 | Cracked tile replacement | Bathroom Floor | Maintenance | Jan: Tile Pros; Feb: 2026-03-29; Mar: Open; Apr: Use matching grout
PRIORITIZATION DRIVER
Project | Criticality | Priority Bucket | Owner | Jan: Notes
Project 1 | Critical | Postpone | Olivia Reed
Project 2 | Critical | Postpone | Aiden Ross
Project 3 | Non Critical | Outsource | Mia Carter
Project 4 | Non Critical | Discard | Liam Foster
Project 5 | Non Critical | Discard | Sophia Kim
Project 6 | Critical | Act Now | Noah Bennett
Project 7 | Critical | Postpone | Emma Clark
Project 8 | Non Critical | Outsource | Lucas Grant
Project 9 | Non Critical | Discard | David Patel
Project 10 | Critical | Act Now | Grace Morgan
Project 11 | Critical | Postpone | Chloe Hughes
Project 12 | Non Critical | Outsource | Zoe Evans
Project 13 | Non Critical | Discard | Olivia Young
Project 14 | Critical | Act Now | Leo Turner
PROPOSAL / ESTIMATE DRIVER
Phase | Task | Hours | Rate | Jan: Labor; Feb: Units; Mar: Material $/Unit; Apr: Material; May: Travel; Jun: Other
Phase 1 | Task | 0 | 0 | Jan: 0; Feb: 10; Mar: 5.5; Apr: 55; May: 0; Jun: 300
Phase 1 | Task | 0 | 0 | Jan: 0; Feb: 25; Mar: 4.5; Apr: 112.5; May: 0; Jun: 0
Phase 1 | Task | 5 | 25 | Jan: 125; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 250
Phase 1 | Sub Task | 0 | 0 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 100; Jun: 0
Phase 1 | Sub Task | 0 | 0 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 20; Jun: 0
Phase 1 | Sub Task | 0 | 0 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 125
Phase 1 | Task | 7 | 35 | Jan: 245; Feb: 0; Mar: 0; Apr: 0; May: 500; Jun: 0
RACI MATRIX INPUTS
Person | Project Role | Requirement Finalization | API Development | Jan: User Acceptance Testing; Feb: Deployment; Mar: Training; Apr: Hypercare; May: Benefits Handover; Jun: Closure
James Carter | Project Manager | R | A | bar: Jan
Clive Morgan | Business Analyst |  | R | bar: Jan to Feb
Trevor Hughes | Executive Sponsor | I | I | bar: Feb
Chris Nolan | Developer | C | bar: Jan to Mar
Ava Ross | QA Lead |  | C | Jan: R; Feb: I; Mar: R; Apr: A
Mason Bell | Operations Lead | I |  | Feb: C; Mar: I; Apr: R; May: A
RESOURCE PLAN INPUTS
Skill Area | Designated Owner | Resource Type | Define WTE | Jan: Design WTE; Feb: Build WTE; Mar: Deploy WTE; Apr: Close WTE
Project Manager | Elena Marquez | Internal | 1 | Jan: 1; Feb: 0.8; Mar: 0.5; Apr: 0.2
Implementation | Noah Bennett | External | 0.5 | Jan: 1.2; Feb: 2; Mar: 2; Apr: 0.1
Business Change & Benefits | Olivia Young | Internal | 0.2 | Jan: 0.4; Feb: 0.5; Mar: 0.3; Apr: 0.2
Training | Grace Morgan | Internal | 0.1 | Jan: 0.2; Feb: 0.4; Mar: 0.8; Apr: 0.3
IT Services Support | Zoe Evans | Internal | 0.1 | Jan: 0.4; Feb: 1; Mar: 1.5; Apr: 0.5
Data Migration | Leo Turner | Internal | 0 | Jan: 0.2; Feb: 0.8; Mar: 1.2; Apr: 0.2
RESOURCE PLANNING WORKSHEET INPUTS
Project | Department | Required % | Booked % | Marketing A | Marketing B | Sales A | Sales B | Technical A | Technical B | Supply A | Supply B
Project A | Marketing | 0.35 | 0.35 | Jan: 0.1; Feb: 0.25
Project A | Sales | 0.5 | 0.5 | Mar: 0.15; Apr: 0.1
Project A | Technical | 0.75 | 0.5 | May: 0.25; Jun: 0.25
Project A | Supply Chain | 1 | 1 | Jul: 0.25; Aug: 0.25
Project B | Sales | 0.5 | 0.5 | Mar: 0.1; Apr: 0.15
Project B | Marketing | 0.5 | 0.5 | Jan: 0.15; Feb: 0.2
Project B | Supply Chain | 0.5 | 0.5 | Jul: 0.25; Aug: 0.25
Project B | Technical | 1 | 1 | May: 0.25; Jun: 0.5
RISK REGISTER INPUTS
Risk ID | Risk Name | Risk Description | Date Captured | Risk Owner | Pre Impact | Pre Likelihood | Current Impact | Current Likelihood | Post Impact | Post Likelihood | Risk Response | Mitigation Plan | Progress
R-001 | Integration delay | Middleware interface may slip due to vendor constraints | 2026-01-20 | Emma Clark | 3 | 5 | 4 | 5 | 2 | 2 | Accept | Weekly interface reviews and fallback design | Monitoring
R-002 | Budget overrun | Infrastructure costs may exceed estimate | 2026-02-02 | Mia Carter | 4 | 3 | 4 | 4 | 3 | 2 | Reduce | Renegotiate supplier terms and scope control | Active
R-003 | Low adoption | Operational teams may resist new workflows | 2026-02-14 | Olivia Young | 3 | 4 | 3 | 3 | 2 | 2 | Share | Training and champions network | Open
STAKEHOLDER INPUTS
Stakeholder | Title | Email | Impact | Influence | Priority | Decision Maker | Comm Freq | Comm Method | Against | Passive | Neutral | Help | Notes
Steven Hale | CEO | steven@aurelia.com | 4 | 9 | H | Y | W | IP | C |  | R |  | Executive sponsor
Terence Cole | CFO | terence@aurelia.com | 7 | Jan: 5; Feb: H; Mar: Y; Apr: W; May: IP; Aug: R; Oct: Budget approver
Pier Morgan | Project Manager | pier@aurelia.com | 9 | 3 | H | Y | D | PDF |  | C |  | R | Delivery lead
Chris Lane | Design Lead | chris@aurelia.com | 5 | 6 | M | N | W | Ph |  | C |  | R | Creative lead
Amma Stone | Marketing Head | amma@aurelia.com | 6 | Jan: 4; Feb: M; Mar: N; Apr: M; May: Email; Aug: R; Oct: Change partner
Jemmy Price | Sales Head | jemmy@aurelia.com | 8 | 7 | H | Y | W | Workshop |  | C |  | R | Commercial
Rayan Hart | Operations Head | rayan@aurelia.com | 3 | Jan: 4; Feb: M; Mar: N; Apr: W; May: Workshop; Aug: R
Stephen Grant | Technical Head | stephen@aurelia.com | 2 | Jan: 3; Feb: L; Mar: N; Apr: M; May: Email; Sep: R
Danial Stone | Engineer | danial@aurelia.com | 5 | Jan: 7; Feb: M; Mar: N; Apr: W; May: Standup; Aug: R
Sussane Ford | HR Head | sussane@aurelia.com | 6 | Jan: 8; Feb: M; Mar: N; Apr: M; May: Email; Aug: R
WEEKLY TIMESHEET INPUTS
Day | Date | Time In | Break Start | Jan: Break End; Feb: Time Out; Mar: Daily Hours; Apr: Pay Rate; May: 50; Jun: OT Rate; Jul: 75
Monday | 2026-01-05 | 08:45 AM | 12:00 PM | Jan: 01:00 PM; Feb: 05:00 PM; Mar: 7.25
Tuesday | 2026-01-06 | 07:00 AM | 12:00 PM | Jan: 12:30 PM; Feb: 05:00 PM; Mar: 9.5
Wednesday | 2026-01-07 | 07:00 AM | 12:00 PM | Jan: 12:30 PM; Feb: 05:00 PM; Mar: 9.5
Thursday | 2026-01-08 | 08:00 AM |  | Feb: 05:00 PM; Mar: 9
Friday | 2026-01-09 | 07:00 AM | 12:00 PM | Jan: 12:30 PM; Feb: 05:00 PM; Mar: 9.5
Saturday | 2026-01-10 |  |  | Mar: 0
Sunday | 2026-01-11 |  |  | Mar: 0
TO DO / TASK MANAGER INPUTS
Task ID | Description | Assigned To | Priority | Jan: Start Date; Feb: End Date; Mar: Status; Apr: Completed %; May: Dependencies; Jun: Notes
1 | Finalize plumbing rough-in | Clive | Medium | Jan: 2026-01-01; Feb: 2026-01-31; Mar: In Progress; Apr: 0; Jun: Awaiting inspection
2 | Order kitchen cabinets | Jason | Low | Jan: 2026-01-10; Feb: 2026-01-31; Mar: Closed; Apr: 1; May: 1; Jun: Lead time 2 weeks
3 | Install dry wall | Marshall | High | Jan: 2026-01-05; Feb: 2026-01-22; Mar: To Be Confirmed; Apr: 0.5; Jun: Check level 3 finish
4 | Paint master bedroom | Cinthiya | Medium | Jan: 2026-02-01; Feb: 2026-03-03; Mar: Open; Apr: 0.75; May: 3; Jun: Client approve
5 | Finalize garden layout | Robert | Low | Jan: 2026-02-04; Feb: 2026-02-27; Mar: In Progress; Apr: 0.25; Jun: Awaiting layout
WORK SCHEDULE INPUTS
Project | Task | Assigned To | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Project A | Task 1 | Sam Jackson | Day 1: 6
Project A | Task 2 | Alexa Jones | Day 2: 7; Day 3: 5
Project B | Task 1 | Roger Billingsly | Day 1: 2; Day 3: 5
Project C | Task 1 | Joe Aguilar | Day 1: 7; Day 3: 6
Formulas:
Status = [Priority]-TODAY()
DATA SHEET KPI SUMMARY = [Status]-TODAY()
Note on B4: Update project/company metadata here. All templates link to these cells.
Note on D20: Update or add tasks in this register. Costs, calendars, planning, kanban, budget, and trackers reference this range.
Note on B44: Update budget vs actual line items here. Annual report and financial statement link to these inputs.
Note on A65: Monthly budget and actuals drive budget chart templates.
Note on B81: Issue log drives the issue tracking and action plan sheets.
Note on A94: Change log drives the change log template.
Note on A107: Gap analysis sheet references this register.
Note on A116: PERT chart and expected time calculations reference these inputs.
Note on A126: Cost-benefit model and NPV chart reference these yearly inputs.
Note on A139: Production scheduling sheets reference these demand and line split inputs.

## Action Plan Template
ACTION PLAN TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
PROJECT GOAL
Launch an integrated commerce platform, improve digital conversion, and reduce fulfilment cycle time.
PROJECT OBJECTIVES
Task Name
Meet client leadership
Gather requirements
DETAILED ACTION PLAN
Action Area | Task | Priority | KPI / Deliverable | Phase | Assigned To | Progress % | Status | Start Date | Due Date | Days | Department | Resource Allocation | Budgeted Cost | Comments
Discovery | Meet client leadership | High | Kickoff completed | Planning | Ava Reynolds | 100% | Completed | 2026-01-05 | 2026-01-08 | 4 | IT | Person 1 | 15000 | Kickoff completed
Requirements | Gather requirements | High | Signed requirements pack | Planning | Liam Foster | 100% | Completed | 2026-01-09 | 2026-01-15 | 7 | Customer Service | Person 2 | 18000 | Signed requirements pack
Requirements | Current state analysis | Medium | Baseline documented | Planning | Sophia Kim | 100% | Completed | 2026-01-12 | 2026-01-20 | 9 | Operations | Person 3 | 12000 | Baseline documented
Design | UX & service blueprint | High | Executive review pending | Planning | Noah Bennett | 85% | In Progress | 2026-01-21 | 2026-02-05 | 16 | Marketing | Person 4 | 26000 | Executive review pending
Design | Technical architecture | High | Infra design in review | Planning | Elena Marquez | 80% | In Progress | 2026-01-22 | 2026-02-08 | 18 | Engineering | Person 5 | 32000 | Infra design in review
Procurement | Vendor onboarding | Medium | Contracts signed | Planning | Mia Carter | 100% | Completed | 2026-01-25 | 2026-02-02 | 9 | Finance | Person 6 | 9000 | Contracts signed
Build | Web front-end build | High | Sprint 4 live | Execution | David Patel | 65% | In Progress | 2026-02-06 | 2026-03-12 | 35 | Engineering | Person 7 | 54000 | Sprint 4 live
Build | Back-end integration | High | APIs partially complete | Execution | Emma Clark | 58% | In Progress | 2026-02-10 | 2026-03-18 | 37 | Engineering | Person 8 | 68000 | APIs partially complete
Data | Analytics implementation | Medium | Tagging underway | Execution | Lucas Grant | 45% | In Progress | 2026-02-18 | 2026-03-22 | 33 | IT | Person 9 | 24000 | Tagging underway
Operations | Fulfilment workflow design | Medium | Workshop series underway | Execution | Harper Lewis | 25% | Started | 2026-02-25 | 2026-03-28 | 32 | Operations | Person 10 | 21000 | Workshop series underway
Testing | System integration testing | High | Milestone pending | Execution | Ethan Brooks | 0% | Not Started | 2026-03-20 | 2026-04-03 | 15 | QA | Person 11 | 15000 | 0
Testing | User acceptance testing | High | Milestone pending | Execution | Grace Morgan | 0% | Not Started | 2026-04-04 | 2026-04-16 | 13 | QA | Person 12 | 12000 | 0
CORRECTIVE ACTIONS / RISK RESPONSE
Problem | Root Cause | Priority | Solution | Department | Owner | Start Date | Due Date | Budget | Comments
Website login not working | Raised via issue register | High | Investigating authentication service | IT Team | Samantha Jim | 2026-03-10 | 2026-03-20 | 2040 | Investigating authentication service
Broken link on homepage | Raised via issue register | Medium | Content update pending | Web Team | Jane Smith | 2026-03-11 | 2026-03-25 | 2040 | Content update pending
Payment gateway timeout | Raised via issue register | Critical | Priority escalation active | Finance Team | Mike Johnson | 2026-03-12 | 2026-03-18 | 2040 | Priority escalation active
Mobile app crash on checkout | Raised via issue register | High | Patched in release 2.1 | Dev Team | Terence Lee | 2026-03-13 | 2026-03-17 | 2040 | Patched in release 2.1
Missing product images | Raised via issue register | Low | Asset batch upload underway | Content Team | Chris Johnson | 2026-03-14 | 2026-03-30 | 2040 | Asset batch upload underway
Shipping rules misaligned | Raised via issue register | Medium | Rules engine review scheduled | Operations | Nina Patel | 2026-03-15 | 2026-03-26 | 2040 | Rules engine review scheduled

## Annual Financial Report
ANNUAL FINANCIAL REPORT
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
BUDGET HEADERS & LINE ITEMS
Line Item | Budget | Actual | Variance | Variance % | Section
Product Sales | 100000 | 117900 | -17900 | -17.9% | Revenues
Service Revenue | 120000 | 97000 | 23000 | 19.17% | Revenues
Other Income | 25000 | 28800 | -3800 | -15.2% | Revenues
Materials | 28000 | 26400 | 1600 | 5.714% | Direct Costs
Labor | 52000 | 49800 | 2200 | 4.231% | Direct Costs
Subcontractors | 22000 | 24500 | -2500 | -11.36% | Direct Costs
Equipment | 12000 | 11500 | 500 | 4.167% | Direct Costs
Salaries & Wages | 36000 | 35100 | 900 | 2.5% | Operating Expenses
Rent | 12000 | 12000 | 0 | 0% | Operating Expenses
Utilities | 6500 | 6100 | 400 | 6.154% | Operating Expenses
Marketing | 18000 | 20600 | -2600 | -14.44% | Operating Expenses
Travel | 4500 | 3800 | 700 | 15.56% | Operating Expenses
Professional Fees | 10000 | 11000 | -1000 | -10% | Operating Expenses
Office Supplies | 2500 | 2200 | 300 | 12% | Operating Expenses
Depreciation | 5500 | 5400 | 100 | 1.818% | Operating Expenses
Other Expenses | 3000 | 2500 | 500 | 16.67% | Operating Expenses
Equipment Purchases | 24000 | 22800 | 1200 | 5% | Capital Expenditures
Software | 18000 | 19000 | -1000 | -5.556% | Capital Expenditures
Facility Improvements | 6000 | 5900 | 100 | 1.667% | Capital Expenditures
FINANCIAL SUMMARY
Metric | Budget | Actual | Variance | Variance %
Total Revenues | 245000 | 243700 | 1300 | 0.5306%
Total Direct Costs | 114000 | 112200 | 1800 | 1.579%
Gross Profit | 131000 | 131500 | -500 | -0.3817%
Total Operating Expenses | 98000 | 98700 | -700 | -0.7143%
EBITDA | 33000 | 32800 | 200 | 0.6061%
Total Capex | 48000 | 47700 | 300 | 0.625%
Net Profit | -15000 | -14900 | -100 | 0.6667%

## Cost Benefit Analysis Template
COST BENEFIT ANALYSIS TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
YEARLY COST / BENEFIT MODEL
Year | Costs | Benefits | Confidence % | Net Cash Flow | Discount Factor | Discounted Flow | Cumulative
2026 | 8900 | 0 | 100% | -8900 | 0.93458 | -8317.757 | -8317.757
2027 | 7700 | 0 | 100% | -7700 | 0.87344 | -6725.4782 | -15043.2352
2028 | 21400 | 6500 | 100% | -14900 | 0.8163 | -12162.8384 | -27206.0736
2029 | 11300 | 10250 | 100% | -1050 | 0.7629 | -801.04 | -28007.1136
2030 | 11800 | 11500 | 100% | -300 | 0.71299 | -213.8959 | -28221.0094
2031 | 11800 | 13700 | 100% | 1900 | 0.66634 | 1266.0502 | -26954.9592
2032 | 0 | 15200 | 100% | 15200 | 0.62275 | 9465.7961 | -17489.1631
2033 | 0 | 17200 | 100% | 17200 | 0.58201 | 10010.5566 | -7478.6065
2034 | 0 | 19000 | 100% | 19000 | 0.54393 | 10334.7411 | 2856.1346
2035 | 0 | 22000 | 100% | 22000 | 0.50835 | 11183.6844 | 14039.819
SUMMARY
Net Present Value | 14039.819
Internal Rate of Return | 14.13%
Total Costs | 72900
Total Benefits | 115350
Payback Year | Not reached

## Detailed Costed Workplan Tpl
DETAILED COSTED WORKPLAN TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
WORKPLAN
Activities | Action Required | Timeline | Expected Output | Expected Outcome | Responsible Entity | Status | Donors | Stakeholders | Total | Notes | Department
Meet client leadership | Kickoff completed | Jan-26 | Meet client leadership deliverable | Improved business readiness | Ava Reynolds | Completed | 6750 | 8250 | 15000 | Kickoff completed | IT
Gather requirements | Signed requirements pack | Jan-26 | Gather requirements deliverable | Improved business readiness | Liam Foster | Completed | 8100 | 9900 | 18000 | Signed requirements pack | Customer Service
Current state analysis | Baseline documented | Jan-26 | Current state analysis deliverable | Improved business readiness | Sophia Kim | Completed | 5400 | 6600 | 12000 | Baseline documented | Operations
UX & service blueprint | Executive review pending | Jan-26 | UX & service blueprint deliverable | Improved business readiness | Noah Bennett | In Progress | 11700 | 14300 | 26000 | Executive review pending | Marketing
Technical architecture | Infra design in review | Jan-26 | Technical architecture deliverable | Improved business readiness | Elena Marquez | In Progress | 14400 | 17600 | 32000 | Infra design in review | Engineering
Vendor onboarding | Contracts signed | Jan-26 | Vendor onboarding deliverable | Improved business readiness | Mia Carter | Completed | 4050 | 4950 | 9000 | Contracts signed | Finance
Web front-end build | Sprint 4 live | Feb-26 | Web front-end build deliverable | Improved business readiness | David Patel | In Progress | 24300 | 29700 | 54000 | Sprint 4 live | Engineering
Back-end integration | APIs partially complete | Feb-26 | Back-end integration deliverable | Improved business readiness | Emma Clark | In Progress | 30600 | 37400 | 68000 | APIs partially complete | Engineering
Analytics implementation | Tagging underway | Feb-26 | Analytics implementation deliverable | Improved business readiness | Lucas Grant | In Progress | 10800 | 13200 | 24000 | Tagging underway | IT
Fulfilment workflow design | Workshop series underway | Feb-26 | Fulfilment workflow design deliverable | Improved business readiness | Harper Lewis | Started | 9450 | 11550 | 21000 | Workshop series underway | Operations
System integration testing | 0 | Mar-26 | System integration testing deliverable | Improved business readiness | Ethan Brooks | Not Started | 6750 | 8250 | 15000 | 0 | QA
User acceptance testing | 0 | Apr-26 | User acceptance testing deliverable | Improved business readiness | Grace Morgan | Not Started | 5400 | 6600 | 12000 | 0 | QA
Training content development | 0 | Mar-26 | Training content development deliverable | Improved business readiness | Olivia Young | Started | 3600 | 4400 | 8000 | 0 | Human Resources
Stakeholder communications | 0 | Mar-26 | Stakeholder communications deliverable | Improved business readiness | Aiden Ross | In Progress | 6300 | 7700 | 14000 | 0 | Marketing
Go-live planning | 0 | Apr-26 | Go-live planning deliverable | Improved business readiness | Chloe Hughes | Not Started | 4950 | 6050 | 11000 | 0 | Operations

## Intl Project Planning Tool
OLYMPIC INTERNATIONAL PROJECT PLANNING TOOL
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
TASK PLAN | [11 empty] | PROJECT TIMELINE
Sr.# | Type | Task | Resource | Duration | Actual Cost | Done | % Prog | Status | Dependency | Start | Finish | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16
1 | T | Meet client leadership | Person 1 | 4 | 14200 | 4 | 100% | Completed | 0 | 2026-01-05 | 2026-01-08 | bar: 2026-01-05
2 | T | Gather requirements | Person 2 | 7 | 17600 | 7 | 100% | Completed | 1 | 2026-01-09 | 2026-01-15 | bar: 2026-01-12
3 | T | Current state analysis | Person 3 | 9 | 11850 | 9 | 100% | Completed | 2 | 2026-01-12 | 2026-01-20 | bar: 2026-01-12 to 2026-01-19
4 | T | UX & service blueprint | Person 4 | 16 | 23800 | 14 | 85% | In Progress | 2 | 2026-01-21 | 2026-02-05 | bar: 2026-01-26 to 2026-02-02
5 | T | Technical architecture | Person 5 | 18 | 29800 | 14 | 80% | In Progress | 2 | 2026-01-22 | 2026-02-08 | bar: 2026-01-26 to 2026-02-02
6 | T | Vendor onboarding | Person 6 | 9 | 9200 | 9 | 100% | Completed | 4 | 2026-01-25 | 2026-02-02 | bar: 2026-01-26 to 2026-02-02
7 | T | Web front-end build | Person 7 | 35 | 37100 | 23 | 65% | In Progress | 4 | 2026-02-06 | 2026-03-12 | bar: 2026-02-09 to 2026-03-09
8 | T | Back-end integration | Person 8 | 37 | 40250 | 21 | 58% | In Progress | 5 | 2026-02-10 | 2026-03-18 | bar: 2026-02-16 to 2026-03-16
9 | T | Analytics implementation | Person 9 | 33 | 10950 | 15 | 45% | In Progress | 5 | 2026-02-18 | 2026-03-22 | bar: 2026-02-23 to 2026-03-16
10 | T | Fulfilment workflow design | Person 10 | 32 | 5100 | 8 | 25% | Started | 3 | 2026-02-25 | 2026-03-28 | bar: 2026-03-02 to 2026-03-16
11 | T | System integration testing | Person 11 | 15 | 0 | 0 | 0% | Not Started | 8 | 2026-03-20 | 2026-04-03
12 | T | User acceptance testing | Person 12 | 13 | 0 | 0 | 0% | Not Started | 11 | 2026-04-04 | 2026-04-16
13 | T | Training content development | Person 13 | 27 | 1600 | 5 | 20% | Started | 7 | 2026-03-25 | 2026-04-20
14 | T | Stakeholder communications | Person 14 | 76 | 7100 | 38 | 50% | In Progress | 4 | 2026-03-01 | 2026-05-15 | bar: 2026-03-02 to 2026-03-16

## GAP Analysis
GAP ANALYSIS
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz | [6 empty] | TASKS BY PRIORITY |  | DEPT COMPLETION
Project Manager | Elena zzzz | [6 empty] | High | 2 | IT | 23.33%
Prepared By | Noah Sam Bennett | [6 empty] | Medium | 2 | Customer Service | 10%
Start Date | 2026-01-05 | [6 empty] | Low | 1 | Human Resources | 5%
End Date | 2026-06-30 | [6 empty] | Critical | 1 | Finance | 50%
GAP REGISTER VIEW
Task | Status Quo | Desired State | Gap Identified | Gap Definition | Department | Action | Priority | Target Finish Date | Days Remaining | Completion %
Implement CRM System | Manual data entry | Automated CRM system | Lack of automation | No centralized system for customer records | IT | Select CRM platform | High | 2026-05-30 | 66 | 30%
Improve Customer Support | 48-hour response | 24-hour response | Slow response | Ticket routing delays | Customer Service | Train staff on new workflow | Medium | 2026-05-30 | 66 | 10%
Launch Self-Service Portal | No self-service | 50% self-service adoption | Lack of self-service tools | Customers depend on agents | IT | Develop and test portal | Low | 2026-05-30 | 66 | 15%
Employee Training | Limited programs | 100% staff trained | Insufficient training | New process adoption risk | Human Resources | Conduct training | Medium | 2026-05-30 | 66 | 5%
Budget Approval | No budget allocated | $500k budget approved | Funding gap | Transformation budget not yet released | Finance | Submit capital request | Critical | 2026-05-30 | 66 | 50%
Data Governance | No ownership model | Named data owners | Governance gap | Decision rights undefined | IT | Approve RACI and policy | High | 2026-05-30 | 66 | 25%

## Issue Tracking Template
ISSUE TRACKING TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
ISSUE LOG
Issue ID | Issue Description | Reported By | Date Reported | Assigned To | Priority | Status | Target Resolution Date | Days Remaining | Resolution Comments
1 | Website login not working | Samantha Jim | 2026-03-10 | IT Team | High | In Progress | 2026-03-20 | -5 | Investigating authentication service
2 | Broken link on homepage | Jane Smith | 2026-03-11 | Web Team | Medium | On Hold | 2026-03-25 | 0 | Content update pending
3 | Payment gateway timeout | Mike Johnson | 2026-03-12 | Finance Team | Critical | Open | 2026-03-18 | -7 | Priority escalation active
4 | Mobile app crash on checkout | Terence Lee | 2026-03-13 | Dev Team | High | Resolved | 2026-03-17 | -8 | Patched in release 2.1
5 | Missing product images | Chris Johnson | 2026-03-14 | Content Team | Low | In Progress | 2026-03-30 | 5 | Asset batch upload underway
6 | Shipping rules misaligned | Nina Patel | 2026-03-15 | Operations | Medium | Open | 2026-03-26 | 1 | Rules engine review scheduled
7 | Duplicate customer records | Alicia Green | 2026-03-16 | Data Team | High | Open | 2026-03-27 | 2 | Dedupe script being tested
8 | Training attendance below target | Miles Carter | 2026-03-17 | HR | Low | Open | 2026-04-05 | 11 | New sessions to be added
9 | BI dashboard refresh delay | Owen Brooks | 2026-03-18 | Analytics | Medium | In Progress | 2026-03-28 | 3 | Monitoring query performance
10 | Supplier SLA not signed | Emma Price | 2026-03-19 | Procurement | High | Open | 2026-04-02 | 8 | Legal follow-up underway

## KANBAN BOARD
KANBAN BOARD
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
TASK LIST |  |  |  |  | 2 | 2 | 6 | 4 | 0
Task | Assigned To | Priority | Due Date | Status | Incoming | To Do | In Progress | Completed | On Hold
Meet client leadership | Ava Reynolds | High | 2026-01-08 | Completed
Gather requirements | Liam Foster | High | 2026-01-15 | Completed
Current state analysis | Sophia Kim | Medium | 2026-01-20 | Completed
UX & service blueprint | Noah Bennett | High | 2026-02-05 | In Progress
Technical architecture | Elena Marquez | High | 2026-02-08 | In Progress
Vendor onboarding | Mia Carter | Medium | 2026-02-02 | Completed
Web front-end build | David Patel | High | 2026-03-12 | In Progress
Back-end integration | Emma Clark | High | 2026-03-18 | In Progress
Analytics implementation | Lucas Grant | Medium | 2026-03-22 | In Progress
Fulfilment workflow design | Harper Lewis | Medium | 2026-03-28 | Incoming
System integration testing | Ethan Brooks | High | 2026-04-03 | To Do
User acceptance testing | Grace Morgan | High | 2026-04-16 | To Do
Training content development | Olivia Young | Medium | 2026-04-20 | Incoming
Stakeholder communications | Aiden Ross | Medium | 2026-05-15 | In Progress

## PERT CHART DIAGRAM
PERT CHART DIAGRAM
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
PERT TEMPLATE
No. | Task Name | Dependency | Description | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Time (TE)
1 | A | 0 | Task 1 | 2 | 3 | 5 | 3.1667
2 | B | 0 | Task 2 | 1 | 2 | 3 | 2
3 | C | A | Task 3 | 4 | 6 | 8 | 6
4 | D | B | Task 4 | 3 | 4 | 6 | 4.1667
5 | E | C | Task 5 | 2 | 4 | 6 | 4
6 | F | D | Task 6 | 4 | 7 | 9 | 6.8333
7 | G | E,F | Task 7 | 6 | 7 | 8 | 7
DEPENDENCY MAP
Start Path A | A → C → E → G
Start Path B | B → D → F → G
Estimated Critical Path Time | 20.1667

## Budget Template
BUDGET TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
PROJECT BUDGET VS. ACTUALS
Budget | 575000
Actual | 463000
Under/(Over) | 575000
Month | Budget | Actual | Variance | Cumulative Budget | Cumulative Actual
Jan-26 | 65000 | 61200 | 3800 | 65000 | 61200
Feb-26 | 82000 | 80100 | 1900 | 147000 | 141300
Mar-26 | 91000 | 95300 | -4300 | 238000 | 236600
Apr-26 | 76000 | 71400 | 4600 | 314000 | 308000
May-26 | 88000 | 90200 | -2200 | 402000 | 398200
Jun-26 | 66000 | 64800 | 1200 | 468000 | 463000
Jul-26 | 30000 | 0 | 30000 | 498000 | 463000
Aug-26 | 22000 | 0 | 22000 | 520000 | 463000
Sep-26 | 18000 | 0 | 18000 | 538000 | 463000
Oct-26 | 15000 | 0 | 15000 | 553000 | 463000
Nov-26 | 12000 | 0 | 12000 | 565000 | 463000
Dec-26 | 10000 | 0 | 10000 | 575000 | 463000

## Project Financial Statement
PROJECT FINANCIAL STATEMENT
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
FINANCIAL TRANSACTIONS
Date | Type | Supplier | PO# | Description | Revenue Requested | Revenue Received | Commitment | PO Amount | Payment Made | Balance (Forecast) | Balance (Actual)
2026-01-05 | Discovery | NorthBridge Consulting | PO-1-12 | Meet client leadership | 16500 | 15000 | 13800 | 15000 | 14200 | 800 | 800
2026-01-09 | Requirements | NorthBridge Consulting | PO-2-13 | Gather requirements | 19800 | 18000 | 16560 | 18000 | 17600 | 400 | 400
2026-01-12 | Requirements | Meridian Advisory | PO-3-14 | Current state analysis | 13200 | 12000 | 11040 | 12000 | 11850 | 150 | 150
2026-01-21 | Design | Studio North | PO-4-15 | UX & service blueprint | 28600 | 26000 | 23920 | 26000 | 23800 | 2200 | 2200
2026-01-22 | Design | Vertex Systems | PO-5-16 | Technical architecture | 35200 | 32000 | 29440 | 32000 | 29800 | 2200 | 2200
2026-01-25 | Procurement | Aurelia Legal | PO-6-17 | Vendor onboarding | 9900 | 9000 | 8280 | 9000 | 9200 | -200 | -200
2026-02-06 | Build | PixelFoundry | PO-7-18 | Web front-end build | 59400 | 54000 | 49680 | 54000 | 37100 | 16900 | 16900
2026-02-10 | Build | CoreStack | PO-8-19 | Back-end integration | 74800 | 68000 | 62560 | 68000 | 40250 | 27750 | 27750
2026-02-18 | Data | BluePeak Data | PO-9-20 | Analytics implementation | 26400 | 24000 | 22080 | 24000 | 10950 | 13050 | 13050
2026-02-25 | Operations | FlowWorks | PO-10-21 | Fulfilment workflow design | 23100 | 21000 | 19320 | 21000 | 5100 | 15900 | 15900
TOTAL |  |  |  |  | 306900 | 279000 | 256680 | 279000 | 199850 | 79150 | 79150

## Multi Project Tracking
MULTIPLE PROJECT TRACKING TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
PROGRAM PORTFOLIO TRACKER
No. | Project Name | Task Description | Dependency | Assigned | Priority | Start Date | Planned End Date | Actual End Date | Estimated Cost | Actual Cost | Completion Percentage | Status
1 | Vertex zzzz | Meet client leadership | 0 | Ava Reynolds | High | 2026-01-05 | 2026-01-08 | 2026-01-08 | 15000 | 14200 | 100% | Completed
2 | Vertex zzzz | Gather requirements | 1 | Liam Foster | High | 2026-01-09 | 2026-01-15 | 2026-01-15 | 18000 | 17600 | 100% | Completed
3 | Vertex zzzz | Current state analysis | 2 | Sophia Kim | Medium | 2026-01-12 | 2026-01-20 | 2026-01-20 | 12000 | 11850 | 100% | Completed
4 | Vertex zzzz | UX & service blueprint | 2 | Noah Bennett | High | 2026-01-21 | 2026-02-05 |  | 26000 | 23800 | 85% | In Progress
5 | Vertex zzzz | Technical architecture | 2 | Elena Marquez | High | 2026-01-22 | 2026-02-08 |  | 32000 | 29800 | 80% | In Progress
6 | Vertex zzzz | Vendor onboarding | 4 | Mia Carter | Medium | 2026-01-25 | 2026-02-02 | 2026-02-02 | 9000 | 9200 | 100% | Completed
7 | Vertex zzzz | Web front-end build | 4 | David Patel | High | 2026-02-06 | 2026-03-12 |  | 54000 | 37100 | 65% | In Progress
8 | Vertex zzzz | Back-end integration | 5 | Emma Clark | High | 2026-02-10 | 2026-03-18 |  | 68000 | 40250 | 58% | In Progress
9 | Vertex zzzz | Analytics implementation | 5 | Lucas Grant | Medium | 2026-02-18 | 2026-03-22 |  | 24000 | 10950 | 45% | In Progress
10 | Vertex zzzz | Fulfilment workflow design | 3 | Harper Lewis | Medium | 2026-02-25 | 2026-03-28 |  | 21000 | 5100 | 25% | Started
11 | Vertex zzzz | System integration testing | 8 | Ethan Brooks | High | 2026-03-20 | 2026-04-03 |  | 15000 | 0 | 0% | Not Started
12 | Vertex zzzz | User acceptance testing | 11 | Grace Morgan | High | 2026-04-04 | 2026-04-16 |  | 12000 | 0 | 0% | Not Started
13 | Vertex zzzz | Training content development | 7 | Olivia Young | Medium | 2026-03-25 | 2026-04-20 |  | 8000 | 1600 | 20% | Started
14 | Vertex zzzz | Stakeholder communications | 4 | Aiden Ross | Medium | 2026-03-01 | 2026-05-15 |  | 14000 | 7100 | 50% | In Progress
15 | Vertex zzzz | Go-live planning | 12 | Chloe Hughes | High | 2026-04-20 | 2026-05-05 |  | 11000 | 0 | 0% | Not Started
16 | Vertex zzzz | Cutover rehearsal | 15 | Leo Turner | High | 2026-05-06 | 2026-05-12 |  | 9000 | 0 | 0% | Not Started

## Production Scheduling
PRODUCTION SCHEDULING
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
PRODUCTION SCHEDULING SHEET
Customer | Article | Quantity | Required Date | Possible Production Lines | Assigned Line | Schedule | Gap | Line 01 | Line 02 | Line 03 | Line 04 | Line 05 | Line 06 | Line 07 | Line 08 | Line 09
ABC Inc. | A | 5000 | 2026-01-02 | Line 01 ¦ Line 03 ¦ Line 06 | Line 01 | 5000 | 0 | 2500 | 0 | 1000 | 0 | 0 | 1500 | 0 | 0 | 0
XYZ LLC. | B | 500 | 2026-01-06 | Line 02 | Line 02 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MAC Traders | C | 200 | 2026-01-04 | Line 03 ¦ Line 08 | Line 03 | 200 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0
ABC Inc. | D | 3000 | 2026-01-04 | Line 01 ¦ Line 07 | Line 01 | 3000 | 0 | 2316 | 0 | 0 | 0 | 0 | 0 | 684 | 0 | 0
Material Masters | H | 1200 | 2026-01-05 | Line 02 ¦ Line 10 | Line 02 | 1200 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 300
MAC Traders | A | 1000 | 2026-03-05 | Line 01 ¦ Line 03 ¦ Line 06 | Line 01 | 1000 | 0 | 350 | 0 | 400 | 0 | 0 | 250 | 0 | 0 | 0
SYSTEMS Inc. | E | 500 | 2026-03-05 | Line 02 | Line 02 | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MORIS TRADERS LLC. | F | 400 | 2026-03-05 | Line 03 ¦ Line 09 | Line 03 | 400 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200
LINE CAPACITY HOURS CALCULATION SHEET
Line | Capacity Hours | Efficiency % | Scheduled Net Hrs | Scheduled Gross Hrs | Gap Hours | Planned Utilization %
Line 01 | 171 | 90% | 115.4 | 128.3 | 42.7 | 67.49%
Line 02 | 171 | 90% | 38.6 | 42.9 | 128.1 | 22.57%
Line 03 | 166 | 95% | 146.9 | 154.6 | 11.4 | 88.49%
Line 04 | 171 | 85% | 0 | 0 | 171 | 0%
Line 05 | 166 | 85% | 0 | 0 | 166 | 0%
Line 06 | 151 | 90% | 38.9 | 43.2 | 107.8 | 25.76%
Line 07 | 171 | 90% | 12.4 | 13.8 | 157.2 | 7.251%
Line 08 | 146 | 85% | 2.5 | 2.9 | 143.1 | 1.712%
Line 09 | 164 | 80% | 2.9 | 3.6 | 160.4 | 1.768%
Line 10 | 171 | 85% | 10 | 11.8 | 159.2 | 5.848%

## Project Budget Cost Tracker
PROJECT BUDGET COST TRACKER
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz | [5 empty] | STATISTICS
Project Manager | Elena zzzz | [5 empty] | Total Tasks | 14
Prepared By | Noah Sam Bennett | [5 empty] | Completed | 4
Start Date | 2026-01-05 | [5 empty] | In Progress | 6
End Date | 2026-06-30 | [5 empty] | Pending | 2
[7 empty] | Overall Completion % | 59.14%
PROJECT BUDGETED COST TRACKER
Category | Task Name | Vendor | Planned Cost | Actual Cost | Variance (+/-) | % Complete | Completion Status | Due Date | Comments/Notes | Department
Discovery | Meet client leadership | NorthBridge Consulting | 15000 | 14200 | 800 | 100% | Completed | 2026-01-08 | Kickoff completed | IT
Requirements | Gather requirements | NorthBridge Consulting | 18000 | 17600 | 400 | 100% | Completed | 2026-01-15 | Signed requirements pack | Customer Service
Requirements | Current state analysis | Meridian Advisory | 12000 | 11850 | 150 | 100% | Completed | 2026-01-20 | Baseline documented | Operations
Design | UX & service blueprint | Studio North | 26000 | 23800 | 2200 | 85% | In Progress | 2026-02-05 | Executive review pending | Marketing
Design | Technical architecture | Vertex Systems | 32000 | 29800 | 2200 | 80% | In Progress | 2026-02-08 | Infra design in review | Engineering
Procurement | Vendor onboarding | Aurelia Legal | 9000 | 9200 | -200 | 100% | Completed | 2026-02-02 | Contracts signed | Finance
Build | Web front-end build | PixelFoundry | 54000 | 37100 | 16900 | 65% | In Progress | 2026-03-12 | Sprint 4 live | Engineering
Build | Back-end integration | CoreStack | 68000 | 40250 | 27750 | 58% | In Progress | 2026-03-18 | APIs partially complete | Engineering
Data | Analytics implementation | BluePeak Data | 24000 | 10950 | 13050 | 45% | In Progress | 2026-03-22 | Tagging underway | IT
Operations | Fulfilment workflow design | FlowWorks | 21000 | 5100 | 15900 | 25% | Started | 2026-03-28 | Workshop series underway | Operations
Testing | System integration testing | QA Labs | 15000 | 0 | 15000 | 0% | Not Started | 2026-04-03 | 0 | QA
Testing | User acceptance testing | QA Labs | 12000 | 0 | 12000 | 0% | Not Started | 2026-04-16 | 0 | QA
Training | Training content development | BrightPath Learning | 8000 | 1600 | 6400 | 20% | Started | 2026-04-20 | 0 | Human Resources
Change | Stakeholder communications | Storyline Comms | 14000 | 7100 | 6900 | 50% | In Progress | 2026-05-15 | 0 | Marketing

## Project Budget Review Template
PROJECT BUDGET REVIEW TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
BUDGET REVIEW
Description | Status | Planned Start Date | Actual Start Date | End Date | Hours | $/HR | Labor Total | Units | $/Unit | Material Total | Travel | Equipment | Fixed | Budget | Actual
Meet client leadership | Completed | 2026-01-05 | 2026-01-05 | 2026-01-08 | 4 | 3750 | 15000 | 4 | 1125 | 4500 | 450 | 750 | 300 | 15000 | 14200
Gather requirements | Completed | 2026-01-09 | 2026-01-09 | 2026-01-15 | 7 | 2571 | 17997 | 7 | 771 | 5397 | 540 | 900 | 360 | 18000 | 17600
Current state analysis | Completed | 2026-01-12 | 2026-01-12 | 2026-01-20 | 9 | 1333 | 11997 | 9 | 400 | 3600 | 360 | 600 | 240 | 12000 | 11850
UX & service blueprint | In Progress | 2026-01-21 | 2026-01-21 | 2026-02-05 | 16 | 1625 | 26000 | 16 | 488 | 7808 | 780 | 1300 | 520 | 26000 | 23800
Technical architecture | In Progress | 2026-01-22 | 2026-01-22 | 2026-02-08 | 18 | 1778 | 32004 | 18 | 533 | 9594 | 960 | 1600 | 640 | 32000 | 29800
Vendor onboarding | Completed | 2026-01-25 | 2026-01-25 | 2026-02-02 | 9 | 1000 | 9000 | 9 | 300 | 2700 | 270 | 450 | 180 | 9000 | 9200
Web front-end build | In Progress | 2026-02-06 | 2026-02-06 | 2026-03-12 | 35 | 1543 | 54005 | 35 | 463 | 16205 | 1620 | 2700 | 1080 | 54000 | 37100
Back-end integration | In Progress | 2026-02-10 | 2026-02-10 | 2026-03-18 | 37 | 1838 | 68006 | 37 | 551 | 20387 | 2040 | 3400 | 1360 | 68000 | 40250
Analytics implementation | In Progress | 2026-02-18 | 2026-02-18 | 2026-03-22 | 33 | 727 | 23991 | 33 | 218 | 7194 | 720 | 1200 | 480 | 24000 | 10950
Fulfilment workflow design | Started | 2026-02-25 | 2026-02-25 | 2026-03-28 | 32 | 656 | 20992 | 32 | 197 | 6304 | 630 | 1050 | 420 | 21000 | 5100
System integration testing | Not Started | 2026-03-20 |  | 2026-04-03 | 15 | 1000 | 15000 | 15 | 300 | 4500 | 450 | 750 | 300 | 15000 | 0
User acceptance testing | Not Started | 2026-04-04 |  | 2026-04-16 | 13 | 923 | 11999 | 13 | 277 | 3601 | 360 | 600 | 240 | 12000 | 0
Formulas:
Actual Start Date = IF([Status]="Not Started","",'Data Sheet'!J20)

## Project Calendar
PROJECT CALENDAR - ACTIVITIES TIME LINE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
ACTIVITY LIST |  |  |  | TIMELINE
No. | Start Date | End Date | Task | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20
1 | 2026-01-05 | 2026-01-08 | Meet client leadership | 1
2 | 2026-01-09 | 2026-01-15 | Gather requirements |  | 1
3 | 2026-01-12 | 2026-01-20 | Current state analysis |  | 1 | 1
4 | 2026-01-21 | 2026-02-05 | UX & service blueprint |  |  |  | 1 | 1
5 | 2026-01-22 | 2026-02-08 | Technical architecture |  |  |  | 1 | 1
6 | 2026-01-25 | 2026-02-02 | Vendor onboarding |  |  |  | 1 | 1
7 | 2026-02-06 | 2026-03-12 | Web front-end build | [5 empty] | 1 | 1 | 1 | 1 | 1
8 | 2026-02-10 | 2026-03-18 | Back-end integration | [6 empty] | 1 | 1 | 1 | 1 | 1
9 | 2026-02-18 | 2026-03-22 | Analytics implementation | [7 empty] | 1 | 1 | 1 | 1
10 | 2026-02-25 | 2026-03-28 | Fulfilment workflow design | [8 empty] | 1 | 1 | 1 | 1
11 | 2026-03-20 | 2026-04-03 | System integration testing | [11 empty] | 1 | 1

## Project Charter
PROJECT CHARTER TEMPLATE WITH EXAMPLE DATA
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
PROJECT DETAILS
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Project Sponsor | Jonathan zzz
Prepared By | Noah Sam Bennett
Project Start Date | 2026-01-05
Expected Completion Date | 2026-06-30
PROJECT OVERVIEW
This project modernizes web, analytics, operations, and customer support processes under one execution plan.
PROJECT SCOPE
• Meet client leadership • Gather requirements • Current state analysis • UX & service blueprint • Technical architecture
PROJECT KEY INFORMATION
Business Case | The investment supports growth, operating efficiency, and customer experience improvements across sales, service, and fulfilment.
Goals & Objectives | Launch an integrated commerce platform, improve digital conversion, and reduce fulfilment cycle time.
Stakeholders | • Executive Sponsor • Project Manager • Workstream Leads • Operations • QA • Customers
Timeline & Budget | Project timeline: Jan 5, 2026 to Jun 30, 2026 Baseline budget: $408,000
Anticipated Deliverables | • Discovery package • Solution design • Built platform • UAT sign-off • Go-live & hypercare
Project Team and Roles | • Executive Sponsor – Jonathan zzz • Project Manager – Elena zzzz • Core Team – Design, Engineering, Operations, QA

## Project Cost Control Template
PROJECT COST CONTROL TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
COST CONTROL
Task | Description | Budgeted Qty | Unit Type | Value | Actual Qty | Unit Type | Value | Budgeted Cost | Actual Cost | Variance
Discovery | Meet client leadership | 4 | "Days" | 3750 | 4 | "Days" | 3550 | 15000 | 14200 | 800
Requirements | Gather requirements | 7 | "Days" | 2571 | 7 | "Days" | 2514 | 18000 | 17600 | 400
Requirements | Current state analysis | 9 | "Days" | 1333 | 9 | "Days" | 1317 | 12000 | 11850 | 150
Design | UX & service blueprint | 16 | "Days" | 1625 | 17 | "Days" | 1400 | 26000 | 23800 | 2200
Design | Technical architecture | 18 | "Days" | 1778 | 19 | "Days" | 1568 | 32000 | 29800 | 2200
Procurement | Vendor onboarding | 9 | "Days" | 1000 | 9 | "Days" | 1022 | 9000 | 9200 | -200
Build | Web front-end build | 35 | "Days" | 1543 | 37 | "Days" | 1003 | 54000 | 37100 | 16900
Build | Back-end integration | 37 | "Days" | 1838 | 39 | "Days" | 1032 | 68000 | 40250 | 27750
Data | Analytics implementation | 33 | "Days" | 727 | 35 | "Days" | 313 | 24000 | 10950 | 13050
Operations | Fulfilment workflow design | 32 | "Days" | 656 | 34 | "Days" | 150 | 21000 | 5100 | 15900
Testing | System integration testing | 15 | "Days" | 1000 | 16 | "Days" | 0 | 15000 | 0 | 15000
Testing | User acceptance testing | 13 | "Days" | 923 | 14 | "Days" | 0 | 12000 | 0 | 12000
Training | Training content development | 27 | "Days" | 296 | 28 | "Days" | 57 | 8000 | 1600 | 6400
Change | Stakeholder communications | 76 | "Days" | 184 | 80 | "Days" | 89 | 14000 | 7100 | 6900
Launch | Go-live planning | 16 | "Days" | 688 | 17 | "Days" | 0 | 11000 | 0 | 11000
Launch | Cutover rehearsal | 7 | "Days" | 1286 | 7 | "Days" | 0 | 9000 | 0 | 9000
Launch | Production deployment | 3 | "Days" | 8333 | 3 | "Days" | 0 | 25000 | 0 | 25000
Support | Hypercare support | 21 | "Days" | 857 | 22 | "Days" | 0 | 18000 | 0 | 18000

## Project Cost Estimate
PROJECT COST ESTIMATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
COMPANY / CUSTOMER
Company Name | Aurelia zzzz
Customer | Northwind Retail Group
Project Manager | Elena zzzz
Estimation Date | 2026-03-25
Valid Until | 2026-04-24
PROJECT DESCRIPTION
The investment supports growth, operating efficiency, and customer experience improvements across sales, service, and fulfilment.
PROJECT PHASE 1
Activity | Vendor/Contractor | Hours | Labor | Materials | Equipment | Overheads | Total | Notes
Meet client leadership | NorthBridge Consulting | 4 | 6000 | 4500 | 3000 | 1500 | 15000 | Kickoff completed
Gather requirements | NorthBridge Consulting | 7 | 7200 | 5400 | 3600 | 1800 | 18000 | Signed requirements pack
Current state analysis | Meridian Advisory | 9 | 4800 | 3600 | 2400 | 1200 | 12000 | Baseline documented
UX & service blueprint | Studio North | 16 | 10400 | 7800 | 5200 | 2600 | 26000 | Executive review pending
Technical architecture | Vertex Systems | 18 | 12800 | 9600 | 6400 | 3200 | 32000 | Infra design in review
Sub Total | [6 empty] | 103000
PROJECT PHASE 2
Activity | Vendor/Contractor | Hours | Labor | Materials | Equipment | Overheads | Total | Notes
Vendor onboarding | Aurelia Legal | 9 | 3600 | 2700 | 1800 | 900 | 9000 | Contracts signed
Web front-end build | PixelFoundry | 35 | 21600 | 16200 | 10800 | 5400 | 54000 | Sprint 4 live
Back-end integration | CoreStack | 37 | 27200 | 20400 | 13600 | 6800 | 68000 | APIs partially complete
Analytics implementation | BluePeak Data | 33 | 9600 | 7200 | 4800 | 2400 | 24000 | Tagging underway
Fulfilment workflow design | FlowWorks | 32 | 8400 | 6300 | 4200 | 2100 | 21000 | Workshop series underway
Sub Total | [6 empty] | 176000
PROJECT PHASE 3
Activity | Vendor/Contractor | Hours | Labor | Materials | Equipment | Overheads | Total | Notes
System integration testing | QA Labs | 15 | 6000 | 4500 | 3000 | 1500 | 15000 | 0
User acceptance testing | QA Labs | 13 | 4800 | 3600 | 2400 | 1200 | 12000 | 0
Training content development | BrightPath Learning | 27 | 3200 | 2400 | 1600 | 800 | 8000 | 0
Stakeholder communications | Storyline Comms | 76 | 5600 | 4200 | 2800 | 1400 | 14000 | 0
Go-live planning | FlowWorks | 16 | 4400 | 3300 | 2200 | 1100 | 11000 | 0
Sub Total | [6 empty] | 60000
PROJECT PHASE 4
Activity | Vendor/Contractor | Hours | Labor | Materials | Equipment | Overheads | Total | Notes
Cutover rehearsal | Vertex Systems | 7 | 3600 | 2700 | 1800 | 900 | 9000 | 0
Production deployment | CoreStack | 3 | 10000 | 7500 | 5000 | 2500 | 25000 | 0
Hypercare support | NorthBridge Consulting | 21 | 7200 | 5400 | 3600 | 1800 | 18000 | 0
Post-launch analytics | BluePeak Data | 15 | 4000 | 3000 | 2000 | 1000 | 10000 | 0
Benefits handover & closure | Meridian Advisory | 10 | 2800 | 2100 | 1400 | 700 | 7000 | 0
Sub Total | [6 empty] | 69000
ASSUMPTIONS AND CONSTRAINTS
• Costs are indicative and based on current scope. • External supplier rates may vary by contract. • Taxes and freight are excluded unless specified.

## Project Cost Tracker
PROJECT COST TRACKER
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz |  |  |  | STATISTICS
Project Manager | Elena zzzz |  |  |  | Total Tasks | 14
Prepared By | Noah Sam Bennett |  |  |  | Completed | 4
Start Date | 2026-01-05 |  |  |  | In Progress | 6
End Date | 2026-06-30 |  |  |  | Pending | 2
[5 empty] | Started | 2
COST TRACKER
Category | Task Name | Vendor | Planned Cost | Actual Cost | Variance (+/-) | % Complete | Completion Status | Due Date | Comments/Notes
Discovery | Meet client leadership | NorthBridge Consulting | 15000 | 14200 | 800 | 100% | Completed | 2026-01-08 | Kickoff completed
Requirements | Gather requirements | NorthBridge Consulting | 18000 | 17600 | 400 | 100% | Completed | 2026-01-15 | Signed requirements pack
Requirements | Current state analysis | Meridian Advisory | 12000 | 11850 | 150 | 100% | Completed | 2026-01-20 | Baseline documented
Design | UX & service blueprint | Studio North | 26000 | 23800 | 2200 | 85% | In Progress | 2026-02-05 | Executive review pending
Design | Technical architecture | Vertex Systems | 32000 | 29800 | 2200 | 80% | In Progress | 2026-02-08 | Infra design in review
Procurement | Vendor onboarding | Aurelia Legal | 9000 | 9200 | -200 | 100% | Completed | 2026-02-02 | Contracts signed
Build | Web front-end build | PixelFoundry | 54000 | 37100 | 16900 | 65% | In Progress | 2026-03-12 | Sprint 4 live
Build | Back-end integration | CoreStack | 68000 | 40250 | 27750 | 58% | In Progress | 2026-03-18 | APIs partially complete
Data | Analytics implementation | BluePeak Data | 24000 | 10950 | 13050 | 45% | In Progress | 2026-03-22 | Tagging underway
Operations | Fulfilment workflow design | FlowWorks | 21000 | 5100 | 15900 | 25% | Started | 2026-03-28 | Workshop series underway
Testing | System integration testing | QA Labs | 15000 | 0 | 15000 | 0% | Not Started | 2026-04-03 | 0
Testing | User acceptance testing | QA Labs | 12000 | 0 | 12000 | 0% | Not Started | 2026-04-16 | 0
Training | Training content development | BrightPath Learning | 8000 | 1600 | 6400 | 20% | Started | 2026-04-20 | 0
Change | Stakeholder communications | Storyline Comms | 14000 | 7100 | 6900 | 50% | In Progress | 2026-05-15 | 0

## Change Log Template
CHANGE LOG TEMPLATE
This template is linked to 'Data Sheet'. Update source inputs there and all linked templates refresh automatically.
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Prepared By | Noah Sam Bennett
Start Date | 2026-01-05
End Date | 2026-06-30
DOCUMENT CONTROL
Version | Date | Project Name | Document Name | Prepared By | Approved By
1.0 | 2026-01-10 | Vertex Commerce Transformation | Project Charter | Noah Bennett | Jonathan Hale
1.1 | 2026-02-05 | Vertex Commerce Transformation | Solution Design | Elena Marquez | Jonathan Hale
1.2 | 2026-02-18 | Vertex Commerce Transformation | Budget Baseline | Mia Carter | Jonathan Hale
1.3 | 2026-03-01 | Vertex Commerce Transformation | Cutover Plan | Leo Turner | Jonathan Hale
CHANGE REGISTER
Version | Date Identified | Type of Change | Change Description | Priority | Expected Resolution | Date Work Initiated | Action | Impact | Rollback Plan | Status | Needs Escalation | Dependencies | Sign Off | Remarks
1.0 | 2026-01-10 | Scope | Added analytics workstream | High | 2026-01-15 | 2026-01-11 | Update plan | High | Prepared rollback plan | Closed | Yes | Project Charter | Jonathan Hale | Approved
1.1 | 2026-02-05 | Requirement | Expanded API security controls | Medium | 2026-02-14 | 2026-02-06 | Revise design | Medium | Monitor closely | Open | No | Solution Design | Jonathan Hale | In review
1.2 | 2026-02-18 | Budget | Additional testing budget | High | 2026-02-25 | 2026-02-19 | Submit CR | High | Prepared rollback plan | Open | Yes | Budget Baseline | Jonathan Hale | Pending finance
1.3 | 2026-03-01 | Schedule | Shifted launch rehearsal | Medium | 2026-03-07 | 2026-03-02 | Resequence tasks | Low | Monitor closely | Open | No | Cutover Plan | Jonathan Hale | Dependency update
1.4 | 2026-03-09 | Resource | Added contract trainers | Low | 2026-03-15 | 2026-03-10 | Onboard trainers | Low | Monitor closely | Closed | No | Training Plan | Jonathan Hale | Completed
1.5 | 2026-03-14 | Risk | Raised payment gateway risk | Critical | 2026-03-17 | 2026-03-14 | Escalate vendor | Critical | Monitor closely | Open | Yes | Risk Register | Jonathan Hale | War room active
1.6 | 2026-03-18 | Data | Refined cleanse criteria | Medium | 2026-03-22 | 2026-03-18 | Update rules | Medium | Monitor closely | Open | No | Data Migration Plan | Jonathan Hale | 0
1.7 | 2026-03-20 | Process | Extended hypercare window | Low | 2026-03-23 | 2026-03-20 | Revise SOP | Low | Monitor closely | Closed | No | Support Model | Jonathan Hale | Signed off
1.8 | 2026-03-22 | Technical | Hotfix branch included | High | 2026-03-24 | 2026-03-22 | Patch deploy | High | Prepared rollback plan | Open | Yes | Release Notes | Jonathan Hale | 0
1.9 | 2026-03-24 | Communication | New launch messaging | Low | 2026-03-29 | 2026-03-24 | Update comms | Low | Monitor closely | Open | No | Comms Pack | Jonathan Hale | 0

## Project Cost Trend Analysis
PROJECT COST TREND ANALYSIS
| Project Name |  | Vertex zzzz
| Project Manager |  | Elena zzzz
| Project Duration |  | 6
| Weight Factor |  | 1.2
| Year |  | 2026
| Project Cost Data | [5 empty] | Cost Trend Analysis
| Budget | YTD Prev | YTD Curr | ETC | Rev Forecast | Variance | Straight Line | Var (I-K) | Weighted | ETC
| 225000 | 145000 | 190000 | 200000 | 390000 | 165000 | 37500 | -45000 | 228000 | -3000
Project | Budget | YTD Prev | YTD Curr | ETC | Rev Forecast | Variance | Straight Line | Var (I-K) | Weighted | ETC
Project 1 | 50000 | 30000 | 40000 | 50000 | 90000 | 40000 | 8333.3333 | -10000 | 48000 | 2000
Project 2 | 100000 | 75000 | 90000 | 80000 | 170000 | 70000 | 16666.6667 | -15000 | 108000 | -8000
Project 3 | 75000 | 40000 | 60000 | 70000 | 130000 | 55000 | 12500 | -20000 | 72000 | 3000

## Project Dashboard
Project Dashboard
Status | Count |  |  | Resource | Tasks
Complete | 4 |  |  | Person 1 | 1
In Progress | 6 |  |  | Person 2 | 1
Not Started | 8 |  |  | Person 3 | 1
Overdue | 5 |  |  | Person 4 | 1
|  |  |  | Person 5 | 1
|  |  |  | Person 6 | 1
|  |  |  | Person 7 | 1
|  |  |  | Person 8 | 1
Project Name |  | Vertex zzzz | [6 empty] | No. of Projects | 1
Project Manager |  | Elena zzzz
Start Date |  | 2026-01-05 | [6 empty] | Not Started | 8
End Date |  | 2026-06-30 | [6 empty] | In Progress | 6
Duration |  | 177 | [6 empty] | Complete | 4
[9 empty] | Overdue | 5
[9 empty] | Planned Cost | 408000
[9 empty] | Actual Cost | 208550
[9 empty] | Variance | 199450
Tasks | Assigned To | Start | End | Days | Status | Planned Cost | Actual Cost | Notes
Meet client leadership | Ava Reynolds | 2026-01-05 | 2026-01-08 | 4 | Completed | 15000 | 14200 | Kickoff completed
Gather requirements | Liam Foster | 2026-01-09 | 2026-01-15 | 7 | Completed | 18000 | 17600 | Signed requirements pack
Current state analysis | Sophia Kim | 2026-01-12 | 2026-01-20 | 9 | Completed | 12000 | 11850 | Baseline documented
UX & service blueprint | Noah Bennett | 2026-01-21 | 2026-02-05 | 16 | In Progress | 26000 | 23800 | Executive review pending
Technical architecture | Elena Marquez | 2026-01-22 | 2026-02-08 | 18 | In Progress | 32000 | 29800 | Infra design in review
Vendor onboarding | Mia Carter | 2026-01-25 | 2026-02-02 | 9 | Completed | 9000 | 9200 | Contracts signed
Web front-end build | David Patel | 2026-02-06 | 2026-03-12 | 35 | In Progress | 54000 | 37100 | Sprint 4 live
Back-end integration | Emma Clark | 2026-02-10 | 2026-03-18 | 37 | In Progress | 68000 | 40250 | APIs partially complete
Analytics implementation | Lucas Grant | 2026-02-18 | 2026-03-22 | 33 | In Progress | 24000 | 10950 | Tagging underway
Fulfilment workflow design | Harper Lewis | 2026-02-25 | 2026-03-28 | 32 | Started | 21000 | 5100 | Workshop series underway
Task | Planned | Actual
Meet client leadership | 15000 | 14200
Gather requirements | 18000 | 17600
Current state analysis | 12000 | 11850
UX & service blueprint | 26000 | 23800
Technical architecture | 32000 | 29800
Vendor onboarding | 9000 | 9200
Web front-end build | 54000 | 37100
Back-end integration | 68000 | 40250
Analytics implementation | 24000 | 10950
Fulfilment workflow design | 21000 | 5100

## Project Proposal Cost
Project Proposal Cost
[6 empty] | Project Lead |  | Elena zzzz |  | Total Estimated Cost
[6 empty] | Start Date |  | 2026-01-05 |  | 1832.5
[6 empty] | End Date |  | 2026-06-30
Tasks | Hrs | Rate | Value | Units | $/Unit | Value | Material | Travel | Other | Cost
Task | 0 | 0 | 0 | 10 | 5.5 | 55 | 0 | 300 | 0 | 355
Task | 0 | 0 | 0 | 25 | 4.5 | 112.5 | 0 | 0 | 0 | 112.5
Task | 5 | 25 | 125 | 0 | 0 | 0 | 0 | 250 | 0 | 375
Sub Task | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100
Sub Task | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20
Sub Task | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 125
Task | 7 | 35 | 245 | 0 | 0 | 0 | 500 | 0 | 0 | 745
Phase or Category Title
Phase or Category Title

## Project Proposal Cost Template
Project Proposal Cost Template
[6 empty] | Project Lead |  | Elena zzzz |  | Total Estimated Cost
[6 empty] | Start Date |  | 2026-01-05 |  | 1832.5
[6 empty] | End Date |  | 2026-06-30
Tasks | Hrs | Rate | Value | Units | $/Unit | Value | Material | Travel | Other | Cost
Task | 0 | 0 | 0 | 10 | 5.5 | 55 | 0 | 300 | 0 | 355
Task | 0 | 0 | 0 | 25 | 4.5 | 112.5 | 0 | 0 | 0 | 112.5
Task | 5 | 25 | 125 | 0 | 0 | 0 | 0 | 250 | 0 | 375
Sub Task | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100
Sub Task | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20
Sub Task | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 125
Task | 7 | 35 | 245 | 0 | 0 | 0 | 500 | 0 | 0 | 745
Phase or Category Title
Phase or Category Title

## Resource Planning Template
Resource Planning Template
Project Name | Vertex zzzz
Project Manager | Elena zzzz
Customer | Aurelia zzzz
Date | 2026-03-25
Resource | Department | Total Hours | Rate / Hr | Amount | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Jack | Marketing | 184 | 25 | 4600 | 48 | 16 | 20 | 30 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Simon | Sales | 88 | 30 | 2640 | 4 | 44 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0
Shaun | Design | 118 | 25 | 2950 | 20 | 50 | 18 | 9 | 5 | 0 | 8 | 8 | 0 | 0 | 0 | 0
Julia | Development | 73 | 40 | 2920 | 19 | 17 | 20 | 10 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Resource | Annual Hours
Jack | 184
Simon | 88
Shaun | 118
Julia | 73

## Project Status Report
PROJECT STATUS REPORT
| Project Name |  | Vertex zzzz
| Project Manager |  | Elena zzzz
| Start Date |  | 2026-01-05
| End Date |  | 2026-06-30
| Last Updated |  | 2026-03-25
Project Current Status
Overall Health | Plan | Costs | Scope | Benefits | Quality | Resources
Amber | Green | Red | Green | Amber | Red | Green
Deliverables from previous reporting period |  |  | Deliverables due in the next reporting period |  |  | Sponsor / Financials |  | Business / Benefits
Kickoff completed |  |  | UX & service blueprint - 2/5/2026 |  |  | Sponsor | Jonathan zzz | Business Unit | Transformation Office
Signed requirements pack |  |  | Technical architecture - 2/8/2026 |  |  | Budget | 408000 | Benefits | Improved customer experience, faster cycle time, and stronger conversion performance.
Baseline documented |  |  | Vendor onboarding - 2/2/2026 |  |  | Forecast | 208550 | Expected Go Live Date | 2026-06-30
[6 empty] | Actual Spend | 208550 | Current Stage | Execution
[6 empty] | Variance | 199450 | Stage End Date | 2026-06-30
Risk / Issue | Risk / Issue ID | Risk / Issue Name | Description | Mitigation / Resolution Plan | Owner | Target Closure Date
In Progress | 1 | Website login not working | Website login not working | Mitigation action in progress | IT Team | 2026-03-20
On Hold | 2 | Broken link on homepage | Broken link on homepage | Mitigation action in progress | Web Team | 2026-03-25
Open | 3 | Payment gateway timeout | Payment gateway timeout | Mitigation action in progress | Finance Team | 2026-03-18
Resolved | 4 | Mobile app crash on checkout | Mobile app crash on checkout | Mitigation action in progress | Dev Team | 2026-03-17
In Progress | 5 | Missing product images | Missing product images | Mitigation action in progress | Content Team | 2026-03-30

## Project Timeline Template
PROJECT TIMELINE TEMPLATE
| Project Name |  | Vertex zzzz
| Project Manager |  | Elena zzzz
| Project Duration |  | Months / Days
Task Name | Sub Task Name | Status | Assigned To | Start Date | End Date | Duration | Comments | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31
Meet client leadership |  | Completed | Ava Reynolds | 2026-01-05 | 2026-01-08 | 4 | Kickoff completed | bar: 2026-01-05 to 2026-01-08
Gather requirements |  | Completed | Liam Foster | 2026-01-09 | 2026-01-15 | 7 | Signed requirements pack | bar: 2026-01-09 to 2026-01-15
Current state analysis |  | Completed | Sophia Kim | 2026-01-12 | 2026-01-20 | 9 | Baseline documented | bar: 2026-01-12 to 2026-01-20
UX & service blueprint |  | In Progress | Noah Bennett | 2026-01-21 | 2026-02-05 | 16 | Executive review pending | bar: 2026-01-21 to 2026-01-31
Technical architecture |  | In Progress | Elena Marquez | 2026-01-22 | 2026-02-08 | 18 | Infra design in review | bar: 2026-01-22 to 2026-01-31
Vendor onboarding |  | Completed | Mia Carter | 2026-01-25 | 2026-02-02 | 9 | Contracts signed | bar: 2026-01-25 to 2026-01-31
Web front-end build |  | In Progress | David Patel | 2026-02-06 | 2026-03-12 | 35 | Sprint 4 live
Back-end integration |  | In Progress | Emma Clark | 2026-02-10 | 2026-03-18 | 37 | APIs partially complete
Analytics implementation |  | In Progress | Lucas Grant | 2026-02-18 | 2026-03-22 | 33 | Tagging underway
Fulfilment workflow design |  | Started | Harper Lewis | 2026-02-25 | 2026-03-28 | 32 | Workshop series underway
System integration testing |  | Not Started | Ethan Brooks | 2026-03-20 | 2026-04-03 | 15 | 0
User acceptance testing |  | Not Started | Grace Morgan | 2026-04-04 | 2026-04-16 | 13 | 0
Training content development |  | Started | Olivia Young | 2026-03-25 | 2026-04-20 | 27 | 0
Stakeholder communications |  | In Progress | Aiden Ross | 2026-03-01 | 2026-05-15 | 76 | 0
Go-live planning |  | Not Started | Chloe Hughes | 2026-04-20 | 2026-05-05 | 16 | 0
Cutover rehearsal |  | Not Started | Leo Turner | 2026-05-06 | 2026-05-12 | 7 | 0
Production deployment |  | Not Started | Zoe Evans | 2026-05-13 | 2026-05-15 | 3 | 0

## Project Prioritization Template
Project Prioritization Template
PRIORITIZATION MATRIX
| Date | 2026-03-25 | Act Now |  | Postpone
| Prepared by | Noah Sam Bennett
|  |  |  | Project 6 |  | Project 1
No. | Task | Priority |  | Project 10 |  | Project 2
1 | Project 1 | Postpone |  | Project 14 |  | Project 7
2 | Project 2 | Postpone |  |  |  | Project 11
3 | Project 3 | Outsource
4 | Project 4 | Discard
5 | Project 5 | Discard
6 | Project 6 | Act Now | Outsource |  | Discard
7 | Project 7 | Postpone
8 | Project 8 | Outsource |  | Project 3 |  | Project 4
9 | Project 9 | Discard |  | Project 8 |  | Project 5
10 | Project 10 | Act Now |  | Project 12 |  | Project 9
11 | Project 11 | Postpone |  |  |  | Project 13
12 | Project 12 | Outsource
13 | Project 13 | Discard
14 | Project 14 | Act Now

## Punch List Template
Punch List Template
Project Name |  | Vertex zzzz
Location |  | Chicago,zzzz
Date |  | 2026-03-25
Prepared by |  | Noah Sam Bennett
Item No. | Description of Work | Location/Room | Type | Responsible Contractor | Due Date | Status (Open/Closed) | Notes/Comments
1 | Paint touch-ups – wall scratches | Living Room | Maintenance | ABC Painting | 2026-04-01 | In Progress | Match existing color
2 | Loose handrail – needs tightening | Staircase | Maintenance | XYZ Carpentry | 2026-04-03 | Closed | Check all bolts
3 | HVAC vent not functioning | Primary Bedroom | Maintenance | CoolAir Inc. | 2026-03-30 | To Be Confirmed | Thermostat sync issue
4 | Missing cabinet hardware | Kitchen | Maintenance | Cabinet Masters | 2026-03-31 | In Progress | Install handles per specs
5 | Cracked tile replacement | Bathroom Floor | Maintenance | Tile Pros | 2026-03-29 | Open | Use matching grout
Sign-Off Section:
Contractor Approval
Client Approval
Remarks

## RACI Matrix Template
RACI Matrix Template
RACI Definitions
Project / Initiative | Vertex zzzz | [8 empty] | Responsible | Who performs the task? (Doer)
Project Manager | Elena zzzz | [8 empty] | Accountable | Who has final authority and ownership?
Last Updated | 46106 | [8 empty] | Consulted | Who provides input or expertise?
Version | 1.0 | [8 empty] | Informed | Who needs to be kept updated?
When to Use This Advanced Template: Complex projects with cross-functional teams. Regulatory/compliance-heavy initiatives. Hybrid projects where clarity on handoffs is critical.
Who | Project Role | Requirement Finalization | API Development | User Acceptance Testing | Deployment | Training | Hypercare | Benefits Handover | Closure
James Carter | Project Manager | R | A | I | 0 | 0 | 0 | 0 | 0
Clive Morgan | Business Analyst | 0 | R | A | C | 0 | 0 | 0 | 0
Trevor Hughes | Executive Sponsor | I | I | 0 | A | 0 | 0 | 0 | 0
Chris Nolan | Developer | C | 0 | R | R | A | 0 | 0 | 0
Ava Ross | QA Lead | 0 | C | R | I | R | A | 0 | 0
Mason Bell | Operations Lead | I | 0 | 0 | C | I | R | A | 0

## Resource Plan Template
Resource Plan Template | [9 empty] | Legends
Balanced
Project Name |  | Vertex zzzz | [8 empty] | Underutilized
Impact Assessment |  | Weighted Allocation | [8 empty] | Overutilized
Timeframe |  | 5 Jan 2026 to 30 Jun 2026
Skill Area | Designated Owner | Resource Type | Define (WTE) | Design (WTE) | Build (WTE) | Deploy (WTE) | Close (WTE) | Total FTE | Notes
Project Manager | Elena Marquez | Internal | 1 | 1 | 0.8 | 0.5 | 0.2 | 3.5
Implementation | Noah Bennett | External | 0.5 | 1.2 | 2 | 2 | 0.1 | 5.8
Business Change & Benefits | Olivia Young | Internal | 0.2 | 0.4 | 0.5 | 0.3 | 0.2 | 1.6
Training | Grace Morgan | Internal | 0.1 | 0.2 | 0.4 | 0.8 | 0.3 | 1.8
IT Services Support | Zoe Evans | Internal | 0.1 | 0.4 | 1 | 1.5 | 0.5 | 3.5
Data Migration | Leo Turner | Internal | 0 | 0.2 | 0.8 | 1.2 | 0.2 | 2.4
Phase Totals |  |  | 1.9 | 3.4 | 5.5 | 6.3 | 1.5 | 18.6

## Resource Planning Worksheet
Resource Planning Worksheet
Project Name |  | Vertex zzzz
Project Name |  | Vertex zzzz
Project | Department | Required | Booked | Marketing A | Marketing B | Sales A | Sales B | Technical A | Technical B | Supply A | Supply B | Variance | Utilization
Project A | Marketing | 35% | 35% | 10% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | OK
Project A | Sales | 50% | 50% | 0% | 0% | 15% | 10% | 0% | 0% | 0% | 0% | 0% | OK
Project A | Technical | 75% | 50% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | -25% | OK
Project A | Supply Chain | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | OK
Project B | Sales | 50% | 50% | 0% | 0% | 10% | 15% | 0% | 0% | 0% | 0% | 0% | OK
Project B | Marketing | 50% | 50% | 15% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | OK
Project B | Supply Chain | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | OK
Project B | Technical | 100% | 100% | 0% | 0% | 0% | 0% | 25% | 50% | 0% | 0% | 0% | OK

## Risk Register Template
Risk Register Template
Risk Heat Map
Project Name |  | Vertex zzzz |  |  |  | 5 | 10 | 15 | 20 | 25
Project Manager |  | Elena zzzz |  |  |  | 4 | 8 | 12 | 16 | 20
Date Updated |  | 46106 |  |  |  | 3 | 6 | 9 | 12 | 15
[6 empty] | 2 | 4 | 6 | 8 | 10
[6 empty] | 1 | 2 | 3 | 4 | 5
Risk ID | Risk Name | Risk Description | Date Captured | Risk Owner | Pre Impact | Pre Likelihood | Pre Score | Current Impact | Current Likelihood | Current Score | Post Impact | Post Likelihood | Post Score | Risk Response | Mitigation Plan / Actions | Progress
R-001 | Integration delay | Middleware interface may slip due to vendor constraints | 2026-01-20 | Emma Clark | 3 | 5 | 15 | 4 | 5 | 20 | 2 | 2 | 4 | Accept | Weekly interface reviews and fallback design | Monitoring
R-002 | Budget overrun | Infrastructure costs may exceed estimate | 2026-02-02 | Mia Carter | 4 | 3 | 12 | 4 | 4 | 16 | 3 | 2 | 6 | Reduce | Renegotiate supplier terms and scope control | Active
R-003 | Low adoption | Operational teams may resist new workflows | 2026-02-14 | Olivia Young | 3 | 4 | 12 | 3 | 3 | 9 | 2 | 2 | 4 | Share | Training and champions network | Open

## Stakeholders Analysis
Stakeholders Analysis
Project Name |  | Vertex zzzz | [11 empty] | Stakeholders Analysis
Project Manager |  | Elena zzzz
Project Description |  | This project modernizes web, analytics, operations, and customer support processes under one execution plan.
[14 empty] | Maintain Confidence | Collaborate With
Stakeholder | Title | Email | Impact of Change | Level of Influence | Priority | Decision Maker | Comm Freq | Comm Method | Against | Passive | Neutral | Help | Notes
Steven Hale | CEO | steven@aurelia.com | 4 | 9 | H | Y | W | IP | C | 0 | R | 0 | Executive sponsor
Terence Cole | CFO | terence@aurelia.com | 7 | 5 | H | Y | W | IP | 0 | 0 | R | 0 | Budget approver
Pier Morgan | Project Manager | pier@aurelia.com | 9 | 3 | H | Y | D | PDF | 0 | C | 0 | R | Delivery lead
Chris Lane | Design Lead | chris@aurelia.com | 5 | 6 | M | N | W | Ph | 0 | C | 0 | R | Creative lead
Amma Stone | Marketing Head | amma@aurelia.com | 6 | 4 | M | N | M | Email | 0 | 0 | R | 0 | Change partner
Jemmy Price | Sales Head | jemmy@aurelia.com | 8 | 7 | H | Y | W | Workshop | 0 | C | 0 | R | Commercial
Rayan Hart | Operations Head | rayan@aurelia.com | 3 | 4 | M | N | W | Workshop | 0 | 0 | R | 0 | 0
Stephen Grant | Technical Head | stephen@aurelia.com | 2 | 3 | L | N | M | Email | 0 | 0 | 0 | R | 0
Danial Stone | Engineer | danial@aurelia.com | 5 | 7 | M | N | W | Standup | 0 | 0 | R | 0 | 0
Sussane Ford | HR Head | sussane@aurelia.com | 6 | 8 | M | N | M | Email | 0 | 0 | R | 0 | 0
[14 empty] | Monitor | Keep Informed

## Task Manager Template
Task Manager Template
Project |  | Vertex zzzz
Project Manager |  | Elena zzzz
Date |  | 46106
Updated on |  | 46106
| Task ID | Task Name | Description | Assigned To | Start Date | Due Date | Priority | Status | Completion Date | Remarks | Overdue | Overdue Days
| 1 | Finalize plumbing rough-in | Finalize plumbing rough-in | Clive | 2026-01-01 | 2026-01-31 | Medium | In Progress |  | Awaiting inspection | No
| 2 | Order kitchen cabinets | Order kitchen cabinets | Jason | 2026-01-10 | 2026-01-31 | Low | Closed | 2026-01-31 | Lead time 2 weeks | No
| 3 | Install dry wall | Install dry wall | Marshall | 2026-01-05 | 2026-01-22 | High | To Be Confirmed |  | Check level 3 finish | No
| 4 | Paint master bedroom | Paint master bedroom | Cinthiya | 2026-02-01 | 2026-03-03 | Medium | Open |  | Client approve | No
| 5 | Finalize garden layout | Finalize garden layout | Robert | 2026-02-04 | 2026-02-27 | Low | In Progress |  | Awaiting layout | No
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yes | 46106
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yes | 46106
| WORK SCHEDULE INPUTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yes | 46106
| Project | Task | Task | Assigned To | Day 2 | Day 3 | Day 1 | Day 4 |  | Day 7 | No
| Project A | Task 1 | Task 1 | Sam Jackson | 0 | 0 | 6 | 0 |  | 0 | Yes | 46106
Formulas:
Overdue = IF(AND([Status]<>"Closed",TODAY()>[Due Date]),"Yes","No")
Overdue Days = IF([Overdue]="Yes",TODAY()-[Due Date],"")

## Task Tracker Template
Task Tracker Template
| ID | Task Name | Dependency | Assigned To | Priority | Start Date | Planned End Date | Actual End Date | Status
| 1 | Meet client leadership |  | Person 1 | High | 46027 | 46030 | 46030 | Completed
| 2 | Gather requirements | 1 | Person 2 | High | 46031 | 46037 | 46037 | Completed
| 3 | Current state analysis | 2 | Person 3 | Medium | 46034 | 46042 | 46042 | Completed
| 4 | UX & service blueprint | 3 | Person 4 | High | 46043 | 46058 |  | In Progress
| 5 | Technical architecture | 4 | Person 5 | High | 46044 | 46061 |  | In Progress
| 6 | Vendor onboarding | 5 | Person 6 | Medium | 46047 | 46055 | 46055 | Completed
| 7 | Web front-end build | 6 | Person 7 | High | 46059 | 46093 |  | In Progress
| 8 | Back-end integration | 7 | Person 8 | High | 46063 | 46099 |  | In Progress
| 9 | Analytics implementation | 8 | Person 9 | Medium | 46071 | 46103 |  | In Progress
| 10 | Fulfilment workflow design | 9 | Person 10 | Medium | 46078 | 46109 |  | Started
| 11 | System integration testing | 10 | Person 11 | High | 46101 | 46115 |  | Not Started
| 12 | User acceptance testing | 11 | Person 12 | High | 46116 | 46128 |  | Not Started
| 13 | Training content development | 12 | Person 13 | Medium | 46106 | 46132 |  | Started
| 14 | Stakeholder communications | 13 | Person 14 | Medium | 46082 | 46157 |  | In Progress
| 15 | Go-live planning | 14 | Person 15 | High | 46132 | 46147 |  | Not Started
| 16 | Cutover rehearsal | 15 | Person 16 | High | 46148 | 46154 |  | Not Started

## Weekly Timesheet Template
WEEKLY TIMESHEET TEMPLATE
Project Name |  | Vertex zzzz | [5 empty] | Pay period start date | 0
Department |  | Transformation Office | [5 empty] | Pay period end date | 0
Designation |  | Elena zzzz
Day | Date | Time In | Time Out (Break Start) | Time In (Break End) | Time Out | Total Hours Worked | Comments
Monday | 2026-01-05 | 08:45 AM | 12:00 PM | 01:00 PM | 05:00 PM | 7.25
Tuesday | 2026-01-06 | 07:00 AM | 12:00 PM | 12:30 PM | 05:00 PM | 9.5
Wednesday | 2026-01-07 | 07:00 AM | 12:00 PM | 12:30 PM | 05:00 PM | 9.5
Thursday | 2026-01-08 | 08:00 AM | 0 | 0 | 05:00 PM | 9
Friday | 2026-01-09 | 07:00 AM | 12:00 PM | 12:30 PM | 05:00 PM | 9.5
Saturday | 2026-01-10 | 0 | 0 | 0 | 0 | 0
Sunday | 2026-01-11 | 0 | 0 | 0 | 0 | 0
[5 empty] | Regular Hours | 40 |  | Pay Rate | 50 | Total Hours | 44.75
[5 empty] | Overtime Hours | 4.75 |  | Overtime Pay Rate | 75 | Regular Pay | 2000
[10 empty] | Overtime Pay | 356.25
[10 empty] | Total Pay | 2356.25

## Project To Do List
Project To Do List
Project Name |  | Vertex zzzz
Date Created |  | 46106
Project Manager |  | Elena zzzz
Task ID | Description | Assigned To | Priority | Start Date | End Date | Status | Completed % | Dependencies | Notes
1 | Finalize plumbing rough-in | Clive | Medium | 2026-01-01 | 2026-01-31 | In Progress | 0% | 0 | Awaiting inspection
2 | Order kitchen cabinets | Jason | Low | 2026-01-10 | 2026-01-31 | Closed | 100% | 1 | Lead time 2 weeks
3 | Install dry wall | Marshall | High | 2026-01-05 | 2026-01-22 | To Be Confirmed | 50% | 0 | Check level 3 finish
4 | Paint master bedroom | Cinthiya | Medium | 2026-02-01 | 2026-03-03 | Open | 75% | 3 | Client approve
5 | Finalize garden layout | Robert | Low | 2026-02-04 | 2026-02-27 | In Progress | 25% | 0 | Awaiting layout

## Work Breakdown Structure
WORK BREAKDOWN STRUCTURE (WBS) TEMPLATE | [8 empty] | Statistics
| Project Name |  | Vertex zzzz | [5 empty] | Main Tasks | 0
| Project Manager |  | Elena zzzz | [5 empty] | Sub Tasks | 0
| Date |  | 46106 | [5 empty] | Completed | 4
| Version |  | 1.0 | [5 empty] | In Progress | 6
[9 empty] | Assigned | 20
[9 empty] | Delayed | 0
Task No. | Description | Owner | Dependency | Resources Required | Status | Cost | Start Date | Estimated Working Days | Finish Date
1 Initiation Phase
1.1 | Meet client leadership | Ava Reynolds | Discovery | Person 1 | Completed | 15000 | 46027 | 4 | 46030
1.2 | Gather requirements | Liam Foster | Requirements | Person 2 | Completed | 18000 | 46031 | 7 | 46037
1.3 | Current state analysis | Sophia Kim | Requirements | Person 3 | Completed | 12000 | 46034 | 9 | 46042
1.4 | UX & service blueprint | Noah Bennett | Design | Person 4 | In Progress | 26000 | 46043 | 16 | 46058
2 Planning Phase
2.1 | Technical architecture | Elena Marquez | Design | Person 5 | In Progress | 32000 | 46044 | 18 | 46061
2.2 | Vendor onboarding | Mia Carter | Procurement | Person 6 | Completed | 9000 | 46047 | 9 | 46055
2.3 | Web front-end build | David Patel | Build | Person 7 | In Progress | 54000 | 46059 | 35 | 46093
2.4 | Back-end integration | Emma Clark | Build | Person 8 | In Progress | 68000 | 46063 | 37 | 46099
3 Execution Phase
3.1 | Analytics implementation | Lucas Grant | Data | Person 9 | In Progress | 24000 | 46071 | 33 | 46103
3.2 | Fulfilment workflow design | Harper Lewis | Operations | Person 10 | Started | 21000 | 46078 | 32 | 46109
3.3 | System integration testing | Ethan Brooks | Testing | Person 11 | Not Started | 15000 | 46101 | 15 | 46115
3.4 | User acceptance testing | Grace Morgan | Testing | Person 12 | Not Started | 12000 | 46116 | 13 | 46128
4 Control Phase
4.1 | Training content development | Olivia Young | Training | Person 13 | Started | 8000 | 46106 | 27 | 46132
4.2 | Stakeholder communications | Aiden Ross | Change | Person 14 | In Progress | 14000 | 46082 | 76 | 46157
4.3 | Go-live planning | Chloe Hughes | Launch | Person 15 | Not Started | 11000 | 46132 | 16 | 46147
4.4 | Cutover rehearsal | Leo Turner | Launch | Person 16 | Not Started | 9000 | 46148 | 7 | 46154
5 Close Phase
5.1 | Production deployment | Zoe Evans | Launch | Person 17 | Not Started | 25000 | 46155 | 3 | 46157
5.2 | Hypercare support | Isla Bennett | Support | Person 18 | Not Started | 18000 | 46158 | 21 | 46178
5.3 | Post-launch analytics | Jack Sullivan | Optimization | Person 19 | Not Started | 10000 | 46179 | 15 | 46193
5.4 | Benefits handover & closure | Ava Reynolds | Closure | Person 20 | Not Started | 7000 | 46194 | 10 | 46203

## Project Work Schedule
PROJECT WORK SCHEDULE TEMPLATE
Project Name |  | Vertex zzzz
Project Manager |  | Elena zzzz
Start Date |  | 46027
Project | Task | Assigned To | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | Total Hours
Project A | Task 1 | Sam Jackson | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
Project A | Task 2 | Alexa Jones | 0 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
Project B | Task 1 | Roger Billingsly | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
Project C | Task 1 | Joe Aguilar | 7 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
Total Hours |  |  | 15 | 7 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38