## Main Action Plan
ACTION PLAN
Executive-ready action tracker for planning, accountability, risk control, and progress reporting
| Project Name | Aurora Smart Campus Rollout |  |  | Client / Division | Northbridge Innovations Ltd. |  |  | Project Manager | Daniel Brooks |  |  | Sponsor | Emma Carter
| Location | Rivergate, Illinois |  |  | Period Start | 2026-04-01 |  |  | Period End | 2026-06-30 |  |  | Today | 2026-04-15
Portfolio Snapshot
Total Actions |  |  | Completed |  |  | In Progress |  |  | At Risk / Blocked |  |  | Overall Completion
15 |  |  | 5 |  |  | 4 |  |  | 1 |  |  | 23.8667
[9 empty] | Not Started | In Progress | At Risk | Blocked | Completed
ID | Action Item | Phase | Department | Owner | Start Date | Due Date | Priority | Status | Risk Level | Dependency | % Complete | Days Left | Budget ($) | Outcome / KPI | Notes
1 | Finalize site survey and network scope | Initiation | IT | Daniel Brooks | 2026-04-01 | 2026-04-08 | High | Completed | Low | - | 100% | 0 | 4500 | Approved technical scope | All major issues closed
2 | Approve procurement shortlist | Planning | Procurement | Sophia Nguyen | 2026-04-03 | 2026-04-12 | Critical | Completed | Medium | 1 | 100% | 0 | 12000 | 3 vendors shortlisted | Sponsor sign-off received
3 | Issue RFP to shortlisted vendors | Planning | Procurement | Sophia Nguyen | 2026-04-10 | 2026-04-16 | High | Completed | Low | 2 | 100% | 1 | 2000 | RFP issued on schedule | Responses due in 5 days
4 | Prepare communications launch pack | Planning | Communications | Ava Collins | 2026-04-08 | 2026-04-22 | Medium | In Progress | Medium | 1 | 65% | 7 | 3500 | Stakeholder pack drafted | Awaiting final brand assets
5 | Confirm furniture relocation plan | Planning | Facilities | Liam Turner | 2026-04-11 | 2026-04-20 | Medium | Completed | Low | 1 | 100% | 5 | 5200 | Floor move plan approved | Coordinated with facilities team
6 | Install core access points | Execution | IT | Noah Bennett | 2026-04-18 | 2026-05-02 | Critical | In Progress | High | 3 | 55% | 17 | 28500 | Coverage > 98% | Two zones pending
7 | Configure security gateways | Execution | IT | Noah Bennett | 2026-04-22 | 2026-05-05 | High | At Risk | High | 6 | 40% | 20 | 14600 | Secure network segmentation | Firewall rule approvals delayed
8 | Deploy smart classroom displays | Execution | Operations | Maya Patel | 2026-04-25 | 2026-05-10 | High | In Progress | Medium | 5 | 50% | 25 | 34000 | 40 displays installed | Vendor labor split across two sites
9 | Create training schedule for staff | Planning | Training | Olivia Reed | 2026-04-16 | 2026-04-28 | Medium | Completed | Low | 4 | 100% | 13 | 1800 | Training calendar published | Shared via intranet
10 | Run pilot training session | Testing | Training | Olivia Reed | 2026-05-04 | 2026-05-12 | Medium | In Progress | Medium | 9 | 35% | 27 | 2400 | Pilot NPS > 8.5 | Feedback collection active
11 | Complete UAT for classroom systems | Testing | Operations | Maya Patel | 2026-05-08 | 2026-05-20 | Critical | Not Started | High | 6,8 | 0% | 35 | 0 | UAT pass rate > 95% | Waiting for full install
12 | Resolve punch-list defects | Testing | IT | Ethan Walker | 2026-05-18 | 2026-05-28 | High | Not Started | Medium | 11 | 0% | 43 | 6200 | All critical defects resolved | To begin after UAT
13 | Executive readiness review | Launch | PMO | Daniel Brooks | 2026-05-26 | 2026-06-02 | Critical | Not Started | Medium | 10,11,12 | 0% | 48 | 1500 | Go-live approval | Review pack not started
14 | Go-live at Rivergate HQ | Launch | Operations | Daniel Brooks | 2026-06-05 | 2026-06-05 | Critical | Not Started | Severe | 13 | 0% | 51 | 5000 | Successful activation | Command center planned
15 | Post-launch support and lessons learned | Closure | PMO | Emma Carter | 2026-06-08 | 2026-06-20 | Medium | On Hold | Low | 14 | 0% | 66 | 2200 | Transition complete | Pending launch
Management Summary
Planned Budget |  |  | Average Completion |  |  | High/Critical Priority Items |  |  | Tasks Due in Next 7 Days |  |  | Blocked Items
123400 |  |  | 49.67% |  |  | 10 |  |  | 1 |  |  | 0
Formulas:
Overall Completion = MAX([In Progress]-TODAY(),0)

## Data Entry
Project Action Plan Template - Data Entry
Project Name | Aurora Smart Campus Rollout
Client / Division | Northbridge Innovations Ltd.
Project Sponsor | Emma Carter
Project Manager | Daniel Brooks
Location | Rivergate, Illinois
Reporting Period Start | 2026-04-01
Reporting Period End | 2026-06-30
Priority |  | Status | Phase | Department | Risk Level | Owners
Critical |  | Not Started | Initiation | PMO | Low | Daniel Brooks
High |  | In Progress | Planning | IT | Medium | Sophia Nguyen
Medium |  | At Risk | Execution | Facilities | High | Liam Turner
Low |  | Blocked | Testing | Procurement | Severe | Maya Patel
|  | Completed | Launch | Operations |  | Olivia Reed
|  | On Hold | Closure | Training |  | Noah Bennett
|  |  |  | Communications |  | Ava Collins
Ethan Walker
Locations
Rivergate HQ
Westbrook Campus
Oakridge Facility
Harbor Point Office

## Instructions
How to Use This Action Plan Template
Designed by a project manager to support planning, execution, reporting, and governance.
1 | Start in Data Entry | Update project name, sponsor, manager, location, and reporting dates in the Data Entry sheet. The main sheet pulls those fields automatically. | Project PMO Standard
2 | Manage actions in Main Action Plan | Use one row per action item. Record the phase, department, owner, dates, priority, status, risk level, budget, expected outcome, and notes. | Project PMO Standard
3 | Use dropdowns | Priority, status, phase, department, owner, and risk level have dropdown menus to keep reporting consistent. | Project PMO Standard
4 | Track progress | Enter % Complete as a percentage. Overall completion, counts by status, and key summary indicators update automatically. | Project PMO Standard
5 | Monitor deadlines | The Days Left column is formula-driven. Lower values require attention; overdue or near-term work is highlighted through conditional formatting. | Project PMO Standard
6 | Interpret the colors | Dark navy headers = core structure; teal = progress and portfolio focus; blue and purple accents = summary and review areas; light background = clean reading zone. | Project PMO Standard
7 | Recommended governance cadence | Review weekly with team leads, refresh risks and blockers, and update notes with key decisions or escalation needs. | Project PMO Standard
8 | Best-practice tips | Keep action items specific and measurable, assign one accountable owner, use realistic due dates, and link every task to an outcome or KPI. | Project PMO Standard
Legend
Completed | In Progress | At Risk | Blocked
Example use cases
• | Project launch readiness and milestone control
• | Corrective action tracking after a risk review
• | Operational improvement plans and PMO reporting
• | Client implementation plans with accountable owners