## Main Template
CHANGE LOG
Executive-grade project change register with impact control, approvals, implementation tracking, and portfolio visibility
PROJECT OVERVIEW |  |  | Open Changes |  |  |  | Approved Changes |  |  |  | Total Cost Impact |  |  |  | Avg Schedule Impact (Days) |  |  |  | High Priority / High Risk
Project Sponsor | Amelia Hart |  | 10 |  |  |  | 9 |  |  |  | 119400 |  |  |  | 4.25 |  |  |  | 3 |  |  | Legend
Project Manager | Daniel Mercer, PMP | [20 empty] | Navy | Core structure
Business Unit | Digital Operations Transformation | [20 empty] | Teal | Controlled / healthy
Primary Site | Riverview Innovation Campus, Austin | [20 empty] | Blue | Active tracking
Baseline Budget | 1250000 | [20 empty] | Violet | High impact / escalation
Baseline Go-Live | 2026-09-30
MASTER CHANGE REGISTER
Change ID | Date Raised | Requested By | Department | Site / Location | Change Title | Change Description | Category | Reason for Change | Scope Impact | Schedule Impact (Days) | Cost Impact ($) | Resource Impact | Priority | Status | Approval Decision | Approved By | Approval Date | Action Owner | Target Impl Date | Actual Impl Date | Days Open | Risk Level | Remarks / Notes
CL-001 | 2026-01-05 | Olivia Chen | Finance | Austin HQ | Expand approval matrix | Add two-step approval for invoices above $50k | Process | Audit readiness | Moderate | 4 | 12000 | Finance analyst support | High | Under Review | Pending |  |  | Mia Roberts | 2026-01-22 |  | 100 | Medium | Awaiting steering committee review
CL-002 | 2026-01-09 | Noah Bennett | Operations | Denver Distribution Center | Add barcode label printer integration | Integrate legacy label printers with new ERP shipping module | Technical | Warehouse continuity | Low | 7 | 28000 | 1 integration specialist | High | Approved | Approved | Amelia Hart | 2026-01-12 | Victor Alvarez | 2026-01-31 | 2026-01-28 | 96 | High | Approved with accelerated implementation
CL-003 | 2026-01-13 | Sophia Turner | Procurement | Austin HQ | Revise supplier onboarding workflow | Insert ESG verification checkpoint into supplier setup | Scope | Compliance requirement | Moderate | 3 | 6500 | Procurement SME review | Medium | Implemented | Approved | Amelia Hart | 2026-01-15 | Ethan Cole | 2026-02-05 | 2026-02-02 | 92 | Low | Delivered in sprint 4
CL-004 | 2026-01-20 | Liam Foster | HR | Riverview Campus | Add contractor timesheet rules | Create separate validation rules for third-party contractors | Quality | Payroll accuracy | Low | 2 | 4800 | HR business analyst | Medium | Closed | Approved | Grace Holloway | 2026-01-21 | Ava Sinclair | 2026-02-10 | 2026-02-08 | 85 | Low | Closed after UAT signoff
CL-005 | 2026-01-28 | Emma Brooks | IT Security | Austin HQ | Enable MFA for mobile approvals | Introduce MFA challenge for manager approvals on mobile app | Technical | Security enhancement | Moderate | 5 | 18500 | Security engineer | High | Approved | Approved | Amelia Hart | 2026-01-29 | Leo Grant | 2026-02-18 |  | 77 | High | Deployment window booked
CL-006 | 2026-02-03 | Mason Reed | PMO | Austin HQ | Move training wave 2 by one week | Shift training schedule to align with regional operations blackout | Schedule | Operational conflict | No Change | 7 | 3200 | Trainer rescheduling | Medium | Closed | Approved | Amelia Hart | 2026-02-04 | Chloe Whitman | 2026-02-20 | 2026-02-20 | 71 | Medium | No budget risk to overall baseline
CL-007 | 2026-02-11 | Isabella James | Sales Ops | Chicago Sales Hub | Add opportunity split field | New field required for revised commission model | Scope | Business policy update | Moderate | 6 | 9600 | CRM analyst + tester | High | Implemented | Approved | Grace Holloway | 2026-02-13 | Nora Bell | 2026-02-28 | 2026-02-27 | 63 | Medium | Included in release 2.1
CL-008 | 2026-02-18 | Benjamin Price | Logistics | Phoenix Fulfillment Center | Increase data retention period | Extend shipment history retention from 12 to 24 months | Technical | Customer claims analysis | Low | 1 | 4100 | DBA support | Low | Rejected | Rejected | Amelia Hart | 2026-02-20 | Harper Lane |  |  | 56 | Low | Rejected due to storage policy conflict
CL-009 | 2026-02-24 | Charlotte Evans | Customer Service | Miami Service Center | Add case escalation SLA alerts | Automated reminders when cases near SLA breach | Quality | Service performance | Moderate | 4 | 8900 | Workflow admin | Medium | Approved | Approved | Amelia Hart | 2026-02-25 | Lucas Dean | 2026-03-12 | 2026-03-11 | 50 | Medium | Improved visibility for supervisors
CL-010 | 2026-03-03 | James Walker | Legal | Austin HQ | Update contract clause library | Refresh clause templates for new data privacy language | Compliance | Regulatory update | Low | 2 | 5600 | Legal reviewer | High | Under Review | Pending |  |  | Zoe Harper | 2026-03-25 |  | 43 | High | Pending counsel review
CL-011 | 2026-03-10 | Evelyn Ross | Manufacturing | Tulsa Plant | Add plant-specific work center codes | New codes required for local production reporting | Scope | Reporting accuracy | Moderate | 8 | 14500 | Plant super-user | Medium | Approved | Approved | Grace Holloway | 2026-03-12 | Owen Price | 2026-04-04 |  | 36 | Medium | Build in progress
CL-012 | 2026-03-17 | Henry Cooper | Data Team | Austin HQ | Correct tax rounding logic | Fix rounding variance on international purchase orders | Technical | Defect correction | Low | 2 | 3700 | Developer hotfix | High | Implemented | Approved | Amelia Hart | 2026-03-18 | Ella Monroe | 2026-03-24 | 2026-03-23 | 29 | Low | Validated with finance controllers
Formulas:
Days Open = TODAY()-[Daniel Mercer, PMP]
Note on A12: Unique reference for each change. Suggested format: CL-001, CL-002, etc.
Note on L12: Enter total incremental cost impact only. Use positive values for added cost.
Note on V12: Days Open uses a formula based on Date Raised. Keep date values real Excel dates.

## Data Entry
DATA ENTRY & CONTROL LISTS
Quick Entry Form (copy completed values into Main Template if preferred) |  |  | Validation Lists / Standard Values
Next Change ID | CL-013 | Auto-generated next sequential ID | Category | Priority | Status | Approval Decision
Date Raised | 2026-04-15 | Enter the request date | Scope | High | Proposed | Pending
Requested By |  | Example: Olivia Chen | Schedule | Medium | Under Review | Approved
Department |  | Example: Finance / Operations / IT Security | Budget | Low | Approved | Rejected
Site / Location |  | Use a real site or office name | Resource |  | Implemented
Change Title |  | Keep the title short and executive-friendly | Quality |  | Closed
Change Description |  | Describe the change, not the whole problem | Technical |  | Rejected
Category |  | Choose from list at right | Compliance
Reason for Change |  | Explain the business driver or trigger | Scope Impact | Risk Level
Scope Impact |  | Example values: Low, Moderate, High, No Change | High | High
Schedule Impact (Days) |  | Whole number of days added or removed | Moderate | Medium
Cost Impact ($) |  | Positive number for added cost | Low | Low
Resource Impact |  | People, contractors, SMEs, tools, or systems needed | No Change
Priority |  | Set urgency level
Status |  | Current stage of the change
Approval Decision |  | Approved / Pending / Rejected
Approved By |  | Approver name if decision is final
Action Owner |  | Single accountable owner
Target Impl Date |  | Planned implementation date
Risk Level |  | Overall execution risk
Remarks / Notes |  | Use concise notes, decisions, assumptions, or blockers

## Instructions
HOW TO USE THIS CHANGE LOG TEMPLATE
Purpose | Track every material project change from request through approval, implementation, and closure. The template is designed for program, project, PMO, and workstream leaders who need disciplined change control.
What the Main Template Covers | Change ID, title, description, requestor, department, site/location, category, reason, impact on scope, time, cost, resources, priority, status, approval, ownership, target/actual implementation dates, days open, risk level, and notes.
Recommended Workflow | 1) Enter or prepare change details on the Data Entry sheet. 2) Add the record to the Main Template table. 3) Assess schedule, cost, scope, and resource impacts. 4) Capture approval decision and approver. 5) Track implementation and close only after validation.
Status Guidance | Proposed = logged but not yet reviewed. Under Review = impact assessment in progress. Approved = authorized to implement. Implemented = completed but still being validated. Closed = fully delivered and signed off. Rejected = formally declined.
Good PM Practice | Keep titles short, descriptions precise, and impacts quantified. Do not close a change until outcome validation is complete. If budget or schedule impact is uncertain, mark the change Under Review and update once confirmed.
Color Usage | Navy = structure and section headers. Teal = approvals and healthy progress. Blue = active tracking and key table areas. Violet = high impact, escalations, or special emphasis. Soft off-white = clean reading background.
Customization Tips | You can add slicers or pivot summaries later, extend the table beyond row 24, protect formula cells, or add more validation lists for departments, sites, or approvers.
Prepared for demonstration using hypothetical project names, stakeholders, and sites. Suitable for adaptation to IT, construction, operations, PMO, or transformation programs.