## Main_Template
DETAILED COSTED WORKPLAN
|  | Project Name | EITI Acceleration & Stakeholder Alignment Program 2026 |  |  | Start Date | 2026-01-05 |  | Total Budget |  | Activities
|  | Project Manager | Mariam Okoro |  |  | End Date | 2026-09-30 |  | 42050 |  | 14
|  | Implementing Company | Aurora Civic Advisory Ltd |  |  | Currency | USD
|  | Location | Republic of Livania / Port Azure |  |  | Last Updated | 2025-12-15 |  | Completion |  | Risk Flags
[9 empty] | 35.71% |  | 2
Executive Summary
EITI Acceleration & Stakeholder Alignment Program 2026 is a connected project-management workbook for planning activities, costs, ownership, outputs, outcomes and timing. Update Setup_Data and Data_Entry only; the main reporting view, budget summary and Gantt sheet recalculate automatically.
Objective Funding Overview | [6 empty] | Status Legend
Objective | Donor Cost | Stakeholder Cost | Total Cost | Activities | Completed |  | Status | Meaning
Establish commitment and governance | 6100 | 2400 | 8500 | 4 | 4 |  | Not Started | Planned but not yet begun
Build data systems and reporting workflow | 13600 | 4600 | 18200 | 5 | 1 |  | In Progress | Actively underway
Deliver disclosure, assurance and learning | 11600 | 3750 | 15350 | 5 | 0 |  | At Risk | May miss time/cost/quality target
Total | 31300 | 10750 | 42050 | 14 | 5 |  | Delayed | Behind baseline plan
[7 empty] | Completed | Closed and accepted
Connected Workplan View (Live from Data_Entry)
Objective | Activity ID | Activity | Action Required | Timeline | Expected Output | Expected Outcome | Responsible Entity | Status | Donor | Donor Cost | Stakeholder Cost | Total | Notes
Establish commitment and governance | 1.1 | Issue public statement of intent to implement EITI | Draft and publish a ministerial statement and executive order endorsing the reform agenda. | 05-Jan to 12-Jan | Public statement issued | Visible government commitment | Ministry of Natural Resources | Completed | Helios Foundation | 1200 | 800 | 2000 | Press event, media pack and approvals complete
Establish commitment and governance | 1.2 | Appoint senior official to lead implementation | Nominate high-level champion and confirm authority memo. | 08-Jan to 15-Jan | Appointment letter and role charter | Clear accountability structure | Aurora Civic Advisory Ltd | Completed | Internal Budget | 900 | 0 | 900 | Role assigned to Deputy Minister
Establish commitment and governance | 1.3 | Secure multi-stakeholder commitment | Conduct dialogues with industry, civil society and local authorities. | 16-Jan to 04-Feb | Signed MoUs and meeting records | Coalition formed around program | Field Outreach Unit | Completed | Civic Transparency Fund | 1800 | 900 | 2700 | Three consultation rounds
Establish commitment and governance | 1.4 | Publicly launch initiative | Organize launch event, media campaign and stakeholder briefings. | 10-Feb to 18-Feb | Launch event and media kit | Public awareness of goals | Harbor Communications | Completed | Helios Foundation | 2200 | 700 | 2900 | National TV and radio slots
Build data systems and reporting workflow | 2.1 | Map reporting entities and data owners | Identify all extractive companies, agencies and data owners. | 20-Feb to 10-Mar | Validated reporting inventory | Complete reporting universe | Cobalt Data Systems | Completed | Northbridge Trust | 2600 | 500 | 3100 | Inventory cross-checked with tax authority
Build data systems and reporting workflow | 2.2 | Design reporting templates | Create digital data collection forms and validation rules. | 03-Mar to 24-Mar | Approved reporting templates | Consistent source data | Cobalt Data Systems | In Progress | Northbridge Trust | 3400 | 1200 | 4600 | Pilot version in review
Build data systems and reporting workflow | 2.3 | Configure document repository | Set up secure repository and user permissions. | 18-Mar to 08-Apr | Repository live with access matrix | Controlled data management | BluePeak Engineering PLC | In Progress | Internal Budget | 2100 | 600 | 2700 | Awaiting final security checklist
Build data systems and reporting workflow | 2.4 | Develop data reconciliation model | Build reconciliation workbook and exception rules. | 01-Apr to 05-May | Reconciliation model tested | Reliable variance analysis | GreenRiver Consulting | At Risk | Northbridge Trust | 3900 | 1500 | 5400 | Risk: late sample files from operators
Build data systems and reporting workflow | 2.5 | Train focal points on reporting process | Deliver workshops for company and agency focal points. | 04-May to 20-May | Training completion certificates | Reduced data errors | Field Outreach Unit | Not Started | Civic Transparency Fund | 1600 | 800 | 2400 | Training venue reserved
Deliver disclosure, assurance and learning | 3.1 | Collect and validate submissions | Receive submissions and check completeness/quality. | 25-May to 18-Jun | Validated submission log | Submission quality improved | Livania Revenue Agency | Not Started | Helios Foundation | 2800 | 900 | 3700 | Dependent on training completion
Deliver disclosure, assurance and learning | 3.2 | Independent assurance review | Perform sample checks and assurance procedures. | 20-Jun to 10-Jul | Assurance memo | Confidence in published figures | GreenRiver Consulting | Not Started | Northbridge Trust | 3200 | 1100 | 4300 | Scope includes royalty and tax streams
Deliver disclosure, assurance and learning | 3.3 | Draft EITI report narrative | Draft findings, context and stakeholder commentary. | 01-Jul to 26-Jul | Draft report narrative | Clear communication of results | Aurora Civic Advisory Ltd | Not Started | Helios Foundation | 2400 | 600 | 3000 | Will integrate assurance findings
Deliver disclosure, assurance and learning | 3.4 | Board review and sign-off | Present final package to steering committee. | 04-Aug to 15-Aug | Approved final report | Decision makers aligned | Ministry of Natural Resources | Not Started | Internal Budget | 1000 | 400 | 1400 | Includes steering committee retreat
Deliver disclosure, assurance and learning | 3.5 | Public dissemination and lessons learned | Publish report, host webinar and produce lessons log. | 20-Aug to 10-Sep | Published report and lessons register | Learning captured for next cycle | Harbor Communications | Delayed | Civic Transparency Fund | 2200 | 750 | 2950 | Awaiting board approval

## Setup_Data
DETAILED COSTED WORKPLAN ¦ PROJECT SETUP
Project Metadata |  | Key Assumptions
Project Name | EITI Acceleration & Stakeholder Alignment Program 2026 | Workdays per Month | 22
Project Sponsor | Helios Foundation | Contingency % | 7%
Implementing Company | Aurora Civic Advisory Ltd | VAT / Tax % | 5%
Project Manager | Mariam Okoro | Default Daily Rate - PM | 650
Country / Location | Republic of Livania / Port Azure | Default Daily Rate - Technical Lead | 550
Start Date | 2026-01-05 | Default Daily Rate - Outreach | 300
End Date | 2026-09-30 | Default Daily Rate - Analyst | 420
Reporting Currency | USD
Version | v1.0
Last Updated | 2025-12-15
Note on E5: Editable planning assumption for illustration.

## Data_Entry
COST DATA ENTRY
Edit the activity rows below. Summary, budget and Gantt sheets update automatically.
Objective ID | Objective Name | Activity ID | Activity | Action Required | Expected Output | Expected Outcome | Location | Responsible Entity | Start Date | End Date | Duration (days) | Status | Donor | Donor Cost | Stakeholder Cost | Total Cost | Notes
OBJ-1 | Establish commitment and governance | 1.1 | Issue public statement of intent to implement EITI | Draft and publish a ministerial statement and executive order endorsing the reform agenda. | Public statement issued | Visible government commitment | Port Azure | Ministry of Natural Resources | 2026-01-05 | 2026-01-12 | 8 | Completed | Helios Foundation | 1200 | 800 | 2000 | Press event, media pack and approvals complete
OBJ-1 | Establish commitment and governance | 1.2 | Appoint senior official to lead implementation | Nominate high-level champion and confirm authority memo. | Appointment letter and role charter | Clear accountability structure | Port Azure | Aurora Civic Advisory Ltd | 2026-01-08 | 2026-01-15 | 8 | Completed | Internal Budget | 900 | 0 | 900 | Role assigned to Deputy Minister
OBJ-1 | Establish commitment and governance | 1.3 | Secure multi-stakeholder commitment | Conduct dialogues with industry, civil society and local authorities. | Signed MoUs and meeting records | Coalition formed around program | Rivergate | Field Outreach Unit | 2026-01-16 | 2026-02-04 | 20 | Completed | Civic Transparency Fund | 1800 | 900 | 2700 | Three consultation rounds
OBJ-1 | Establish commitment and governance | 1.4 | Publicly launch initiative | Organize launch event, media campaign and stakeholder briefings. | Launch event and media kit | Public awareness of goals | Port Azure | Harbor Communications | 2026-02-10 | 2026-02-18 | 9 | Completed | Helios Foundation | 2200 | 700 | 2900 | National TV and radio slots
OBJ-2 | Build data systems and reporting workflow | 2.1 | Map reporting entities and data owners | Identify all extractive companies, agencies and data owners. | Validated reporting inventory | Complete reporting universe | Lunaris | Cobalt Data Systems | 2026-02-20 | 2026-03-10 | 19 | Completed | Northbridge Trust | 2600 | 500 | 3100 | Inventory cross-checked with tax authority
OBJ-2 | Build data systems and reporting workflow | 2.2 | Design reporting templates | Create digital data collection forms and validation rules. | Approved reporting templates | Consistent source data | Lunaris | Cobalt Data Systems | 2026-03-03 | 2026-03-24 | 22 | In Progress | Northbridge Trust | 3400 | 1200 | 4600 | Pilot version in review
OBJ-2 | Build data systems and reporting workflow | 2.3 | Configure document repository | Set up secure repository and user permissions. | Repository live with access matrix | Controlled data management | Port Azure | BluePeak Engineering PLC | 2026-03-18 | 2026-04-08 | 22 | In Progress | Internal Budget | 2100 | 600 | 2700 | Awaiting final security checklist
OBJ-2 | Build data systems and reporting workflow | 2.4 | Develop data reconciliation model | Build reconciliation workbook and exception rules. | Reconciliation model tested | Reliable variance analysis | Port Azure | GreenRiver Consulting | 2026-04-01 | 2026-05-05 | 35 | At Risk | Northbridge Trust | 3900 | 1500 | 5400 | Risk: late sample files from operators
OBJ-2 | Build data systems and reporting workflow | 2.5 | Train focal points on reporting process | Deliver workshops for company and agency focal points. | Training completion certificates | Reduced data errors | North Vale | Field Outreach Unit | 2026-05-04 | 2026-05-20 | 17 | Not Started | Civic Transparency Fund | 1600 | 800 | 2400 | Training venue reserved
OBJ-3 | Deliver disclosure, assurance and learning | 3.1 | Collect and validate submissions | Receive submissions and check completeness/quality. | Validated submission log | Submission quality improved | Port Azure | Livania Revenue Agency | 2026-05-25 | 2026-06-18 | 25 | Not Started | Helios Foundation | 2800 | 900 | 3700 | Dependent on training completion
OBJ-3 | Deliver disclosure, assurance and learning | 3.2 | Independent assurance review | Perform sample checks and assurance procedures. | Assurance memo | Confidence in published figures | South Basin | GreenRiver Consulting | 2026-06-20 | 2026-07-10 | 21 | Not Started | Northbridge Trust | 3200 | 1100 | 4300 | Scope includes royalty and tax streams
OBJ-3 | Deliver disclosure, assurance and learning | 3.3 | Draft EITI report narrative | Draft findings, context and stakeholder commentary. | Draft report narrative | Clear communication of results | Port Azure | Aurora Civic Advisory Ltd | 2026-07-01 | 2026-07-26 | 26 | Not Started | Helios Foundation | 2400 | 600 | 3000 | Will integrate assurance findings
OBJ-3 | Deliver disclosure, assurance and learning | 3.4 | Board review and sign-off | Present final package to steering committee. | Approved final report | Decision makers aligned | Port Azure | Ministry of Natural Resources | 2026-08-04 | 2026-08-15 | 12 | Not Started | Internal Budget | 1000 | 400 | 1400 | Includes steering committee retreat
OBJ-3 | Deliver disclosure, assurance and learning | 3.5 | Public dissemination and lessons learned | Publish report, host webinar and produce lessons log. | Published report and lessons register | Learning captured for next cycle | Rivergate | Harbor Communications | 2026-08-20 | 2026-09-10 | 22 | Delayed | Civic Transparency Fund | 2200 | 750 | 2950 | Awaiting board approval

## Budget_Summary
BUDGET SUMMARY & KPI VIEW
Project | EITI Acceleration & Stakeholder Alignment Program 2026 | [5 empty] | Total Activities
Project Manager | Mariam Okoro | [5 empty] | 14
Reporting Period | 05-Jan-2026 to 30-Sep-2026
Total Budget
Budget by Objective |  |  |  | Activity Status Summary |  |  | 42050
Objective | Donor Cost | Stakeholder Cost | Total Cost | Status | Count | Budget
Establish commitment and governance | 6100 | 2400 | 8500 | Not Started | 5 | 14800 | Completed %
Build data systems and reporting workflow | 13600 | 4600 | 18200 | In Progress | 2 | 7300 | 35.71%
Deliver disclosure, assurance and learning | 11600 | 3750 | 15350 | At Risk | 1 | 5400
Grand Total | 31300 | 10750 | 42050 | Delayed | 1 | 2950 | At Risk / Delayed
|  |  |  | Completed | 5 | 11600 | 2

## Timeline_Gantt
PROJECT TIMELINE / GANTT VIEW
[6 empty] | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
Activity ID | Activity | Owner | Status | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1.1 | Issue public statement of intent to implement EITI | Ministry of Natural Resources | Completed | 2026-01-05 | 2026-01-12
1.2 | Appoint senior official to lead implementation | Aurora Civic Advisory Ltd | Completed | 2026-01-08 | 2026-01-15
1.3 | Secure multi-stakeholder commitment | Field Outreach Unit | Completed | 2026-01-16 | 2026-02-04
1.4 | Publicly launch initiative | Harbor Communications | Completed | 2026-02-10 | 2026-02-18
2.1 | Map reporting entities and data owners | Cobalt Data Systems | Completed | 2026-02-20 | 2026-03-10
2.2 | Design reporting templates | Cobalt Data Systems | In Progress | 2026-03-03 | 2026-03-24
2.3 | Configure document repository | BluePeak Engineering PLC | In Progress | 2026-03-18 | 2026-04-08
2.4 | Develop data reconciliation model | GreenRiver Consulting | At Risk | 2026-04-01 | 2026-05-05
2.5 | Train focal points on reporting process | Field Outreach Unit | Not Started | 2026-05-04 | 2026-05-20
3.1 | Collect and validate submissions | Livania Revenue Agency | Not Started | 2026-05-25 | 2026-06-18
3.2 | Independent assurance review | GreenRiver Consulting | Not Started | 2026-06-20 | 2026-07-10
3.3 | Draft EITI report narrative | Aurora Civic Advisory Ltd | Not Started | 2026-07-01 | 2026-07-26
3.4 | Board review and sign-off | Ministry of Natural Resources | Not Started | 2026-08-04 | 2026-08-15
3.5 | Public dissemination and lessons learned | Harbor Communications | Delayed | 2026-08-20 | 2026-09-10

## Instructions
INSTRUCTIONS ¦ WHAT THIS TEMPLATE IS AND HOW TO USE IT
1. What this workbook is | This workbook is a project-manager's detailed costed workplan template. It explains scope, actions, timing, outputs, outcomes, ownership and cost in one connected Excel file.
2. Core idea | You should enter data only on Setup_Data and Data_Entry. Every other sheet is a management view driven by formulas.
3. Setup_Data sheet | Use Setup_Data to define the project name, sponsor, implementing company, project manager, location, dates, currency and planning assumptions.
4. Data_Entry sheet | Use one row per activity. Enter objective, activity details, dates, status, donor and cost fields. Duration and Total Cost are calculated automatically.
5. Main_Template sheet | This is the polished reporting page. It summarizes project information, objective budgets, KPI tiles, live workplan rows and a status legend for leadership or donors.
6. Budget_Summary sheet | This sheet rolls up costs by objective and by activity status. It also contains charts and KPI tiles for quick review.
7. Timeline_Gantt sheet | This gives a simple weekly Gantt chart. Adjust start or end dates in Data_Entry and the activity bar moves automatically.
8. Lookups sheet | This powers dropdown menus for Status, Responsible Entity, Donor and Location. Add to these lists if your program needs more values.
9. Recommended PM workflow | Update statuses weekly, review risks, compare actual vs planned dates, and use notes for decisions, blockers or dependencies.
10. How the budget works | Donor Cost + Stakeholder Cost = Total Cost. Objective summaries use SUMIFS formulas, so they always reflect Data_Entry.
11. Good practice when customizing | Copy the last formatted row on Data_Entry downward if you need more activities. Keep the formula columns intact.
12. Example | If you change a donor cost, the total cost, objective total, charts and KPI budget all update. If you change dates, the Gantt view updates too.
Quick Start
1. Update Setup_Data
2. Add / edit activity rows in Data_Entry
3. Review Main_Template
4. Review Budget_Summary and Timeline_Gantt

## Lookups
Lookup Lists
Statuses | Responsible Entities | Donor Streams | Locations
Not Started | Aurora Civic Advisory Ltd | Helios Foundation | Port Azure
In Progress | BluePeak Engineering PLC | Northbridge Trust | Rivergate
At Risk | GreenRiver Consulting | Civic Transparency Fund | Lunaris
Delayed | Ministry of Natural Resources | Internal Budget | North Vale
Completed | Livania Revenue Agency |  | South Basin
Cobalt Data Systems
Harbor Communications
Field Outreach Unit