## Main Template
Detailed Costed Workplan
Live workbook connected to "Data Entry" sheet — update once, report everywhere.
Project Profile |  |  |  | Governance |  |  | Cost Snapshot |  |  | Progress Snapshot
Company | NovaBuild Partners Ltd. |  |  | Project Manager | Amina Okafor |  | Baseline Budget | 1850000 |  | Activities | 15
Project | GreenBridge Solar Farm Rollout |  |  | Sponsor | Daniel Mercer |  | Contingency Value | 148000 |  | Completed | 4
Client | City of Lakemont Energy Authority |  |  | Version | v1.0 |  | Planned Cost (Activities) | 1983500 |  | In Progress | 2
Location | Lakemont, Westhaven |  |  | Reporting Cycle | Monthly |  | Actual Cost | 256930 |  | Overall % Complete | 35.67%
Date Range | 04-May-2026 to 30-Oct-2026 |  |  | Last Updated | 2026-04-13 |  | Cost Variance | 1726570 |  | Delayed | 0
Budget Utilization |  |  | Schedule Days Planned |  |  | Avg Activity Completion |  |  | Contingency Remaining
12.95% |  |  | 180 |  |  | 35.67% |  |  | 1741070
Live Workplan View
ID | Phase | Activity / Deliverable | Owner | Start | End | Status | Planned Cost | Actual Cost | % Complete | Variance
1 | Initiation | Project charter approval | Amina Okafor | 2026-05-04 | 2026-05-08 | Completed | 6500 | 6200 | 100% | 300
2 | Planning | Stakeholder mapping & kickoff | Jonas Reed | 2026-05-11 | 2026-05-15 | Completed | 8200 | 8400 | 100% | -200
3 | Planning | Site survey and geotechnical review | Priya Nanda | 2026-05-18 | 2026-05-29 | Completed | 42000 | 41850 | 100% | 150
4 | Design | Detailed engineering design | Marco Silva | 2026-06-01 | 2026-06-26 | In Progress | 165000 | 122000 | 75% | 43000
5 | Procurement | Tender package preparation | Nora Bennett | 2026-06-08 | 2026-06-19 | Completed | 18500 | 17680 | 100% | 820
6 | Procurement | Panel supplier selection | Nora Bennett | 2026-06-22 | 2026-07-10 | In Progress | 97500 | 60800 | 60% | 36700
7 | Procurement | Inverter procurement | Leo Kramer | 2026-07-01 | 2026-07-17 | Not Started | 148000 | 0 | 0% | 148000
8 | Construction | Ground works & civil prep | Helen Ward | 2026-07-13 | 2026-08-07 | Not Started | 320000 | 0 | 0% | 320000
9 | Construction | Mounting structure installation | Helen Ward | 2026-08-10 | 2026-08-28 | Not Started | 285000 | 0 | 0% | 285000
10 | Construction | PV panel installation | Ibrahim Musa | 2026-08-24 | 2026-09-18 | Not Started | 410000 | 0 | 0% | 410000
11 | Construction | Electrical cabling & inverter setup | Ibrahim Musa | 2026-09-07 | 2026-09-25 | Not Started | 298000 | 0 | 0% | 298000
12 | Quality | QA/QC inspections | Sofia Marin | 2026-09-14 | 2026-10-02 | Not Started | 56500 | 0 | 0% | 56500
13 | Handover | Grid compliance testing | Sofia Marin | 2026-10-05 | 2026-10-16 | Not Started | 73000 | 0 | 0% | 73000
14 | Handover | Client training and documentation | Jonas Reed | 2026-10-12 | 2026-10-23 | Not Started | 25500 | 0 | 0% | 25500
15 | Closure | Final acceptance & closeout | Amina Okafor | 2026-10-26 | 2026-10-30 | Not Started | 29800 | 0 | 0% | 29800
Status | Count |  | Phase | Planned Cost
Completed | 4 |  | Initiation | 6500
In Progress | 2 |  | Planning | 50200
Not Started | 9 |  | Design | 165000
Delayed | 0 |  | Procurement | 264000
On Hold | 0 |  | Construction | 1313000
|  |  | Quality | 56500
|  |  | Handover | 98500
|  |  | Closure | 29800

## Data Entry
PROJECT DATA ENTRY HUB
Company | NovaBuild Partners Ltd. |  |  | Project Sponsor | Daniel Mercer |  |  | Baseline Budget | 1850000 |  |  | Prepared By | Project Controls Office
Project Name | GreenBridge Solar Farm Rollout |  |  | Location | Lakemont, Westhaven |  |  | Contingency % | 8% |  |  | Version | v1.0
Client | City of Lakemont Energy Authority |  |  | Project Start | 2026-05-04 |  |  | Currency | USD |  |  | Last Updated | 2026-04-13
Project Manager | Amina Okafor |  |  | Project End | 2026-10-30 |  |  | Reporting Cycle | Monthly |  |  | Portfolio | Renewable Infrastructure
Enter or update project activity data below. All dashboard, budget and resource views update automatically.
ID | Phase | Activity / Deliverable | Department | Owner | Location | Start Date | End Date | Duration (Days) | Status | Priority | Risk | Planned Cost | Actual Cost | % Complete
1 | Initiation | Project charter approval | PMO | Amina Okafor | Lakemont | 2026-05-04 | 2026-05-08 | 5 | Completed | High | Low | 6500 | 6200 | 100%
2 | Planning | Stakeholder mapping & kickoff | PMO | Jonas Reed | Lakemont | 2026-05-11 | 2026-05-15 | 5 | Completed | High | Low | 8200 | 8400 | 100%
3 | Planning | Site survey and geotechnical review | Engineering | Priya Nanda | Lakemont | 2026-05-18 | 2026-05-29 | 12 | Completed | High | Medium | 42000 | 41850 | 100%
4 | Design | Detailed engineering design | Engineering | Marco Silva | Riverview | 2026-06-01 | 2026-06-26 | 26 | In Progress | High | Medium | 165000 | 122000 | 75%
5 | Procurement | Tender package preparation | Procurement | Nora Bennett | Lakemont | 2026-06-08 | 2026-06-19 | 12 | Completed | Medium | Low | 18500 | 17680 | 100%
6 | Procurement | Panel supplier selection | Procurement | Nora Bennett | Northgate | 2026-06-22 | 2026-07-10 | 19 | In Progress | High | Medium | 97500 | 60800 | 60%
7 | Procurement | Inverter procurement | Procurement | Leo Kramer | Northgate | 2026-07-01 | 2026-07-17 | 17 | Not Started | High | Medium | 148000 | 0 | 0%
8 | Construction | Ground works & civil prep | Construction | Helen Ward | Silver Plains | 2026-07-13 | 2026-08-07 | 26 | Not Started | High | High | 320000 | 0 | 0%
9 | Construction | Mounting structure installation | Construction | Helen Ward | Silver Plains | 2026-08-10 | 2026-08-28 | 19 | Not Started | High | High | 285000 | 0 | 0%
10 | Construction | PV panel installation | Construction | Ibrahim Musa | Silver Plains | 2026-08-24 | 2026-09-18 | 26 | Not Started | High | High | 410000 | 0 | 0%
11 | Construction | Electrical cabling & inverter setup | Construction | Ibrahim Musa | Silver Plains | 2026-09-07 | 2026-09-25 | 19 | Not Started | High | High | 298000 | 0 | 0%
12 | Quality | QA/QC inspections | Quality | Sofia Marin | Silver Plains | 2026-09-14 | 2026-10-02 | 19 | Not Started | Medium | Medium | 56500 | 0 | 0%
13 | Handover | Grid compliance testing | Quality | Sofia Marin | Lakemont | 2026-10-05 | 2026-10-16 | 12 | Not Started | High | Medium | 73000 | 0 | 0%
14 | Handover | Client training and documentation | PMO | Jonas Reed | Lakemont | 2026-10-12 | 2026-10-23 | 12 | Not Started | Medium | Low | 25500 | 0 | 0%
15 | Closure | Final acceptance & closeout | PMO | Amina Okafor | Lakemont | 2026-10-26 | 2026-10-30 | 5 | Not Started | High | Low | 29800 | 0 | 0%
Note on K6: Baseline budget before contingency. Use your approved project budget.
Note on K7: Contingency reserve applied on top of baseline budget for executive reporting.
Note on P15: Enter completion as a percentage from 0% to 100%.

## Monthly Budget
Monthly Budget & Cash Flow View
Automatically summarizes planned and actual cost by month from the Data Entry sheet.
Month | Planned Cost | Actual Cost | Variance | Cum. Planned | Cum. Actual | Budget Consumption | Forecast At Completion | Notes
2026-05-01 | 56700 | 56450 | 250 | 56700 | 56450 | 3.051% | 1850000
2026-06-01 | 281000 | 200480 | 80520 | 337700 | 256930 | 13.89% | 1927050
2026-07-01 | 468000 | 0 | 468000 | 805700 | 256930 | 13.89% | 1850000
2026-08-01 | 695000 | 0 | 695000 | 1500700 | 256930 | 13.89% | 1850000
2026-09-01 | 354500 | 0 | 354500 | 1855200 | 256930 | 13.89% | 1850000
2026-10-01 | 128300 | 0 | 128300 | 1983500 | 256930 | 13.89% | 1850000
TOTAL | 1983500 | 256930 | 1726570

## Resource Plan
Resource & Responsibility Summary
Auto-generated from activity ownership in Data Entry.
Owner | Department | Activities | Planned Cost | Actual Cost | Avg % Complete | High Risk Items | Next End Date
Amina Okafor | PMO | 2 | 36300 | 6200 | 50% | 0
Jonas Reed | PMO | 2 | 33700 | 8400 | 50% | 0
Priya Nanda | Engineering | 1 | 42000 | 41850 | 100% | 0
Marco Silva | Engineering | 1 | 165000 | 122000 | 75% | 0
Nora Bennett | Procurement | 2 | 116000 | 78480 | 80% | 0
Leo Kramer | Procurement | 1 | 148000 | 0 | 0% | 0
Helen Ward | Construction | 2 | 605000 | 0 | 0% | 2
Ibrahim Musa | Construction | 2 | 708000 | 0 | 0% | 2
Sofia Marin | Quality | 2 | 129500 | 0 | 0% | 0

## Instructions
Instructions ¦ Detailed Costed Workplan Workbook
1. What this workbook is | A Detailed Costed Workplan translates project scope into activities, dates, owners, costs and progress. This workbook combines schedule tracking, cost control and responsibility management into a single live reporting tool.
2. Core design principle | The Data Entry sheet is the single source of truth. Update project details and activity rows there. All other sheets pull from that sheet automatically using formulas.
3. Sheet guide | Main Template = executive dashboard and live workplan. Data Entry = project details plus activity-level inputs. Monthly Budget = month-by-month cost summary and cash-flow trend. Resource Plan = ownership, accountability and workload cost view. Instructions = user manual. Lists = dropdown options used for data validation.
4. How to enter project details | Go to Data Entry. Update Company, Project Name, Client, Project Manager, Sponsor, dates, baseline budget, contingency and reporting cycle in the top section.
5. How to enter activities | In rows 16 to 40 of Data Entry, fill ID, Phase, Activity / Deliverable, Department, Owner, Location, Start Date, End Date, Status, Priority, Risk, Planned Cost, Actual Cost and % Complete. Duration calculates automatically.
6. Allowed values | Status values: Not Started, In Progress, Completed, Delayed, On Hold. Priority values: High, Medium, Low. Risk values: High, Medium, Low. Department and Location use dropdown lists to keep reporting consistent.
7. How updates flow | If you change an owner, cost, date or progress in Data Entry, the Main Template, Monthly Budget and Resource Plan sheets refresh automatically because they are formula-linked.
8. How to read the dashboard | Use the KPI cards for quick control: budget utilization, planned schedule span, average completion and contingency remaining. The live workplan section shows task-level cost variance and status. Charts visualize status mix and cost by phase.
9. How to control cost | Compare Planned Cost and Actual Cost per activity. Positive variance on the Main Template means you are under budget when actual is below plan. Monthly Budget helps monitor spend timing and cumulative consumption.
10. How to control schedule | Start and End dates define the activity window. Duration is calculated automatically. Use Status and % Complete together: for example, an activity can be In Progress at 60% complete.
11. Recommended operating rhythm | Update actual cost and % complete weekly. Review dashboard metrics with the project team weekly and with sponsors monthly. Lock a monthly reporting date for version control.
12. Best practices | Keep activity names short and action-oriented. Assign one owner per task. Use realistic planned costs. Mark delayed items immediately. Review high-risk items before they affect schedule or budget.
13. Customization tips | You can extend Data Entry with more rows, add locations to the Lists sheet, or copy formulas downward. Keep the same column structure so linked reports continue to work.

## Lists
Statuses | Priority | Departments | Locations | Risk
Not Started | High | PMO | Lakemont | High
In Progress | Medium | Engineering | Riverview | Medium
Completed | Low | Procurement | Northgate | Low
Delayed |  | Construction | Silver Plains
On Hold |  | Quality
HSE
Finance