## Main Template
Gantt Chart
A polished, senior-PM ready schedule for a realistic office relocation program — timeline, dependencies, ownership, milestones, status and budget visibility
2026-04-06
| Project |  |  |  | Client |  |  |  | PMO Lead |  |  |  | Status Date |  |  |  | Overall Progress |  |  |  | Total Budget |  |  |  | Legend
| Northstar Digital HQ Relocation Program |  |  |  | Meridian Peak Holdings |  |  |  | Ava Sterling |  |  |  | 2026-06-19 |  |  |  | 52.19% |  |  |  | 835500 |  |  |  | Completed
Planned
Weekly Timeline
ID | Phase | Task / Milestone | Type | Owner | Start | Finish | Dur. | % Comp. | Status | Predecessor | Location | Budget | Priority | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
1 | Initiation | Project kickoff | Milestone | Ava Sterling | 2026-04-06 | 2026-04-06 | 1 | 100% | Complete | - | Rivergate, NY | 0 | High | 3
2 | Initiation | Current-state site assessment | Task | Milo Chen | 2026-04-07 | 2026-04-17 | 11 | 100% | Complete | 1 | Rivergate, NY | 18500 | High | 2 | 1
3 | Planning | Space design concept | Task | Nina Brooks | 2026-04-20 | 2026-05-08 | 19 | 85% | In Progress | 2 | Rivergate, NY | 42000 | High |  |  | 2 | 2 | 1
4 | Planning | Lease negotiation sign-off | Milestone | Elijah Hart | 2026-05-12 | 2026-05-12 | 1 | 100% | Complete | 3 | Rivergate, NY | 0 | High | [5 empty] | 3
5 | Planning | IT infrastructure blueprint | Task | Priya Raman | 2026-05-04 | 2026-05-29 | 26 | 75% | In Progress | 2 | Rivergate, NY | 68000 | High |  |  |  |  | 2 | 2 | 1 | 1
6 | Execution | Construction and fit-out | Task | Jonas Reed | 2026-05-18 | 2026-07-17 | 61 | 45% | In Progress | 4 | Rivergate, NY | 375000 | High | [6 empty] | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
7 | Execution | Furniture procurement | Task | Sofia Bennett | 2026-05-18 | 2026-06-26 | 40 | 60% | In Progress | 4 | Brookhollow, NJ | 128000 | Medium | [6 empty] | 2 | 2 | 2 | 1 | 1 | 1
8 | Execution | Telecom and network installation | Task | Priya Raman | 2026-06-01 | 2026-07-10 | 40 | 25% | In Progress | 5,6 | Rivergate, NY | 94000 | High | [8 empty] | 2 | 1 | 1 | 1 | 1 | 1
9 | Execution | Change management & staff communications | Task | Lena Ortiz | 2026-05-25 | 2026-08-07 | 75 | 55% | In Progress | 4 | Rivergate, NY | 36000 | Medium | [7 empty] | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
10 | Execution | Move readiness review | Milestone | Ava Sterling | 2026-07-24 | 2026-07-24 | 1 | 0% | Not Started | 6,7,8 | Rivergate, NY | 0 | High | [15 empty] | 3
11 | Closure | Physical move weekend | Task | Owen Price | 2026-08-01 | 2026-08-03 | 3 | 0% | Not Started | 10 | Rivergate, NY | 52000 | High | [16 empty] | 1 | 1
12 | Closure | Hypercare support | Task | Milo Chen | 2026-08-04 | 2026-08-14 | 11 | 0% | Not Started | 11 | Rivergate, NY | 22000 | Medium | [17 empty] | 1 | 1
13 | Closure | Project closure report | Milestone | Ava Sterling | 2026-08-28 | 2026-08-28 | 1 | 0% | Not Started | 12 | Rivergate, NY | 0 | Medium | [20 empty] | 3
Management notes • Update only the Data Entry sheet. • The Main Template refreshes automatically. • Green bars = completed work, blue bars = remaining planned work, orange = milestone. • Red emphasis supports leadership review of schedule issues.

## Data Entry
Project Gantt Chart Template — Data Entry Hub
Hypothetical project: Northstar Digital HQ Relocation Program ¦ Client: Meridian Peak Holdings ¦ Delivery Partner: BlueHarbor Consulting
| Project Name | Northstar Digital HQ Relocation Program |  |  |  |  | Program Start | 2026-04-06
| Client | Meridian Peak Holdings |  |  |  |  | Program End | 2026-08-28
| PMO Lead | Ava Sterling |  |  |  |  | Status Date | 2026-06-19
ID | Phase | Task / Milestone | Type | Owner | Start Date | End Date | Duration (days) | % Complete | Status | Predecessor | Location | Budget ($) | Priority | Notes
1 | Initiation | Project kickoff | Milestone | Ava Sterling | 2026-04-06 | 2026-04-06 | 1 | 100% | Complete | - | Rivergate, NY | 0 | High | Formal launch with sponsor and workstream leads
2 | Initiation | Current-state site assessment | Task | Milo Chen | 2026-04-07 | 2026-04-17 | 11 | 100% | Complete | 1 | Rivergate, NY | 18500 | High | Facilities, IT, security and occupancy walkthroughs
3 | Planning | Space design concept | Task | Nina Brooks | 2026-04-20 | 2026-05-08 | 19 | 85% | In Progress | 2 | Rivergate, NY | 42000 | High | Concept layouts and seating plans
4 | Planning | Lease negotiation sign-off | Milestone | Elijah Hart | 2026-05-12 | 2026-05-12 | 1 | 100% | Complete | 3 | Rivergate, NY | 0 | High | Board-approved lease execution
5 | Planning | IT infrastructure blueprint | Task | Priya Raman | 2026-05-04 | 2026-05-29 | 26 | 75% | In Progress | 2 | Rivergate, NY | 68000 | High | Network, AV, access control and server-room design
6 | Execution | Construction and fit-out | Task | Jonas Reed | 2026-05-18 | 2026-07-17 | 61 | 45% | In Progress | 4 | Rivergate, NY | 375000 | High | General contractor mobilization through practical completion
7 | Execution | Furniture procurement | Task | Sofia Bennett | 2026-05-18 | 2026-06-26 | 40 | 60% | In Progress | 4 | Brookhollow, NJ | 128000 | Medium | Desks, meeting rooms, reception and break areas
8 | Execution | Telecom and network installation | Task | Priya Raman | 2026-06-01 | 2026-07-10 | 40 | 25% | In Progress | 5,6 | Rivergate, NY | 94000 | High | Carrier circuit, core switch, Wi-Fi and room systems
9 | Execution | Change management & staff communications | Task | Lena Ortiz | 2026-05-25 | 2026-08-07 | 75 | 55% | In Progress | 4 | Rivergate, NY | 36000 | Medium | Town halls, FAQs, training and floor-neighborhood briefings
10 | Execution | Move readiness review | Milestone | Ava Sterling | 2026-07-24 | 2026-07-24 | 1 | 0% | Not Started | 6,7,8 | Rivergate, NY | 0 | High | Go / no-go review with sponsor and vendors
11 | Closure | Physical move weekend | Task | Owen Price | 2026-08-01 | 2026-08-03 | 3 | 0% | Not Started | 10 | Rivergate, NY | 52000 | High | Pack, transport, set-up and day-1 support
12 | Closure | Hypercare support | Task | Milo Chen | 2026-08-04 | 2026-08-14 | 11 | 0% | Not Started | 11 | Rivergate, NY | 22000 | Medium | Issue triage, desk moves and snag resolution
13 | Closure | Project closure report | Milestone | Ava Sterling | 2026-08-28 | 2026-08-28 | 1 | 0% | Not Started | 12 | Rivergate, NY | 0 | Medium | Benefits review, lessons learned and formal close
Data Summary | Total Tasks / Milestones | 13 | Total Budget | 835500 | Weighted Progress | 52.19% | Open Items | 10

## Instructions
How to Use This Gantt Chart Template
Designed like a senior project manager would present it: clean controls, realistic data, decision-ready visuals and easy maintenance.
Step | Area | Explanation
1 | Purpose | This workbook is built to plan, communicate and monitor a project schedule visually. It explains the full scope of a Gantt chart: task list, ownership, timing, dependencies, milestones, completion progress, budget and schedule status.
2 | Where to edit | Go to the Data Entry sheet to update project details, task rows, dates, owners, budget, status and percent complete. The Main Template is presentation-ready and should generally not be typed over.
3 | Task types | Use 'Task' for normal activities and 'Milestone' for one-day checkpoints or approvals. Milestones show as orange markers in the timeline.
4 | Dependencies | Use the Predecessor column to note the task ID(s) that must occur before the current activity. Example: '5,6' means Task 5 and Task 6 should finish first.
5 | Status discipline | Recommended status logic: Not Started = work has not begun; In Progress = active now; Complete = finished; At Risk = likely issue; Delayed = already off plan.
6 | Progress tracking | Enter % Complete as a value from 0% to 100%. On the Main Template, the completed portion of each bar is green and the planned remainder is blue.
7 | Overdue highlighting | If a task finish date is earlier than the Status Date and the item is not Complete, the row is softly highlighted to draw attention in leadership reviews.
8 | Recommended PM cadence | Update the Data Entry sheet weekly before your governance meeting. Review critical path items, upcoming milestones, delayed tasks, budget-heavy items and owner accountability.
9 | Color language used | Dark blues structure the template, greens indicate healthy progress, orange is used for milestones / caution, gold for active work, and red highlights risk or delay.
10 | Hypothetical example | This workbook uses fictional companies, locations and people to feel realistic: Meridian Peak Holdings, BlueHarbor Consulting, Rivergate, NY and Brookhollow, NJ.
Palette used in workbook
#2F5597 | Core title/header blue
#1F3A5F | Deep executive navy
#548235 | Section green
#92D050 | Completed progress
#ED7D31 | Milestones / caution
#C00000 | Delay / issue emphasis
#FFC000 | Active work / in progress
#70AD47 | KPI progress highlight
#4472C4 | Planned work / accent blue