## Main Template
Gap Analysis | [13 empty] | Priority Summary
Northstar Infrastructure Solutions ¦ Orion Tower Redevelopment Program ¦ Austin, Texas | [13 empty] | High | 6
Client | Helio Properties Group | Program Sponsor | Liam Chen | Senior PM | Ava Morgan | Reporting Date | 2026-04-15 | Review Cycle | Weekly | Overall Health |  | Amber |  | Medium | 5
[14 empty] | Low | 1
Total Gaps |  |  | High Priority |  | Delayed |  |  | Avg Completion |  |  | Budget Exposure
12 |  |  | 6 |  | 1 |  |  | 34.17% |  |  | 340500 |  |  | Status Summary
[14 empty] | Not Started | 4
Integrated Gap Register (auto-linked from Data Entry sheet) | [13 empty] | In Progress | 7
Gap ID | Area | Current State | Desired State | Gap | Root Cause | Impact | Priority | Owner | Target Date | Status | Completion | Budget Impact | Comments | Completed | 0
GA-001 | Governance | Weekly governance meetings happen inconsistently; minutes are not centrally filed. | Weekly governance cadence with tracked decisions and action logs. | Inconsistent governance rhythm and no single source of truth for decisions. | Undefined meeting owner and no reporting discipline. | Leadership misalignment and delayed approvals. | High | Ava Morgan | 2026-04-10 | In Progress | 60% | 18500 | PMO templates drafted; action log pilot in progress. | Delayed | 1
GA-002 | Schedule Management | Look-ahead schedule covers only 2 weeks and is manually updated. | Rolling 6-week look-ahead linked to master schedule. | Planning horizon is too short to proactively resolve clashes. | Scheduler capacity is limited and site teams update late. | Missed dependencies and avoidable schedule slippage. | High | Noah Patel | 2026-04-05 | In Progress | 45% | 32000 | Need subcontractor commitment to weekly updates.
GA-003 | Cost Control | Change orders are tracked in email and not reconciled weekly. | Centralized change log with weekly commercial review. | Change visibility is poor; approved vs pending items are unclear. | Fragmented tracking across commercial and site teams. | Budget overruns and invoice disputes. | High | Mia Thompson | 2026-04-18 | Not Started | 15% | 64000 | Commercial lead starts next Monday. | Management Notes
GA-004 | Quality Assurance | Defect data is logged, but repeat issues are not categorized. | Defects categorized by root cause with trend analysis. | Team cannot identify recurring quality failure patterns. | No standard defect coding framework. | Rework cost and client confidence risk. | Medium | Sofia Brooks | 2026-04-22 | In Progress | 40% | 21000 | QA checklist revision underway. | Use this area during leadership reviews to summarize decisions, escalations, and approved actions. Example: • Fast-track document control clean-up by April 8 • Add procurement risk review to weekly governance • Assign commercial analyst to change order reconciliation
GA-005 | Safety | Near-miss reports are submitted, but closure actions lag. | Near-miss corrective actions closed within 5 business days. | Action closure discipline is weak after incident reporting. | Supervisors lack follow-up reminders and ownership visibility. | Residual safety exposure and audit findings. | High | Ethan Walker | 2026-04-03 | Delayed | 30% | 28000 | Need daily closure review in toolbox talk.
GA-006 | Procurement | Long-lead materials tracker is updated only at month-end. | Weekly long-lead tracker with red/amber/green supplier signals. | Procurement risks are escalated too late. | Supplier updates are not standardized across packages. | Material delays could affect critical path. | High | Grace Bennett | 2026-04-12 | In Progress | 55% | 47000 | Steel package at risk due to vendor submittals.
GA-007 | Stakeholder Engagement | Tenant coordination meetings occur ad hoc and issues are reactive. | Fortnightly tenant coordination with published issue log. | Stakeholder concerns surface late and create rework. | No standard engagement calendar or comms plan. | Client dissatisfaction and disruption to occupancy planning. | Medium | Lucas Reed | 2026-04-25 | Not Started | 10% | 15000 | Draft engagement calendar created.
GA-008 | Document Control | Drawing revisions are stored in multiple folders with inconsistent naming. | Controlled repository with naming convention and revision register. | Teams may use outdated drawings in the field. | No enforced folder structure or document controller checkpoints. | Construction errors and claims risk. | High | Emma Hughes | 2026-04-08 | In Progress | 65% | 39000 | Folder clean-up 70% complete.
GA-009 | Resource Planning | Trade foremen allocations are set week to week without capacity view. | Four-week resource plan by trade with constraints review. | Resource bottlenecks are not visible early enough. | No consolidated labor forecast from trade partners. | Productivity loss and overtime pressure. | Medium | Oliver Grant | 2026-04-20 | In Progress | 35% | 26000 | Need partner labor forecast template.
GA-010 | Risk Management | Risk register exists but mitigation owners do not update actions. | Monthly risk review with owner accountability and due dates. | Risk mitigation actions are stale and not driving decisions. | Risk reviews are not embedded in monthly governance. | Unmanaged exposure to scope, cost, and schedule threats. | Medium | Harper Cole | 2026-04-28 | Not Started | 5% | 18000 | Risk workshop scheduled with leadership.
GA-011 | Training & Capability | New supervisors have no onboarding to project controls tools. | Structured onboarding with tool training in first 10 days. | Capability gap reduces consistency in reporting and controls. | Rapid mobilization with no standard induction package. | Data quality issues and slow issue resolution. | Low | Chloe Rivera | 2026-05-02 | Not Started | 0% | 9000 | LMS content outline prepared.
GA-012 | Reporting | Monthly report is manually compiled from several sources over 2 days. | Automated monthly dashboard generated in under 2 hours. | Reporting cycle is slow and prone to version errors. | Source data is decentralized and manually consolidated. | Late executive insight and inefficient PMO effort. | Medium | Daniel Foster | 2026-04-15 | In Progress | 50% | 23000 | Power Query pilot planned.

## Data Entry
Gap Analysis Data Entry ¦ Northstar Infrastructure Solutions
Project: Orion Tower Redevelopment Program ¦ Location: Austin, Texas ¦ Program Sponsor: Liam Chen ¦ PM: Ava Morgan
Enter or update project gaps below. The Main Template sheet pulls live from this data.
Gap ID | Workstream / Area | Current State | Desired Future State | Gap Description | Root Cause | Impact | Priority | Owner | Target Date | Status | Completion % | Budget Impact ($) | Comments
GA-001 | Governance | Weekly governance meetings happen inconsistently; minutes are not centrally filed. | Weekly governance cadence with tracked decisions and action logs. | Inconsistent governance rhythm and no single source of truth for decisions. | Undefined meeting owner and no reporting discipline. | Leadership misalignment and delayed approvals. | High | Ava Morgan | 2026-04-10 | In Progress | 60% | 18500 | PMO templates drafted; action log pilot in progress.
GA-002 | Schedule Management | Look-ahead schedule covers only 2 weeks and is manually updated. | Rolling 6-week look-ahead linked to master schedule. | Planning horizon is too short to proactively resolve clashes. | Scheduler capacity is limited and site teams update late. | Missed dependencies and avoidable schedule slippage. | High | Noah Patel | 2026-04-05 | In Progress | 45% | 32000 | Need subcontractor commitment to weekly updates.
GA-003 | Cost Control | Change orders are tracked in email and not reconciled weekly. | Centralized change log with weekly commercial review. | Change visibility is poor; approved vs pending items are unclear. | Fragmented tracking across commercial and site teams. | Budget overruns and invoice disputes. | High | Mia Thompson | 2026-04-18 | Not Started | 15% | 64000 | Commercial lead starts next Monday.
GA-004 | Quality Assurance | Defect data is logged, but repeat issues are not categorized. | Defects categorized by root cause with trend analysis. | Team cannot identify recurring quality failure patterns. | No standard defect coding framework. | Rework cost and client confidence risk. | Medium | Sofia Brooks | 2026-04-22 | In Progress | 40% | 21000 | QA checklist revision underway.
GA-005 | Safety | Near-miss reports are submitted, but closure actions lag. | Near-miss corrective actions closed within 5 business days. | Action closure discipline is weak after incident reporting. | Supervisors lack follow-up reminders and ownership visibility. | Residual safety exposure and audit findings. | High | Ethan Walker | 2026-04-03 | Delayed | 30% | 28000 | Need daily closure review in toolbox talk.
GA-006 | Procurement | Long-lead materials tracker is updated only at month-end. | Weekly long-lead tracker with red/amber/green supplier signals. | Procurement risks are escalated too late. | Supplier updates are not standardized across packages. | Material delays could affect critical path. | High | Grace Bennett | 2026-04-12 | In Progress | 55% | 47000 | Steel package at risk due to vendor submittals.
GA-007 | Stakeholder Engagement | Tenant coordination meetings occur ad hoc and issues are reactive. | Fortnightly tenant coordination with published issue log. | Stakeholder concerns surface late and create rework. | No standard engagement calendar or comms plan. | Client dissatisfaction and disruption to occupancy planning. | Medium | Lucas Reed | 2026-04-25 | Not Started | 10% | 15000 | Draft engagement calendar created.
GA-008 | Document Control | Drawing revisions are stored in multiple folders with inconsistent naming. | Controlled repository with naming convention and revision register. | Teams may use outdated drawings in the field. | No enforced folder structure or document controller checkpoints. | Construction errors and claims risk. | High | Emma Hughes | 2026-04-08 | In Progress | 65% | 39000 | Folder clean-up 70% complete.
GA-009 | Resource Planning | Trade foremen allocations are set week to week without capacity view. | Four-week resource plan by trade with constraints review. | Resource bottlenecks are not visible early enough. | No consolidated labor forecast from trade partners. | Productivity loss and overtime pressure. | Medium | Oliver Grant | 2026-04-20 | In Progress | 35% | 26000 | Need partner labor forecast template.
GA-010 | Risk Management | Risk register exists but mitigation owners do not update actions. | Monthly risk review with owner accountability and due dates. | Risk mitigation actions are stale and not driving decisions. | Risk reviews are not embedded in monthly governance. | Unmanaged exposure to scope, cost, and schedule threats. | Medium | Harper Cole | 2026-04-28 | Not Started | 5% | 18000 | Risk workshop scheduled with leadership.
GA-011 | Training & Capability | New supervisors have no onboarding to project controls tools. | Structured onboarding with tool training in first 10 days. | Capability gap reduces consistency in reporting and controls. | Rapid mobilization with no standard induction package. | Data quality issues and slow issue resolution. | Low | Chloe Rivera | 2026-05-02 | Not Started | 0% | 9000 | LMS content outline prepared.
GA-012 | Reporting | Monthly report is manually compiled from several sources over 2 days. | Automated monthly dashboard generated in under 2 hours. | Reporting cycle is slow and prone to version errors. | Source data is decentralized and manually consolidated. | Late executive insight and inefficient PMO effort. | Medium | Daniel Foster | 2026-04-15 | In Progress | 50% | 23000 | Power Query pilot planned.

## Instructions
How to Use This Gap Analysis Template
Designed for project managers, PMOs, construction teams, transformation programs, and operational improvement leaders.
1. Purpose | This workbook helps compare the current state of a project or process against the desired future state, identify gaps, assign actions, and track closure progress.
2. Sheet Overview | Main Template: Executive-ready register with KPIs, charts, live-linked gap list, and review notes. Data Entry: Input all gap details here. The Main Template sheet updates automatically. Instructions: Operating guide, field definitions, and formatting legend.
3. Recommended Workflow | 1) Add or update one row per gap in Data Entry. 2) Define the current state and desired future state clearly. 3) Describe the gap and root cause in plain business language. 4) Assign priority, owner, target date, and status. 5) Update Completion % weekly. 6) Review Main Template during governance meetings.
4. Field Definitions | Gap ID: Unique reference code. Workstream / Area: Function, stream, or department affected. Current State: What is happening today. Desired Future State: What good looks like. Gap Description: The specific gap between current and desired states. Root Cause: Why the gap exists. Impact: Delivery, cost, quality, compliance, safety, or stakeholder effect. Priority: High / Medium / Low. Owner: Person accountable for closure. Target Date: Planned close date. Status: Not Started / In Progress / Completed / Delayed. Completion %: Enter as a percentage. Budget Impact ($): Estimated exposure or improvement value. Comments: Latest note, dependency, or next step.
5. Good Practice Tips | • Keep each gap actionable and specific. • Use measurable desired states where possible. • Focus comments on the next action and blocker. • Review High priority and Delayed items first. • Archive closed items periodically if the register becomes large.
6. Color Legend | Dark blue headers = title / major sections Blue headers = core data sections Green headers = ownership / planning fields Orange headers = progress / action tracking Yellow = attention or exposure Light red / amber / green = status and progress signals
7. Hypothetical Scenario Used | Company: Northstar Infrastructure Solutions Client: Helio Properties Group Program: Orion Tower Redevelopment Program Location: Austin, Texas Sample leaders: Ava Morgan, Liam Chen, Noah Patel, Mia Thompson, Sofia Brooks
Tip: Duplicate the Data Entry sheet if you want a fresh issue log for a new project, then relink formulas if needed.