## Issue Tracker
Strategic Issue Tracker ¦ Crestline BuildWorks PMO
Program: Orion Office Campus Modernization ¦ Sponsor: Northwind Commercial Group ¦ Reporting Period: Q2 FY2026
Open Issues |  |  |  |  | Critical Issues |  |  |  |  | Overdue Items |  |  |  |  | Avg Days Open |  |  |  |  | Escalated
11 |  |  |  |  | 2 |  |  |  |  | 9 |  |  |  |  | 70.0833 |  |  |  |  | 2
Issue ID | Date Reported | Project | Site / Location | Business Unit | Issue Title | Category | Priority | Severity | Impact Area | Impact Summary | Reported By | Owner | Department | Status | Root Cause | Action Plan | Target Resolution | Days Open | Resolution Date | Ageing Bucket | Overdue Flag | Escalation Level | Comments / Latest Update | Last Updated
ISS-2026-001 | 2026-01-07 | Orion Office Campus Modernization | Seattle HQ Tower A | Corporate Real Estate | Permit revision pending for lobby fire doors | Compliance | High | Major | Timeline | Authority review may delay practical completion by 7 days. | Maya Chen | Gavin Mercer | Facilities Delivery | In Progress | Revised egress drawings were submitted late after design markups. | Submit stamped revision set and hold twice-weekly permit calls. | 2026-01-16 | 98 |  | 31+ days | Overdue | Watchlist | City reviewer requested one more code clarification. | 2026-01-12
ISS-2026-002 | 2026-01-10 | Orion Office Campus Modernization | Seattle HQ Tower B | Technology Enablement | Network switch lead time exceeds baseline | Vendor | Critical | Critical | Timeline | Floor-by-floor cutover will slip unless substitute stock is approved. | Noah Patel | Priya Kline | IT Delivery | Escalated | Primary supplier allocation reduced for Q1 shipments. | Approve alternate manufacturer and re-sequence cabling teams. | 2026-01-20 | 95 |  | 31+ days | Overdue | Escalated | Executive procurement review scheduled with Falcon Systems. | 2026-01-15
ISS-2026-003 | 2026-01-14 | Orion Office Campus Modernization | Bellevue Data Hub | Technology Enablement | Server room cooling alarms caused by sensor drift | Technical | Medium | Moderate | Operations | Temporary nuisance alarms affecting handover tests. | Iris Bennett | Owen Clarke | Operations | Resolved | Sensor calibration values not aligned after firmware update. | Recalibrate sensors and validate with 48-hour trending. | 2026-01-18 | 91 |  | 31+ days | On Track | Monitor | Trend logs stable; ready for closure in next governance meeting. | 2026-01-17
ISS-2026-004 | 2026-01-19 | Orion Office Campus Modernization | Seattle HQ Tower A | Corporate Real Estate | Stone cladding color mismatch on east facade | Quality | High | Major | Quality | Visible finish variance on executive entrance elevation. | Leo Martinez | Amara Singh | Quality Assurance | Open | Batch approval sample was not cross-checked against full production run. | Hold installation, review mock-up, and issue supplier NCR. | 2026-01-28 | 86 |  | 31+ days | Overdue | Watchlist | Supplier offered replacement lots with 12-day turnaround. | 2026-01-22
ISS-2026-005 | 2026-01-23 | Orion Office Campus Modernization | Portland Regional Office | Shared Services | Furniture package over budget by 8.6% | Cost | Medium | Moderate | Budget | Workspace fit-out package exceeds approved capex allowance. | Ava Brooks | Daniel Frost | Finance | In Progress | Final specification included premium finishes without cost challenge. | Value engineer package and secure commercial credit from vendor. | 2026-02-03 | 82 |  | 31+ days | Overdue | Monitor | Finance requested revised estimate with savings options. | 2026-01-30
ISS-2026-006 | 2026-01-30 | Orion Office Campus Modernization | Bellevue Data Hub | Technology Enablement | Access control reader failures at loading dock | Safety | Critical | Critical | Safety | Loading bay cannot be fully secured during late deliveries. | Sofia Ramirez | Priya Kline | Health & Safety | In Progress | Moisture ingress behind reader back boxes during wash-down. | Install weatherproof housing and add overnight guard coverage. | 2026-02-02 | 75 |  | 31+ days | Overdue | Escalated | Temporary security patrol approved until permanent fix verified. | 2026-02-01
ISS-2026-007 | 2026-02-05 | Orion Office Campus Modernization | Seattle HQ Tower B | Corporate Real Estate | Elevator car finish scratched during final cleaning | Quality | Low | Minor | Quality | Cosmetic defect limited to one passenger elevator cab. | Ethan Cole | Gavin Mercer | Facilities Delivery | Closed | Protective film removed before heavy materials movement completed. | Replace panel set and update sequence for remaining cars. | 2026-02-10 | 69 |  | 31+ days | On Track | Monitor | Closed after replacement panel installed and client accepted finish. | 2026-02-10
ISS-2026-008 | 2026-02-11 | Orion Office Campus Modernization | Portland Regional Office | Technology Enablement | AV room rack layout clashes with sprinkler pipework | Design Change | High | Major | Scope | Boardroom go-live at risk unless rack orientation is revised. | Mila Thompson | Owen Clarke | IT Delivery | On Hold | Coordination model was not refreshed after fire protection redesign. | Issue updated coordinated drawing and reprice installers. | 2026-02-19 | 63 |  | 31+ days | Overdue | Watchlist | Awaiting MEP consultant approval on alternate rack footprint. | 2026-02-15
ISS-2026-009 | 2026-02-18 | Orion Office Campus Modernization | Seattle HQ Tower A | Corporate Real Estate | Temporary power outage interrupted floor finish curing | Schedule | Medium | Moderate | Timeline | One fit-out zone needs 2 additional curing days. | Harper Lewis | Amara Singh | PMO | Resolved | Generator handover between subcontractors was poorly coordinated. | Refresh shutdown permit workflow and add hold-point checklist. | 2026-02-24 | 56 |  | 31+ days | On Track | Monitor | Recovery plan accepted; impact absorbed in float. | 2026-02-22
ISS-2026-010 | 2026-02-25 | Orion Office Campus Modernization | Bellevue Data Hub | Technology Enablement | Backup generator fuel sampling failed quality spec | Vendor | High | Major | Operations | Commissioning cannot complete until compliant fuel is delivered. | Zoe Carter | Daniel Frost | Procurement | Open | Supplier delivered product from non-approved depot. | Reject batch, expedite replacement, and apply service credit. | 2026-03-03 | 49 |  | 31+ days | Overdue | Watchlist | Replacement tanker booked for Monday AM. | 2026-02-27
ISS-2026-011 | 2026-03-04 | Orion Office Campus Modernization | Seattle HQ Tower B | Shared Services | Move management communications not sent to all occupants | Communication | Medium | Moderate | Customer | Business readiness impacted for two departments. | Jacob Reed | Lena Ortiz | PMO | In Progress | Distribution list omitted contractor-managed teams. | Reissue pack, add FAQs, and run floor captain briefing. | 2026-03-08 | 42 |  | 31+ days | Overdue | Monitor | Second communication sent with corrected distribution list. | 2026-03-05
ISS-2026-012 | 2026-03-11 | Orion Office Campus Modernization | Seattle HQ Tower B | Technology Enablement | Conference room tablets not pairing with scheduling platform | Technical | High | Major | Operations | Twelve rooms unavailable for live scheduling during pilot week. | Chloe Morgan | Priya Kline | IT Delivery | Open | Tablet firmware image incompatible with latest scheduling app build. | Rollback image, retest MDM policy, and publish hotfix package. | 2026-03-17 | 35 |  | 31+ days | Overdue | Watchlist | Pilot users using manual bookings as temporary workaround. | 2026-03-14
Formulas:
Days Open = IF([Open Issues]="","",IF([Resolution Date]<>"",[Resolution Date]-[Date Reported],TODAY()-[Date Reported]))
Overdue Flag = IF([Open Issues]="","",IF(AND([Resolution Date]="",[Target Resolution]<TODAY(),[Status]<>"Closed",[Status]<>"Resolved"),"Overdue","On Track"))
Note on A5: Unique issue reference. Example: ISS-2026-013
Note on S5: Formula-driven aging in days. Calculated from Date Reported to Resolution Date or today.
Note on V5: Formula-driven alert: flagged Overdue when target date has passed and issue is not Resolved/Closed.

## Data Entry
Issue Intake Form & Validation Lists
Use this sheet to stage new issues before copying them into the main tracker. Validation lists at the right drive dropdowns.
New Issue ID | ISS-2026-021 | Example Use | Category | Priority | Severity | ImpactArea | Status | Department | Escalation
Date Reported | 2026-03-28 | 1) Complete fields in column B | Technical | Low | Minor | Timeline | Open | PMO | Monitor
Project | Orion Office Campus Modernization | 2) Use dropdowns for controlled values | Resource | Medium | Moderate | Budget | In Progress | IT Delivery | Watchlist
Site / Location | Seattle HQ Tower B | 3) Copy values to next blank row in Issue Tracker | Cost | High | Major | Scope | On Hold | Facilities Delivery | Escalated
Business Unit | Corporate Real Estate | 4) Do not type over formula columns in the main sheet | Schedule | Critical | Critical | Quality | Resolved | Finance
Issue Title | Elevator commissioning delayed after firmware mismatch |  | Quality |  |  | Safety | Closed | Procurement
Category | Schedule |  | Communication |  |  | Customer | Escalated | Quality Assurance
Priority | High |  | Vendor |  |  | Operations |  | Health & Safety
Severity | Major |  | Compliance |  |  | Compliance |  | Operations
Impact Area | Timeline |  | Safety
Impact Summary | Final occupancy sign-off may slip by 5 working days unless vendor patch is approved. |  | Design Change
Reported By | Lena Ortiz
Owner | Gavin Mercer
Department | Facilities Delivery
Status | Open
Root Cause | Vendor patch not validated against site controller revision.
Action Plan | Fast-track vendor test window; confirm rollback plan; daily review with OT security.
Target Resolution | 2026-04-03
Resolution Date
Escalation Level | Monitor
Comments / Latest Update | Awaiting vendor test script and revised installation method statement.

## Instructions
How to Use This Issue Tracker
Purpose | This workbook gives project teams a disciplined way to log, assign, analyze, and close delivery issues. It is designed for PMO governance, site teams, functional leads, and steering committees. | Recommended Triage
Critical + Critical
Sheet 1 ¦ Issue Tracker | Use the main tracker for your live issue register. Every row is one issue. KPI cards summarize open, critical, overdue, average age, and escalated items. Filter by status, owner, location, or department during reviews. | High + Major
Medium + Moderate
Sheet 2 ¦ Data Entry | Use the intake form to draft a new issue with consistent dropdown values. Once complete, copy the values into the next blank row on the main tracker. | Low + Minor
Close quickly; avoid clutter in governance pack
Required Fields | At minimum, complete: Issue ID, Date Reported, Project, Issue Title, Category, Priority, Severity, Impact Area, Owner, Department, Status, Target Resolution, and Comments.
Status Guidance | Open = logged but not yet being worked; In Progress = owner actively driving action; On Hold = blocked by dependency; Resolved = fix implemented and awaiting confirmation; Closed = fully verified and complete; Escalated = raised for management intervention.
Priority vs Severity | Priority answers 'How fast should we act?'. Severity answers 'How bad is the impact?'. Use Critical only where delivery, safety, compliance, or operations face immediate risk.
Formula Fields | Days Open, Ageing Bucket, and Overdue Flag are formula-driven on the main tracker. Do not overwrite those columns.
Good PMO Practice | Review issues weekly, challenge stale actions, confirm owners, and always record the latest update with a date so the register tells the current story.
Hypothetical Context | Sample data uses fictional organizations and names such as Crestline BuildWorks, Northwind Commercial Group, Falcon Systems, Lena Ortiz, Priya Kline, and Seattle HQ Tower B.
Visual Key
Blue headers | Structure and governance sections
Green blocks | Positive/closed status or guidance
Amber / Orange | Watch items and medium/high urgency
Red | Critical or escalated attention
Yellow highlight | Aging items requiring review