## Kanban Board
KANBAN BOARD
ApexNova Consulting • NorthStar Transformation Program • Rivergate Tower, Austin • PMO Command Center
Project Sponsor | Elena Foster |  |  | Total Tasks |  | Completed |  | In Progress | Blocked |  | Due in 7 Days
Project Manager | Jordan Blake, PMP |  |  | 20 |  | 3 |  | 4 | 2 |  | 0
Company / Site | ApexNova Consulting / Austin HQ
Reporting Rhythm | Weekly governance every Monday
|  |  |  | Overdue |  | On-Time Close % |  | Critical Items
|  |  |  | 17 |  | 100% |  | 4
Backlog |  | Ready |  | In Progress |  | Review |  | Blocked | Done |  | PM ALERTS
4 tasks WIP Limit: No limit Approved scope waiting to be prepared |  | 4 tasks WIP Limit: 6 Prioritized work cleared to start |  | 4 tasks WIP Limit: 4 Active execution underway |  | 3 tasks WIP Limit: 3 QA / sign-off in progress |  | 2 tasks WIP Limit: 0 target Dependency or issue is stopping flow | 3 tasks WIP Limit: N/A Completed and formally closed |  | WIP level acceptable
Escalate blockers to sponsor / vendor
0 items due in next 7 days
Use the KPI cards and lane counts to rebalance ownership, remove blockers, and keep work moving left to right without overloading the team.
STATUS SUMMARY |  |  |  |  | ASSIGNEE WORKLOAD |  |  |  | PRIORITY MIX
Status | Task Count | Share % | Interpretation |  | Assignee | Open Tasks | Done Tasks | Site | Priority | Task Count | Open Items | PM Attention
Backlog | 4 | 20% | Future pipeline |  | Olivia Chen | 2 | 0 | Austin HQ | Critical | 4 | 4 | Immediate sponsor visibility
Ready | 4 | 20% | Start-ready scope |  | Marcus Reed | 2 | 0 | Austin HQ | High | 7 | 6 | Weekly check required
In Progress | 4 | 20% | Active execution |  | Sofia Martinez | 1 | 1 | Chicago Studio | Medium | 6 | 5 | Monitor flow
Review | 3 | 15% | Awaiting sign-off |  | Ethan Brooks | 2 | 0 | Denver Hub | Low | 3 | 2 | As capacity allows
Blocked | 2 | 10% | Needs intervention |  | Priya Nair | 1 | 0 | Austin HQ
Done | 3 | 15% | Delivered output |  | Noah Patel | 1 | 1 | Denver Hub
[5 empty] | Ava Thompson | 2 | 0 | Seattle Lab
[5 empty] | Liam Walker | 2 | 0 | New York Office
What this template explains: task status, workflow stages, workload distribution, priorities, bottlenecks, deadlines, accountability, progress monitoring, and continuous improvement — all from a project manager's point of view.
Note on A1: Designed as an executive-quality Kanban board template for project delivery control.

## Data Entry
Task ID | Initiative | Task Name | Description | Department | Site | Assignee | Status | Priority | Start Date | Due Date | Completion % | WIP Lane | Blocker | Completed Date | Days Left | Schedule Health | Owner Load | Notes
KNB-001 | CRM Rollout | Map current sales workflow | Document lead lifecycle for redesign | Sales Ops | Austin HQ | Olivia Chen | Backlog | High | 2026-03-24 | 2026-04-03 | 0% | Backlog |  |  | -12 | Overdue | 2 | Waiting for stakeholder interviews
KNB-002 | CRM Rollout | Create migration checklist | Prepare data migration controls | PMO | Austin HQ | Marcus Reed | Ready | High | 2026-03-25 | 2026-04-01 | 10% | Ready |  |  | -14 | Overdue | 2 | Dependencies cleared; ready to start
KNB-003 | Website Refresh | Draft new homepage copy | Refresh brand messaging for launch | Marketing | Chicago Studio | Sofia Martinez | In Progress | Medium | 2026-03-20 | 2026-03-31 | 55% | In Progress |  |  | -15 | Overdue | 2 | Awaiting final legal disclaimer
KNB-004 | Warehouse Upgrade | Validate scanner devices | Test handheld devices on floor | Operations | Denver Hub | Ethan Brooks | Review | High | 2026-03-18 | 2026-03-29 | 90% | Review |  |  | -17 | Overdue | 2 | QA sign-off scheduled Monday
KNB-005 | CRM Rollout | Resolve duplicate accounts | Clean customer master data | Data Team | Austin HQ | Priya Nair | Blocked | Critical | 2026-03-19 | 2026-03-28 | 40% | Blocked | Awaiting vendor export fix |  | -18 | Overdue | 1 | External dependency with DataBridge Systems
KNB-006 | Warehouse Upgrade | Publish training guide | Finalize floor supervisor handbook | Operations | Denver Hub | Noah Patel | Done | Medium | 2026-03-10 | 2026-03-21 | 100% | Done |  | 2026-03-20 |  | On Time | 2 | Completed one day early
KNB-007 | Customer Portal | Design password reset flow | Improve self-service recovery journey | Product | Seattle Lab | Ava Thompson | Ready | Medium | 2026-03-26 | 2026-04-04 | 15% | Ready |  |  | -11 | Overdue | 2 | UX approved wireframes
KNB-008 | Finance Close | Reconcile AP exceptions | Close out unmatched invoices | Finance | New York Office | Liam Walker | In Progress | High | 2026-03-21 | 2026-03-30 | 65% | In Progress |  |  | -16 | Overdue | 2 | Controller review required
KNB-009 | Website Refresh | Approve image library | Select final campaign visuals | Creative | Chicago Studio | Maya Johnson | Backlog | Low | 2026-03-27 | 2026-04-08 | 0% | Backlog |  |  | -7 | Overdue | 2 | Pending executive moodboard feedback
KNB-010 | Customer Portal | Create API error log | Track failed calls with root cause tags | Engineering | Seattle Lab | Daniel Kim | Review | Medium | 2026-03-17 | 2026-03-28 | 85% | Review |  |  | -18 | Overdue | 1 | Code merged; needs UAT evidence
KNB-011 | CRM Rollout | Set user permission matrix | Align roles for regional teams | IT Admin | Austin HQ | Olivia Chen | In Progress | High | 2026-03-23 | 2026-04-02 | 45% | In Progress |  |  | -13 | Overdue | 2 | Security team reviewing edge cases
KNB-012 | Finance Close | Update month-end checklist | Add automation verification steps | Finance | New York Office | Harper Lewis | Done | Low | 2026-03-08 | 2026-03-19 | 100% | Done |  | 2026-03-18 |  | On Time | 1 | Completed ahead of deadline
KNB-013 | Warehouse Upgrade | Mark safety floor zones | Paint and inspect high-traffic paths | Facilities | Denver Hub | Ethan Brooks | Ready | Critical | 2026-03-25 | 2026-03-30 | 20% | Ready |  |  | -16 | Overdue | 2 | Materials delivered on site
KNB-014 | Customer Portal | Review accessibility findings | Address contrast and label issues | QA | Seattle Lab | Grace Turner | Blocked | High | 2026-03-22 | 2026-03-27 | 35% | Blocked | Need vendor VPAT confirmation |  | -19 | Overdue | 1 | Accessibility vendor delayed response
KNB-015 | Website Refresh | Finalize SEO redirect map | Prevent broken links at go-live | Marketing | Chicago Studio | Sofia Martinez | Done | High | 2026-03-11 | 2026-03-25 | 100% | Done |  | 2026-03-24 |  | On Time | 2 | No broken links in smoke test
KNB-016 | CRM Rollout | Build executive dashboard | Create renewal and pipeline KPIs | BI Team | Austin HQ | Marcus Reed | Backlog | Medium | 2026-03-27 | 2026-04-10 | 0% | Backlog |  |  | -5 | Overdue | 2 | Awaiting approved KPI definitions
KNB-017 | Finance Close | Validate posting rules | Check automation for edge entries | Finance Systems | New York Office | Liam Walker | In Progress | Critical | 2026-03-24 | 2026-03-29 | 60% | In Progress |  |  | -17 | Overdue | 2 | Requires overnight test cycle
KNB-018 | Warehouse Upgrade | Review loading dock signage | Confirm compliance wording | Facilities | Denver Hub | Noah Patel | Review | Low | 2026-03-16 | 2026-03-30 | 75% | Review |  |  | -16 | Overdue | 2 | Compliance comments resolved
KNB-019 | Customer Portal | Write release notes | Communicate customer-facing changes | Product Marketing | Seattle Lab | Ava Thompson | Backlog | Medium | 2026-03-28 | 2026-04-06 | 0% | Backlog |  |  | -9 | Overdue | 2 | Needs final list of shipped stories
KNB-020 | Website Refresh | Launch readiness review | Cross-functional go-live checkpoint | PMO | Chicago Studio | Maya Johnson | Ready | Critical | 2026-03-26 | 2026-03-31 | 30% | Ready |  |  | -15 | Overdue | 2 | Leadership review booked
Formulas:
Days Left = IF(OR([Status]="Done",[Due Date]=""),"",[Due Date]-TODAY())
Schedule Health = IF([Status]="Done",IF(AND([Completed Date]<>"",[Completed Date]<=[Due Date]),"On Time","Late"),IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=3,"At Risk","On Track")))
Note on A1: Enter one task per row. Replace the sample data with your own project tasks.

## Instructions
KANBAN BOARD TEMPLATE – HOW TO USE
1. Purpose | Color / Meaning
This workbook helps a project manager visualize workflow, control work-in-progress, identify bottlenecks, and keep deadlines visible. It is built around a realistic fictional program at ApexNova Consulting. | Backlog
Ready
In Progress
Review
2. Data Entry process | Blocked
Use the 'Data Entry' sheet for all task updates. Each row is one task. Update assignee, status, priority, dates, completion %, blockers, and notes. Keep naming consistent and use the dropdown lists. | Done
Critical Priority
| High Priority | Backlog | Critical | Backlog
|  | Ready | High | Ready
3. Workflow stages explained |  | In Progress | Medium | In Progress
Backlog = approved but not yet ready. Ready = fully planned and cleared to start. In Progress = active execution. Review = waiting for QA, manager, or stakeholder sign-off. Blocked = cannot continue because of a dependency or issue. Done = completed and closed. |  | Review | Low | Review
|  | Blocked |  | Blocked
|  | Done |  | Done
4. Metrics explained
The Kanban Board sheet shows total work, completed work, active work, blocked items, due-soon work, overdue work, on-time close rate, workload by owner, and priority mix. These metrics help with flow management and decision-making.
5. Operating rhythm
Daily stand-up: update task status and blockers. Weekly governance: review overdue items, WIP balance, and due-soon tasks. Retrospective: look for bottlenecks and rebalance ownership or WIP limits.
6. Good PM practices
Keep WIP low. Move tasks to Blocked immediately when stalled. Use due dates that reflect real commitments. Close done items promptly. Write blocker notes with the next action and owner.