## PERT Master Template
PERT Chart
Executive Planning Dashboard • Northwind Aero Logistics • Project Apollo Nexus ERP Rollout
| Project Start |  |  |  | Project Finish |  |  |  | Project Duration (days) |  |  |  | Critical Tasks |  |  |  | Total Tasks |  |  |  | PERT highlights
| 2026-04-06 |  |  |  | 2026-05-08 |  |  |  | 32 |  |  |  | 6 |  |  |  | 10 |  |  |  | • Three-point estimating captures uncertainty using Optimistic, Most Likely, and Pessimistic durations.
• Early / Late dates quantify sequencing flexibility and expose schedule risk.
• Zero-slack tasks are flagged as Critical to focus executive attention on schedule protection.
PERT schedule engine | [17 empty] | Visual timeline (days from project start)
Task ID | Task Name | Predecessor | Owner | Location | O | M | P | Expected | Sched. Dur. | ES | EF | LS | LF | Slack | Status | Plan Start | Plan Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
AN-01 | Executive Kickoff & Charter Sign-off |  | Daniel Mercer | Chicago HQ | 2 | 3 | 4 | 3 | 3 | 0 | 3 | 0 | 3 | 0 | Critical | 2026-04-06 | 2026-04-09 | bar: Visual timeline (days from project start) 1 to Visual timeline (days from project start) 3
AN-02 | Requirements Blueprint | AN-01 | Priya Raman | Austin Hub | 5 | 7 | 10 | 7 | 8 | 3 | 11 | 14 | 22 | 11 | Monitor | 2026-04-09 | 2026-04-17 | bar: Visual timeline (days from project start) 4 to Visual timeline (days from project start) 11
AN-03 | Infrastructure & Security Setup | AN-01 | Luis Ortega | Phoenix DC | 4 | 6 | 8 | 6 | 6 | 3 | 9 | 3 | 9 | 0 | Critical | 2026-04-09 | 2026-04-15 | bar: Visual timeline (days from project start) 4 to Visual timeline (days from project start) 9
AN-04 | Data Migration Design | AN-02 | Olivia Chen | Dallas Ops | 3 | 5 | 7 | 5 | 5 | 11 | 16 | 22 | 27 | 11 | Monitor | 2026-04-17 | 2026-04-22 | bar: Visual timeline (days from project start) 12 to Visual timeline (days from project start) 16
AN-05 | Integration Build | AN-03 | Noah Bennett | Austin Hub | 6 | 9 | 12 | 9 | 9 | 9 | 18 | 9 | 18 | 0 | Critical | 2026-04-15 | 2026-04-24 | bar: Visual timeline (days from project start) 10 to Visual timeline (days from project start) 18
AN-06 | User Training Package | AN-02 | Emma Sinclair | Chicago HQ | 2 | 4 | 5 | 4 | 4 | 11 | 15 | 28 | 32 | 17 | Monitor | 2026-04-17 | 2026-04-21 | bar: Visual timeline (days from project start) 12 to Visual timeline (days from project start) 15
AN-07 | Conference Room Pilot | AN-04 | James Holloway | Dallas Ops | 3 | 4 | 6 | 4 | 5 | 16 | 21 | 27 | 32 | 11 | Monitor | 2026-04-22 | 2026-04-27 | bar: Visual timeline (days from project start) 17 to Visual timeline (days from project start) 21
AN-08 | UAT & Defect Triage | AN-05 | Sofia Alvarez | Austin Hub | 5 | 8 | 10 | 8 | 8 | 18 | 26 | 18 | 26 | 0 | Critical | 2026-04-24 | 2026-05-02 | bar: Visual timeline (days from project start) 19 to Visual timeline (days from project start) 26
AN-09 | Cutover Rehearsal | AN-08 | Henry Cole | Phoenix DC | 2 | 3 | 5 | 3 | 4 | 26 | 30 | 26 | 30 | 0 | Critical | 2026-05-02 | 2026-05-06 | bar: Visual timeline (days from project start) 27 to Visual timeline (days from project start) 30
AN-10 | Go-Live & Hypercare Launch | AN-09 | Ava Kingsley | Chicago HQ | 1 | 2 | 3 | 2 | 2 | 30 | 32 | 30 | 32 | 0 | Critical | 2026-05-06 | 2026-05-08 | bar: Visual timeline (days from project start) 31 to Visual timeline (days from project start) 32
Legend | [6 empty] | Status | Count
| Critical path bar | [5 empty] | Critical | 6
| Non-critical / float available | [5 empty] | Monitor | 4
User-facing inputs
Schedule metrics / formulas
Note on I9: PERT expected duration = (Optimistic + 4 × Most Likely + Pessimistic) / 6
Note on O9: Slack = Late Start - Early Start. Zero slack indicates the critical path.

## Data Entry
Northwind Aero Logistics
Project Apollo Nexus ERP Rollout — PERT Data Entry
Project Start Date | 2026-04-06 |  | Program Director | Daniel Mercer
Sponsor | Megan Hart, COO |  | Primary Site | Chicago HQ
Task ID | Workstream | Task Name | Owner | Location | Predecessor ID | Optimistic (days) | Most Likely (days) | Pessimistic (days) | Milestone? | Notes
AN-01 | Mobilize | Executive Kickoff & Charter Sign-off | Daniel Mercer | Chicago HQ |  | 2 | 3 | 4 | N | Launch governance, cadence, and approval authority
AN-02 | Design | Requirements Blueprint | Priya Raman | Austin Hub | AN-01 | 5 | 7 | 10 | N | Confirm process maps for order-to-cash and procure-to-pay
AN-03 | Technology | Infrastructure & Security Setup | Luis Ortega | Phoenix DC | AN-01 | 4 | 6 | 8 | N | Provision cloud tenants, SSO, and firewall rules
AN-04 | Data | Data Migration Design | Olivia Chen | Dallas Ops | AN-02 | 3 | 5 | 7 | N | Define source mapping, cleansing logic, and mock-load controls
AN-05 | Technology | Integration Build | Noah Bennett | Austin Hub | AN-03 | 6 | 9 | 12 | N | Build CRM, WMS, and finance interfaces
AN-06 | Change | User Training Package | Emma Sinclair | Chicago HQ | AN-02 | 2 | 4 | 5 | N | Role-based quick guides and classroom content
AN-07 | Pilot | Conference Room Pilot | James Holloway | Dallas Ops | AN-04 | 3 | 4 | 6 | N | Walk through end-to-end scenarios with super users
AN-08 | Quality | UAT & Defect Triage | Sofia Alvarez | Austin Hub | AN-05 | 5 | 8 | 10 | N | Business validation and severity-based fix cycles
AN-09 | Cutover | Cutover Rehearsal | Henry Cole | Phoenix DC | AN-08 | 2 | 3 | 5 | N | Dry run cutover steps, rollback, and command center coverage
AN-10 | Release | Go-Live & Hypercare Launch | Ava Kingsley | Chicago HQ | AN-09 | 1 | 2 | 3 | Y | Milestone launch and 14-day hypercare handoff
Editing guidance | Update only blue/green shaded input cells and add new tasks beneath row 17 if your real project is larger.

## Instructions
Instructions — PERT Chart Template
Built for a senior project manager’s scheduling workflow: estimate uncertainty, visualize dependencies, and identify the critical path.
1) What this template explains
• | Task sequencing: every activity can reference a predecessor so you can see the order of execution.
• | Three-point estimation: optimistic, most likely, and pessimistic durations drive the PERT expected duration.
• | Critical path logic: tasks with zero slack are automatically flagged as Critical.
• | Schedule flexibility: Early Start/Finish and Late Start/Finish expose float and sequencing risk.
• | Date-based planning: the dashboard converts day offsets into calendar dates from the project start date.
• | Visual communication: the timeline acts as an executive-ready schedule summary for steering meetings.
2) How to use the workbook
Step 1 | Go to the Data Entry sheet and replace the sample project metadata (sponsor, program director, start date) if needed.
Step 2 | Update each task row with your own Task ID, predecessor, and three-point estimates. Keep tasks in logical sequence from earliest to latest.
Step 3 | Review the PERT Master Template sheet. Expected durations, schedule dates, slack, and critical path status calculate automatically.
Step 4 | Use the visual timeline and charts in sponsor updates, gate reviews, and weekly PMO status meetings.
Step 5 | Add more task rows by copying the last completed row in both Data Entry and the main template if your project exceeds 10 tasks.
3) Field-by-field reference
Field | Meaning
Predecessor ID | The task that must finish before the current task can begin.
Optimistic / Most Likely / Pessimistic | Best case, expected case, and worst case duration estimates in days.
Expected | PERT weighted duration: (O + 4M + P) / 6.
ES / EF | Early Start and Early Finish.
LS / LF | Late Start and Late Finish.
Slack | Difference between Late Start and Early Start.
Status | Critical or Monitor.
4) Color system
| #1F3A5F / #2F5597 | Executive headers and section bands
| #548235 / #70AD47 / #92D050 | Process, positive flow, timeline, and schedule confidence
| #ED7D31 / #FFC000 | Instructions, callouts, and review prompts
| #C00000 | Critical path, executive attention, and risk
| #4472C4 | Input accents and supporting visuals
Pro tip | For portfolio-level reporting, copy the main sheet structure per project and standardize the start date, status rules, and task coding format.