## PMO Budget Dashboard
PMO Budget
Portfolio Office for 2026 Strategic Programs ¦ Head Office: Meridian City ¦ Prepared by: Elena Park, Senior PMO Manager
Portfolio Controls |  |  |  | KPI Dashboard | [7 empty] | Status & Forecast
Company | Aurelia Infrastructure Group | PMO Director | Jordan Whitmore | Total Planned Budget |  | Approved Budget |  | Actual Spend |  | Remaining Budget |  | Contingency Reserve
PMO Region | North America Capital Delivery | Report Owner | Elena Park | 4425000 |  | 4290000 |  | 3028000 |  | 1262000 |  | 225000
Budget Year | 2026 | Portfolio Count | 10
Currency | USD | Latest Refresh | 2026-04-15 | Forecast at Completion |  | Variance vs Approved |  | Budget Utilization % |  | Projects Over Budget |  | Risk Exposure
|  |  |  | 4422000 |  | 132000 |  | 70.58% |  | 1 |  | 180000
Vendor Spend
1858000
Internal Labor Spend
1170000
Project / Program | Sponsor | Location | Resourcing | Funding Source | Planned Budget | Approved Budget | Actual Spend | Forecast EAC | Contingency | Risk Exposure | Variance | Status | Spend % | Notes
Atlas ERP Modernization | Olivia Chen | Chicago | Internal | Corporate PMO | 650000 | 620000 | 415000 | 638000 | 35000 | 18000 | 18000 | On Track | 66.94% | Core ERP upgrade across finance and procurement
Northwind Plant Expansion PMO | Marcus Hale | Denver | Vendor | Capital Program | 820000 | 800000 | 602000 | 845000 | 40000 | 52000 | 45000 | At Risk | 75.25% | Schedule pressure due to steel package delays
Helios Cybersecurity Uplift | Priya Raman | Austin | Internal | Operations | 390000 | 385000 | 246000 | 382000 | 22000 | 12000 | -3000 | On Track | 63.9% | Control tower and identity governance rollout
Lakehurst Warehouse Automation | Daniel Brooks | Phoenix | Vendor | Innovation Fund | 540000 | 525000 | 431000 | 566000 | 25000 | 34000 | 41000 | Over Budget | 82.1% | Robotics integration vendor change order
Meridian HQ Workspace Refit | Sofia Alvarez | Meridian City | Internal | Operations | 210000 | 205000 | 121000 | 198000 | 15000 | 8000 | -7000 | On Track | 59.02% | PMO-led move planning and change communications
Orion Data Lake Program | Liam Carter | Toronto | Vendor | Corporate PMO | 730000 | 710000 | 488000 | 726000 | 30000 | 16000 | 16000 | On Track | 68.73% | Data platform, governance and migration wave 1
Aegis Field Mobility Rollout | Nora Bennett | Seattle | Internal | Capital Program | 315000 | 300000 | 214000 | 308000 | 18000 | 10000 | 8000 | On Track | 71.33% | Tablet deployment and work management enablement
Aurora Sustainability Reporting | Ethan Wells | Boston | Internal | Innovation Fund | 185000 | 175000 | 98000 | 169000 | 12000 | 6000 | -6000 | On Track | 56% | ESG reporting process design and dashboard support
Pioneer Customer Portal Rebuild | Maya Singh | Atlanta | Vendor | Corporate PMO | 460000 | 450000 | 337000 | 472000 | 20000 | 21000 | 22000 | At Risk | 74.89% | UX scope growth and delayed UAT readiness
Summit Leadership Academy | Grace Turner | San Diego | Internal | Operations | 125000 | 120000 | 76000 | 118000 | 8000 | 3000 | -2000 | On Track | 63.33% | Portfolio governance and delivery capability academy
Portfolio Totals |  |  |  |  | 4425000 | 4290000 | 3028000 | 4422000 | 225000 | 180000 |  |  | 70.58%
Category Summary |  |  | Monthly Spend Trend
Cost Category | Actual Spend |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Internal Labor | 246000 | Portfolio | 261000 | 267000 | 263000 | 251500 | 250700 | 236300 | 240000 | 242500 | 232500 | 190000 | 0 | 0
Software & Tools | 903000
Training | 174000 |  | Monthly Spend Trend Oct: Governance & Financial Control
Travel | 121000 |  | Monthly Spend Trend Oct: Approved Revisions; Monthly Spend Trend Nov: 10
External Consulting | 939000 |  | Monthly Spend Trend Oct: At-Risk Projects; Monthly Spend Trend Nov: 2
Equipment | 645000 |  | Monthly Spend Trend Oct: Average Utilization; Monthly Spend Trend Nov: 68.15%
[12 empty] | Forecast Overrun | 132000
[12 empty] | Top Issue | Vendor rates rising in Lakehurst rollout
[12 empty] | Next Review | 15-Apr-2026
[9 empty] | Corporate PMO | 1780000
[9 empty] | Capital Program | 1100000
[9 empty] | Operations | 710000
[9 empty] | Innovation Fund | 700000

## Data Entry
Data Entry Sheet ¦ Hypothetical Portfolio Data
Edit blue-text input cells only. Linked formulas on the dashboard update automatically.
Project-Level Inputs | [5 empty] | Budget & Controls | [7 empty] | Monthly Actual Spend Inputs
Project / Program | Sponsor | Location | Resourcing | Funding Source | Planned Budget | Approved Budget | Actual Spend | Forecast EAC | Contingency | Risk Exposure | Cost Category | Status | Notes | Jan | Revision Ref | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Atlas ERP Modernization | Olivia Chen | Chicago | Internal | Corporate PMO | 650000 | 620000 | 415000 | 638000 | 35000 | 18000 | Software & Tools | On Track | Core ERP upgrade across finance and procurement | 34000 | REV-014 | 36000 | 31000 | 37000 | 39000 | 34000 | 33000 | 35000 | 32000 | 0 | 0 | 0
Northwind Plant Expansion PMO | Marcus Hale | Denver | Vendor | Capital Program | 820000 | 800000 | 602000 | 845000 | 40000 | 52000 | External Consulting | At Risk | Schedule pressure due to steel package delays | 52000 | REV-011 | 48000 | 53000 | 50000 | 51000 | 48000 | 50000 | 52000 | 49000 | 47000 | 0 | 0
Helios Cybersecurity Uplift | Priya Raman | Austin | Internal | Operations | 390000 | 385000 | 246000 | 382000 | 22000 | 12000 | Internal Labor | On Track | Control tower and identity governance rollout | 21000 | REV-008 | 23000 | 22000 | 20000 | 19000 | 21000 | 18000 | 20000 | 17000 | 16500 | 0 | 0
Lakehurst Warehouse Automation | Daniel Brooks | Phoenix | Vendor | Innovation Fund | 540000 | 525000 | 431000 | 566000 | 25000 | 34000 | Equipment | Over Budget | Robotics integration vendor change order | 41000 | REV-012 | 39000 | 42000 | 35000 | 36000 | 32000 | 34000 | 36000 | 38000 | 34000 | 0 | 0
Meridian HQ Workspace Refit | Sofia Alvarez | Meridian City | Internal | Operations | 210000 | 205000 | 121000 | 198000 | 15000 | 8000 | Travel | On Track | PMO-led move planning and change communications | 9000 | REV-005 | 11000 | 12000 | 10000 | 10000 | 9000 | 11000 | 12000 | 10000 | 8000 | 0 | 0
Orion Data Lake Program | Liam Carter | Toronto | Vendor | Corporate PMO | 730000 | 710000 | 488000 | 726000 | 30000 | 16000 | Software & Tools | On Track | Data platform, governance and migration wave 1 | 44000 | REV-009 | 45000 | 43000 | 41000 | 39000 | 37000 | 38000 | 36000 | 35000 | 34000 | 0 | 0
Aegis Field Mobility Rollout | Nora Bennett | Seattle | Internal | Capital Program | 315000 | 300000 | 214000 | 308000 | 18000 | 10000 | Equipment | On Track | Tablet deployment and work management enablement | 17000 | REV-006 | 18000 | 16000 | 17000 | 15000 | 16000 | 17000 | 15000 | 14000 | 14000 | 0 | 0
Aurora Sustainability Reporting | Ethan Wells | Boston | Internal | Innovation Fund | 185000 | 175000 | 98000 | 169000 | 12000 | 6000 | Training | On Track | ESG reporting process design and dashboard support | 8000 | REV-004 | 9000 | 8000 | 7000 | 8500 | 7500 | 8000 | 7000 | 6500 | 6500 | 0 | 0
Pioneer Customer Portal Rebuild | Maya Singh | Atlanta | Vendor | Corporate PMO | 460000 | 450000 | 337000 | 472000 | 20000 | 21000 | External Consulting | At Risk | UX scope growth and delayed UAT readiness | 29000 | REV-010 | 31000 | 30000 | 28000 | 27000 | 26000 | 25000 | 24000 | 26000 | 25000 | 0 | 0
Summit Leadership Academy | Grace Turner | San Diego | Internal | Operations | 125000 | 120000 | 76000 | 118000 | 8000 | 3000 | Training | On Track | Portfolio governance and delivery capability academy | 6000 | REV-003 | 7000 | 6000 | 6500 | 6200 | 5800 | 6000 | 5500 | 5000 | 5000 | 0 | 0
Validation checks
Total planned budget | 4425000 |  | Projects marked Over Budget | 1
Total approved budget | 4290000 |  | Projects marked At Risk | 2
Total actual spend | 3028000 |  | Portfolio contingency | 225000
Total forecast EAC | 4422000 |  | Portfolio risk exposure | 180000
Note on F6: Planned baseline budget before approval. Example figures are hypothetical.
Note on G6: Approved funding after governance review.
Note on I6: Estimated final cost at completion (EAC).
Note on P6: Internal revision / approval reference ID for realism.

## Instructions
Instructions ¦ How to Use This PMO Budget Template
Designed from a senior PMO manager perspective for portfolio planning, tracking, control and executive reporting.
Step | Area | Instruction
1 | Purpose | This workbook is a PMO budget planning and control model. It covers budget overview, project-wise allocations, planned vs actual spend, forecasting, contingency, risk exposure, cost category tracking, monthly trend analysis, and governance controls.
2 | Where to enter data | Use the 'Data Entry' sheet for all manual changes. The dashboard sheet is formula-driven and intended for leadership reporting.
3 | Blue text cells | Blue-font input cells are meant for user updates. Example: budgets, actuals, forecasts, contingency, risk exposure, and monthly actuals.
4 | Dropdown fields | Use the built-in dropdowns for Resourcing, Funding Source, Cost Category, and Status so that dashboard calculations stay consistent.
5 | Main KPIs explained | The dashboard shows Total Planned Budget, Approved Budget, Actual Spend, Remaining Budget, Forecast at Completion, Variance vs Approved, Budget Utilization %, and Projects Over Budget.
6 | Variance logic | Variance is calculated as Forecast at Completion minus Approved Budget. Positive variance means projected overrun; negative variance means projected savings.
7 | Budget utilization | Spend % is Actual Spend divided by Approved Budget. Orange highlights indicate utilization above 90%; red variance highlights indicate projected overruns.
8 | Monthly analysis | Enter monthly actual spend in Jan–Dec columns. The dashboard trend chart aggregates all project rows to show portfolio burn pattern over the year.
9 | Cost category reporting | Each project has one primary cost category for executive reporting. You can adapt this to multiple categories if your organization tracks budget at a more granular work-package level.
10 | Funding sources | The sample template uses hypothetical funding sources: Corporate PMO, Capital Program, Operations, and Innovation Fund. Replace them with your actual cost centers if needed.
11 | Governance controls | Use the Revision Ref column to store board, CAB, or steering committee approval references. The governance panel summarizes revision count, at-risk projects, and next review date.
12 | How to extend | To add more projects, copy row 16 downward in Data Entry and the linked row 28 downward in Dashboard. Keep formulas and formatting aligned.
13 | Best practice | Update Actual Spend monthly, refresh Forecast EAC with PM input, review contingency sufficiency, and discuss any project with status At Risk or Over Budget in the monthly governance forum.
14 | Disclaimer | All company names, project names, people, locations, and budget figures in this workbook are hypothetical and created for demonstration purposes.
Legend | Blue text | Manual input cells / editable fields
| Green/gray cells | Linked summaries and reporting sections
| Orange highlight | Caution / high utilization / at-risk discussion point
| Red highlight | Overrun / issue requiring action