## PMO Financial Statement
PMO Financial Statement
Portfolio owner: Enterprise Transformation PMO ¦ Reporting period: FY2026 ¦ HQ: Harbor Point, Illinois
Portfolio Controls & Assumptions | [6 empty] | Total Approved Budget |  |  | Actual Spend YTD |  |  | Committed Cost |  |  | Forecast at Completion
Reporting Month | Mar-26
Portfolio Currency | USD | [5 empty] | 14155000 |  |  | 6655000 |  |  | 1960000 |  |  | 14565000
PMO Lead | Elena Whitmore | [5 empty] | Remaining Budget |  |  | Portfolio Variance |  |  | Reserve Utilization |  |  | Portfolio Health
Finance Business Partner | Marcus Hale
Reserve Policy | 5.0% | [5 empty] | 5540000 |  |  | -410000 |  |  | 49.52% |  |  | AT RISK
Project Portfolio Financial Summary | [10 empty] | Cost Category Statement
Project | Sponsor | Region | Stage | Approved Budget | Actual Spend | Committed Cost | Forecast EAC | Variance | Budget Utilization % |  | Category | Budget | Actual | Committed | Forecast | Variance | Share of Budget
Orion ERP Modernization | Nadia Cross | North America | Execution | 4200000 | 1980000 | 640000 | 4380000 | -180000 | 47.14% |  | Labor | 5200000 | 2610000 | 770000 | 5335000 | -135000 | 39.5%
Harbor Analytics Hub | Daniel Reeves | EMEA | Execution | 2750000 | 1465000 | 320000 | 2685000 | 65000 | 53.27% |  | Software | 1850000 | 1010000 | 265000 | 1880000 | -30000 | 14.05%
Crescent Cyber Uplift | Priya Sethi | APAC | Execution | 1950000 | 1015000 | 180000 | 2080000 | -130000 | 52.05% |  | Hardware | 920000 | 455000 | 118000 | 948000 | -28000 | 6.988%
Atlas Procurement Cloud | Miguel Santos | Latin America | Planning | 1650000 | 420000 | 260000 | 1715000 | -65000 | 25.45% |  | Vendors | 2350000 | 1195000 | 495000 | 2510000 | -160000 | 17.85%
Nova HR Experience | Laura Bennett | North America | Execution | 1325000 | 655000 | 150000 | 1290000 | 35000 | 49.43% |  | Training | 380000 | 145000 | 18000 | 355000 | 25000 | 2.886%
Westhaven Plant Mobility | Omar El-Karim | Europe | Execution | 2280000 | 1120000 | 410000 | 2415000 | -135000 | 49.12% |  | Travel | 210000 | 69000 | 12000 | 176000 | 34000 | 1.595%
Portfolio Total |  |  |  | 14155000 | 6655000 | 1960000 | 14565000 | -410000 | 47.02% |  | Overhead | 640000 | 278000 | 42000 | 628000 | 12000 | 4.861%
[11 empty] | Contingency | 1615000 | 893000 | 240000 | 1731000 | -116000 | 12.27%
[11 empty] | Category Total | 13165000 | 6655000 | 1960000 | 13563000 | -398000 | 100%
Monthly Spend, Commitments & Forecast Trend
Month | Budget Phased | Actual Spend | Committed Cost | Forecast EAC | [6 empty] | Executive Financial Commentary
2026-01-01 | 950000 | 865000 | 110000 | 975000 | [6 empty] | Forecast at completion shows moderate pressure driven by accelerator vendors and accelerated rollout in Westhaven.
2026-02-01 | 1025000 | 978000 | 128000 | 1030000 | [6 empty] | Reserve utilization is tracked against approved portfolio risk reserve. Values above 75% should trigger steering committee review.
2026-03-01 | 1100000 | 812000 | 95000 | 1085000 | [6 empty] | Budget variance highlights where scope changes, delivery delays, or procurement decisions are affecting plan.
2026-04-01 | 1180000 | 0 | 142000 | 1175000 | [6 empty] | Use the Data Entry sheet to replace hypothetical figures with live project financials.
2026-05-01 | 1200000 | 0 | 150000 | 1205000
2026-06-01 | 1225000 | 0 | 152000 | 1240000
2026-07-01 | 1250000 | 0 | 155000 | 1260000
2026-08-01 | 1275000 | 0 | 160000 | 1280000
2026-09-01 | 1300000 | 0 | 165000 | 1310000
2026-10-01 | 1325000 | 0 | 170000 | 1335000
2026-11-01 | 1350000 | 0 | 175000 | 1360000
2026-12-01 | 1375000 | 0 | 180000 | 1390000

## Data Entry
PMO Financial Data Entry
Enter or replace the hypothetical financial values below. Blue text = user input. Green text = values linked by the main report. Black text = formulas.
Project Level Inputs | [11 empty] | Cost Category Inputs
ID | Project Name | Sponsor | Region | Stage | Approved Budget | Actual Spend YTD | Committed Cost | Forecast EAC | Risk Reserve | Reserve Used |  | Budget | Actual | Committed | Forecast
1 | Orion ERP Modernization | Nadia Cross | North America | Execution | 4200000 | 1980000 | 640000 | 4380000 | 210000 | 102000 | Labor | 5200000 | 2610000 | 770000 | 5335000
2 | Harbor Analytics Hub | Daniel Reeves | EMEA | Execution | 2750000 | 1465000 | 320000 | 2685000 | 137500 | 54000 | Software | 1850000 | 1010000 | 265000 | 1880000
3 | Crescent Cyber Uplift | Priya Sethi | APAC | Execution | 1950000 | 1015000 | 180000 | 2080000 | 97500 | 72000 | Hardware | 920000 | 455000 | 118000 | 948000
4 | Atlas Procurement Cloud | Miguel Santos | Latin America | Planning | 1650000 | 420000 | 260000 | 1715000 | 82500 | 12000 | Vendors | 2350000 | 1195000 | 495000 | 2510000
5 | Nova HR Experience | Laura Bennett | North America | Execution | 1325000 | 655000 | 150000 | 1290000 | 66250 | 24500 | Training | 380000 | 145000 | 18000 | 355000
6 | Westhaven Plant Mobility | Omar El-Karim | Europe | Execution | 2280000 | 1120000 | 410000 | 2415000 | 114000 | 86000 | Travel | 210000 | 69000 | 12000 | 176000
[11 empty] | Overhead | 640000 | 278000 | 42000 | 628000
Monthly Portfolio Trend Inputs | [10 empty] | Contingency | 1615000 | 893000 | 240000 | 1731000
ID | Month | Budget Phased | Actual Spend | Committed Cost | Forecast EAC | Burn Rate %
1 | 2026-01-01 | 950000 | 865000 | 110000 | 975000 | 91.05%
2 | 2026-02-01 | 1025000 | 978000 | 128000 | 1030000 | 95.41%
3 | 2026-03-01 | 1100000 | 812000 | 95000 | 1085000 | 73.82%
4 | 2026-04-01 | 1180000 | 0 | 142000 | 1175000 | 0%
5 | 2026-05-01 | 1200000 | 0 | 150000 | 1205000 | 0%
6 | 2026-06-01 | 1225000 | 0 | 152000 | 1240000 | 0%
7 | 2026-07-01 | 1250000 | 0 | 155000 | 1260000 | 0%
8 | 2026-08-01 | 1275000 | 0 | 160000 | 1280000 | 0%
9 | 2026-09-01 | 1300000 | 0 | 165000 | 1310000 | 0%
10 | 2026-10-01 | 1325000 | 0 | 170000 | 1335000 | 0%
11 | 2026-11-01 | 1350000 | 0 | 175000 | 1360000 | 0%
12 | 2026-12-01 | 1375000 | 0 | 180000 | 1390000 | 0%
Note on F6: Hypothetical approved budgets for sample projects of Aurelius Infrastructure Group PMO.
Note on M7: Hypothetical cost category budget mix for demonstration only.
Note on B16: Illustrative FY2026 monthly phasing used to power charts on the main report.

## Instructions
Instructions — PMO Financial Statement Template
Purpose: Provide a portfolio-level financial statement for a PMO with budget, spend, commitments, forecast, reserves, cost categories, and monthly trend reporting.
Step | What to do | Why it matters | Best practice
1 | Replace hypothetical values in the Data Entry sheet. | All visuals and financial statements on the main sheet are linked to these cells. | Update Approved Budget, Actual Spend, Committed Cost, Forecast EAC, Risk Reserve, and Reserve Used first.
2 | Refresh project list and sponsor details. | Keeps executive reporting aligned to the current portfolio. | Use one row per active project; archive closed projects outside the template if needed.
3 | Update category-level costs. | Shows where spend sits across labor, software, vendors, travel, and contingency. | Ensure category totals reconcile with your ERP or cost center reports.
4 | Enter monthly phased plan and actuals. | Enables trend analysis and burn-rate monitoring. | For future months, actual spend may remain zero while forecast continues.
5 | Review KPI cards on the main template. | Confirms portfolio-level financial health at a glance. | Pay particular attention to Forecast EAC, Variance, and Reserve Utilization.
6 | Investigate red or orange flags. | Highlights over-budget risks, exhausted reserves, or overly high utilization. | Projects above 90% utilization or negative variance should be reviewed by PMO governance.
7 | Use commentary section for steering committees. | Provides context behind numbers and decisions. | Summarize drivers such as scope change, vendor acceleration, savings, or schedule shifts.
Template Scope — What this PMO statement explains
• Budget summary and approved funding
• Actual spend to date
• Committed cost not yet paid
• Forecast at completion (EAC)
• Budget variance and remaining budget
• Project-wise breakdown by sponsor, region, and stage
• Cost categories such as labor, software, hardware, vendors, training, travel, overhead, and contingency
• Risk reserve and contingency usage
• Monthly trend and burn rate
• Portfolio financial health for PMO governance and executive review
This workbook is intentionally designed as a polished executive template using fictional company, project, and location names. Replace with your real PMO portfolio details as needed.