## PMO Portfolio Dashboard
PMO Multiple Project
Portfolio view for hypothetical enterprise programs across North America, Europe, Asia-Pacific and the Middle East
Total Projects |  |  | On Track |  |  | At Risk |  |  | Critical | Total Budget | Actual Spend
10 |  |  | 4 |  |  | 4 |  |  | 2 | 9700000 | 5683000
Portfolio Completion |  |  | Budget Consumed |  |  | Open Risks |  |  | Open Issues | Change Requests | Avg Team Size
54.1% |  |  | 58.59% |  |  | 33 |  |  | 46 | 19 | 7.8
Portfolio Health by Project | [5 empty] | Top Portfolio Risks & Actions |  |  |  | Milestones, Spend & Summary
Project | PM | Priority | RAG | % Complete | Budget Var % | Priority Risk | Owner | Trigger | Mitigation Action | Highest Budget Project
Apex Nova ERP | Emma Carter | High | Amber | 48% | -50.59% | Quantum Lab clean-room permit delay | Mason Wright | Authority approval misses April 15 | Escalate via regulatory advisor and fast-track revised package | Quantum Lab Expansion
Helios CRM Rollout | Liam Brooks | High | Green | 55% | -50% | Meridian plant civil works lag | Noah Bennett | Structural steel delivery > 3 weeks late | Re-sequence mechanical installs and mobilize backup contractor
Meridian Plant Upgrade | Olivia Reed | Medium | Red | 69% | -33.1% | Atlas automation vendor integration | Lucas Meyer | API defect rate exceeds tolerance | Stand up daily triage with vendor CTO and add defect burn-down | Most Advanced Project
Orion Data Hub | Maya Patel | High | Amber | 43% | -47.96% | Orion scope expansion | Ethan Cole | Data governance sign-off not frozen | Freeze change window and route new scope to steering committee | Summit PMO Maturity
Vantage HR Cloud | Henry Foster | Medium | Green | 28% | -71.3%
Atlas Warehouse Automation | Grace Turner | High | Amber | 72% | -32.44% |  |  |  |  | Largest Risk Load
Nimbus Finance Reporting | Jack Sullivan | Low | Green | 39% | -61.29% |  |  |  |  | Quantum Lab Expansion
Quantum Lab Expansion | Sofia Alvarez | High | Red | 61% | -33.78%
Echo Cyber Uplift | Isabella Price | Medium | Green | 52% | -47.63% |  |  |  |  | Closest Finish Date
Summit PMO Maturity | Amelia Ross | Medium | Amber | 74% | -32.69% |  |  |  |  | Summit PMO Maturity
Status | Count |  | Project | % Complete |  | Project | Approved Budget | Actual Spend
Green | 4 |  | Apex Nova ERP | 48% |  | Apex Nova ERP | 850000 | 420000
Amber | 4 |  | Helios CRM Rollout | 55% |  | Helios CRM Rollout | 620000 | 310000
Red | 2 |  | Meridian Plant Upgrade | 69% |  | Meridian Plant Upgrade | 1450000 | 970000
|  |  | Orion Data Hub | 43% |  | Orion Data Hub | 980000 | 510000
|  |  | Vantage HR Cloud | 28% |  | Vantage HR Cloud | 540000 | 155000
|  |  | Atlas Warehouse Automation | 72% |  | Atlas Warehouse Automation | 1680000 | 1135000
|  |  | Nimbus Finance Reporting | 39% |  | Nimbus Finance Reporting | 310000 | 120000
|  |  | Quantum Lab Expansion | 61% |  | Quantum Lab Expansion | 2250000 | 1490000
|  |  | Echo Cyber Uplift | 52% |  | Echo Cyber Uplift | 760000 | 398000
|  |  | Summit PMO Maturity | 74% |  | Summit PMO Maturity | 260000 | 175000

## Data Entry
PMO Multiple Project Template
Enter or update project data in the blue/white table below. Dashboard formulas on Sheet 1 will update automatically in Excel.
Project ID | Project Name | Client / Business Unit | Location | Project Manager | Sponsor | Portfolio | Priority | Start Date | End Date | Approved Budget | Actual Spend | % Complete | RAG Status | Team Size | Open Risks | Open Issues | Change Requests | Executive Summary | Planned Duration (Days) | Days Elapsed | Schedule Variance (Days) | Budget Remaining | Budget Variance % | Resource Utilization % | Status Score | Phase | Next Gate
PRJ-001 | Apex Nova ERP | Northbridge Manufacturing | Chicago, USA | Emma Carter | David Lin | Transformation | High | 2026-01-06 | 2026-10-30 | 850000 | 420000 | 48% | Amber | 6 | 3 | 5 | 2 | Stabilize legacy ERP cutover | 297 | 99 | -44 | 430000 | -50.59% | 90.83% | 70 | Execution | Discovery
PRJ-002 | Helios CRM Rollout | Solstice Retail Group | Austin, USA | Liam Brooks | Sophia Nguyen | Technology | High | 2026-02-03 | 2026-08-28 | 620000 | 310000 | 55% | Green | 8 | 2 | 4 | 1 | Rollout to 120 retail stores | 206 | 71 | -42 | 310000 | -50% | 83.75% | 100 | Monitoring | Deploy
PRJ-003 | Meridian Plant Upgrade | BluePeak Foods | Leeds, UK | Olivia Reed | Noah Bennett | Operations | Medium | 2025-11-10 | 2026-09-18 | 1450000 | 970000 | 69% | Red | 10 | 5 | 6 | 4 | Civil works behind baseline | 312 | 156 | -59 | 480000 | -33.1% | 88.5% | 40 | Closing | Build
PRJ-004 | Orion Data Hub | Stratagem Health | Boston, USA | Maya Patel | Ethan Cole | Data | High | 2026-01-20 | 2026-12-15 | 980000 | 510000 | 43% | Amber | 9 | 4 | 5 | 2 | Data governance scope expanded | 329 | 85 | -56 | 470000 | -47.96% | 87.22% | 70 | Closing | Build
PRJ-005 | Vantage HR Cloud | Pinewell Energy | Calgary, Canada | Henry Foster | Ava Martin | HR | Medium | 2026-03-02 | 2026-11-20 | 540000 | 155000 | 28% | Green | 5 | 1 | 3 | 1 | Core design completed | 263 | 44 | -30 | 385000 | -71.3% | 84% | 100 | Initiation | Design
PRJ-006 | Atlas Warehouse Automation | WestHarbor Logistics | Rotterdam, Netherlands | Grace Turner | Lucas Meyer | Automation | High | 2025-12-01 | 2026-10-02 | 1680000 | 1135000 | 72% | Amber | 12 | 6 | 7 | 3 | Vendor integration risk | 305 | 135 | -85 | 545000 | -32.44% | 88.33% | 70 | Closing | Build
PRJ-007 | Nimbus Finance Reporting | Everfield Capital | Dubai, UAE | Jack Sullivan | Zara Khan | Finance | Low | 2026-02-16 | 2026-07-31 | 310000 | 120000 | 39% | Green | 4 | 1 | 2 | 0 | Month-end reporting automation | 165 | 58 | -6 | 190000 | -61.29% | 83.75% | 100 | Closing | Design
PRJ-008 | Quantum Lab Expansion | Aurora Biotech | Basel, Switzerland | Sofia Alvarez | Mason Wright | Capital | High | 2025-10-06 | 2026-12-04 | 2250000 | 1490000 | 61% | Red | 14 | 7 | 8 | 5 | Permit and clean-room delay | 424 | 191 | -68 | 760000 | -33.78% | 88.21% | 40 | Closing | Benefits Realization
PRJ-009 | Echo Cyber Uplift | BrightWave Telecom | Sydney, Australia | Isabella Price | Leo Scott | Cybersecurity | Medium | 2026-01-13 | 2026-09-11 | 760000 | 398000 | 52% | Green | 7 | 2 | 4 | 1 | Security tooling on plan | 241 | 92 | -33 | 362000 | -47.63% | 85% | 100 | Closing | Build
PRJ-010 | Summit PMO Maturity | Crestline Holdings | Singapore | Amelia Ross | Benjamin Tan | PMO | Medium | 2026-01-27 | 2026-06-26 | 260000 | 175000 | 74% | Amber | 3 | 2 | 2 | 0 | Governance model training in progress | 150 | 78 | -33 | 85000 | -32.69% | 91.67% | 70 | Execution | Build
Formulas:
Days Elapsed = TODAY()-[Start Date]
Note on K3: Approved budget in USD. Adjust currency format if your PMO reports in another currency.
Note on M3: Portfolio progress percentage for each project.
Note on N3: RAG = Green / Amber / Red portfolio health indicator.

## Instructions
Instructions — How to Use This PMO Multiple Project Excel Template
Designed for portfolio managers, PMO leads, program directors and executive reporting
1. Purpose | Use this workbook to monitor multiple concurrent projects in one PMO portfolio view. It consolidates schedule, budget, risk, issues, progress, and resource indicators into a single executive dashboard.
2. Sheet Structure | Sheet 1 = executive dashboard and portfolio summary. Sheet 2 = data entry and project-level calculations. Sheet 3 = guidance and setup notes.
3. What to Update | On the Data Entry sheet, update Project Name, Client / Business Unit, Location, Project Manager, Sponsor, Portfolio, Priority, Start Date, End Date, Approved Budget, Actual Spend, % Complete, RAG Status, Team Size, Open Risks, Open Issues, Change Requests, Executive Summary, Phase and Next Gate.
4. What is Calculated Automatically | Planned Duration, Days Elapsed, Schedule Variance, Budget Remaining, Budget Variance %, Resource Utilization %, dashboard KPIs, chart summaries and project spotlight metrics.
5. RAG Rules | Green = on track, Amber = at risk / needs management attention, Red = critical issue requiring escalation. Adjust these rules based on your PMO governance framework.
6. Recommended Update Cadence | Update weekly for portfolio reviews and monthly for steering committee packs. For critical programs, refresh the Data Entry sheet before each governance meeting.
7. Suggested Governance Use | Use the dashboard during PMO review meetings, leadership updates, steering committees, and capacity planning sessions. Focus first on projects with Red status, negative schedule variance, and budget overrun trends.
8. Customization Tips | Add more project rows to the Data Entry sheet as needed. If you expand the table, extend formulas and charts or convert ranges to a larger table range. You can also adapt currency, phases, gates and status logic to your organization.
9. Hypothetical Content Notice | All companies, locations, names, sponsors and project examples in this file are fictional and included only to make the template feel realistic.
Quick start: open Sheet 2, update the project table, then review Sheet 1 for executive reporting. Keep dates, budgets and % complete current for best results.