## Main Template
Production Scheduling Master
Orion Peak Manufacturing • Enterprise Production Control Board • Prepared by Project Management Office
Planning Window Start | 2026-03-28 |  |  | Planning Window End | 2026-04-08 |  |  |  |  | Pending Orders |  | In Progress |  | Completed |  | Delayed |  | On-Time Rate |  | Capacity Utilization
Default View | All Plants |  |  | Prepared For | Executive Operations Review |  |  |  |  | 5 |  | 3 |  | 3 |  | 1 |  | 66.67% |  | 84.31%
Live Schedule Overview | [20 empty] | 12-Day Visual Production Timeline
[21 empty] | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08
Order ID | Customer | Product | Plant | Line | Machine | Supervisor | Shift | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Qty | Produced Qty | Material | Priority | Status | Progress % | Days +/- | Utilization % | Remarks | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
OPS-2401 | Northwind Retail | Aurora Mixer 200 | Dallas Plant | Line A | MX-01 | Elena Torres | Day | 2026-03-30 | 2026-04-01 | 2026-03-30 |  | 1200 | 450 | Available | High | In Progress | 37.5% | 7 | 85% | Pilot batch for spring launch | bar: 2026-03-30 to 2026-04-01
OPS-2402 | Summit Foods | Titan Pack 12 | Dallas Plant | Line B | PK-04 | Marcus Hale | Night | 2026-03-31 | 2026-04-02 |  |  | 800 | 0 | Available | Medium | Pending | 0% | 6 | 75% | Awaiting line clearance | bar: 2026-03-31 to 2026-04-02
OPS-2403 | BlueHarbor Stores | Nova Bottle 1L | Phoenix Hub | Line C | BT-02 | Priya Nair | Day | 2026-03-29 | 2026-03-31 | 2026-03-29 | 2026-03-31 | 1500 | 1500 | Available | High | Completed | 100% | 0 | 93.75% | Finished on schedule | bar: 2026-03-29 to 2026-03-31
OPS-2404 | Helio Pharm | SteriCap 50 | Phoenix Hub | Line D | SC-08 | Derrick Boone | Swing | 2026-03-28 | 2026-03-30 | 2026-03-28 |  | 600 | 420 | Low Stock | Critical | Delayed | 70% | 9 | 140% | Sterile caps arriving late | bar: 2026-03-28 to 2026-03-30
OPS-2405 | Everfield Home | Atlas Kettle X | Nashville Works | Line A | KT-03 | Nina Brooks | Day | 2026-04-01 | 2026-04-04 |  |  | 950 | 0 | Available | Medium | Pending | 0% | 4 | 72.22% | New tooling approved | bar: 2026-04-01 to 2026-04-04
OPS-2406 | FreshRoot Market | PureSeal Jar 8oz | Nashville Works | Line B | JR-05 | Owen Carter | Night | 2026-03-30 | 2026-04-01 | 2026-03-30 |  | 2200 | 800 | Available | High | In Progress | 36.36% | 7 | 95% | High-volume food packaging run | bar: 2026-03-30 to 2026-04-01
OPS-2407 | MetroChef Supply | Forge Pan Set | Dallas Plant | Line C | FG-07 | Laila Khan | Swing | 2026-04-02 | 2026-04-05 |  |  | 500 | 0 | Ordered | Low | Pending | 0% | 3 | 53.33% | Supplier ETA confirmed | bar: 2026-04-02 to 2026-04-05
OPS-2408 | Apex Auto Parts | Torque Bolt Kit | Phoenix Hub | Line E | TB-11 | Victor Chen | Day | 2026-03-27 | 2026-03-29 | 2026-03-27 | 2026-03-30 | 3000 | 3000 | Available | Critical | Completed | 100% | 1 | 103.6% | Closed one day late due to QA hold | bar: 2026-03-28 to 2026-03-29
OPS-2409 | Crescent Hotels | Luna Linen Cart | Nashville Works | Line D | LC-09 | Maya Patel | Night | 2026-04-03 | 2026-04-06 |  |  | 180 | 0 | Available | Low | Pending | 0% | 2 | 55.56% | Custom color finish | bar: 2026-04-03 to 2026-04-06
OPS-2410 | GreenPath Labs | EcoTube 25 | Dallas Plant | Line E | ET-10 | Isaac Stone | Day | 2026-03-28 | 2026-04-01 | 2026-03-28 |  | 1400 | 1100 | Available | High | In Progress | 78.57% | 7 | 94.29% | Validation samples shipped | bar: 2026-03-28 to 2026-04-01
OPS-2411 | Harbor Health | MediTray S | Phoenix Hub | Line A | MT-02 | Sara Whitman | Swing | 2026-03-26 | 2026-03-28 | 2026-03-26 | 2026-03-28 | 900 | 900 | Available | Medium | Completed | 100% | 0 | 87.5% | Ready for dispatch | bar: 2026-03-28
OPS-2412 | NovaBuild Supply | Ridge Fastener Pro | Nashville Works | Line C | RF-12 | Jonas Reed | Day | 2026-04-04 | 2026-04-07 |  |  | 2600 | 0 | Ordered | Medium | Pending | 0% | 1 | 65.79% | Customer requested split shipment | bar: 2026-04-04 to 2026-04-07
Legend | Completed | In Progress | Pending | Delayed |  | Project Manager Insight | Use the dashboard to balance capacity against priority, accelerate delayed jobs, and protect customer due dates.

## Data Entry
Production Scheduling Data Entry
Use this sheet for editable inputs. Fields with dropdowns standardize scheduling data for the dashboard. | [19 empty] | Plant | Line | Shift | Material | Priority | Status
Order ID | Customer | Product | Plant | Line | Machine | Supervisor | Shift | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned Qty | Produced Qty | Material Status | Priority | Status | Capacity Hrs | Required Hrs | Remarks | Dallas Plant | Line A | Day | Available | Low | Pending
OPS-2401 | Northwind Retail | Aurora Mixer 200 | Dallas Plant | Line A | MX-01 | Elena Torres | Day | 2026-03-30 | 2026-04-01 | 2026-03-30 |  | 1200 | 450 | Available | High | In Progress | 40 | 34 | Pilot batch for spring launch | Phoenix Hub | Line B | Swing | Low Stock | Medium | In Progress
OPS-2402 | Summit Foods | Titan Pack 12 | Dallas Plant | Line B | PK-04 | Marcus Hale | Night | 2026-03-31 | 2026-04-02 |  |  | 800 | 0 | Available | Medium | Pending | 24 | 18 | Awaiting line clearance | Nashville Works | Line C | Night | Ordered | High | Delayed
OPS-2403 | BlueHarbor Stores | Nova Bottle 1L | Phoenix Hub | Line C | BT-02 | Priya Nair | Day | 2026-03-29 | 2026-03-31 | 2026-03-29 | 2026-03-31 | 1500 | 1500 | Available | High | Completed | 32 | 30 | Finished on schedule |  | Line D |  | Blocked | Critical | Completed
OPS-2404 | Helio Pharm | SteriCap 50 | Phoenix Hub | Line D | SC-08 | Derrick Boone | Swing | 2026-03-28 | 2026-03-30 | 2026-03-28 |  | 600 | 420 | Low Stock | Critical | Delayed | 20 | 28 | Sterile caps arriving late |  | Line E
OPS-2405 | Everfield Home | Atlas Kettle X | Nashville Works | Line A | KT-03 | Nina Brooks | Day | 2026-04-01 | 2026-04-04 |  |  | 950 | 0 | Available | Medium | Pending | 36 | 26 | New tooling approved
OPS-2406 | FreshRoot Market | PureSeal Jar 8oz | Nashville Works | Line B | JR-05 | Owen Carter | Night | 2026-03-30 | 2026-04-01 | 2026-03-30 |  | 2200 | 800 | Available | High | In Progress | 40 | 38 | High-volume food packaging run
OPS-2407 | MetroChef Supply | Forge Pan Set | Dallas Plant | Line C | FG-07 | Laila Khan | Swing | 2026-04-02 | 2026-04-05 |  |  | 500 | 0 | Ordered | Low | Pending | 30 | 16 | Supplier ETA confirmed
OPS-2408 | Apex Auto Parts | Torque Bolt Kit | Phoenix Hub | Line E | TB-11 | Victor Chen | Day | 2026-03-27 | 2026-03-29 | 2026-03-27 | 2026-03-30 | 3000 | 3000 | Available | Critical | Completed | 28 | 29 | Closed one day late due to QA hold
OPS-2409 | Crescent Hotels | Luna Linen Cart | Nashville Works | Line D | LC-09 | Maya Patel | Night | 2026-04-03 | 2026-04-06 |  |  | 180 | 0 | Available | Low | Pending | 18 | 10 | Custom color finish
OPS-2410 | GreenPath Labs | EcoTube 25 | Dallas Plant | Line E | ET-10 | Isaac Stone | Day | 2026-03-28 | 2026-04-01 | 2026-03-28 |  | 1400 | 1100 | Available | High | In Progress | 35 | 33 | Validation samples shipped
OPS-2411 | Harbor Health | MediTray S | Phoenix Hub | Line A | MT-02 | Sara Whitman | Swing | 2026-03-26 | 2026-03-28 | 2026-03-26 | 2026-03-28 | 900 | 900 | Available | Medium | Completed | 16 | 14 | Ready for dispatch
OPS-2412 | NovaBuild Supply | Ridge Fastener Pro | Nashville Works | Line C | RF-12 | Jonas Reed | Day | 2026-04-04 | 2026-04-07 |  |  | 2600 | 0 | Ordered | Medium | Pending | 38 | 25 | Customer requested split shipment
Note on A3: Unique production order identifier.
Note on Q3: Use Pending, In Progress, Delayed, or Completed to drive dashboard KPIs.
Note on R3: Available capacity hours for the selected line or machine in the plan window.
Note on S3: Hours actually required for this order. Used for utilization analysis.

## Instructions
Instructions & Operating Guide
Workbook owner: Orion Peak Manufacturing PMO • Purpose: standardize production planning, execution tracking, and reporting
1. What this template covers
• Production order planning by plant, line, machine, and shift.
• Planned vs. actual start / finish dates for schedule control.
• Quantity, capacity, material readiness, priority, and execution status.
• KPI monitoring for pending, in-progress, completed, delayed, on-time rate, and utilization.
• A visual 12-day timeline to spot line congestion and deadline risk quickly.
2. How to use the workbook
• Enter or update production orders on the Data Entry sheet only.
• Use the dropdown fields to keep status, priority, and material labels consistent.
• Review the Main Template for executive reporting and daily production meetings.
• Extend the entry table by copying the last formatted row downward if more orders are needed.
3. Recommended PM cadence
• Morning: confirm material status, labor coverage, and line readiness.
• Midday: update produced quantity and flag emerging delays.
• End of day: close completed jobs, revise forecasts, and re-sequence pending work.
4. Color guide
• #2F5597 / #1F3A5F: core headers and leadership dashboard zones.
• #548235 / #70AD47 / #92D050: healthy progress, on-time delivery, and completed jobs.
• #ED7D31 / #FFC000: watch items, constrained capacity, and pending work.
• #C00000: delayed or high-risk orders requiring escalation.
5. Status definitions
• Pending = approved but not started.
• In Progress = work has started and remains active.
• Delayed = behind plan, blocked, or at risk of missing the planned finish.
• Completed = finished and ready for dispatch or next-stage processing.
6. Key field reference
Order ID | Unique production order or work order number.
Plant / Line / Machine | Where production is scheduled to run.
Capacity Hrs | Available hours in the plan window for the assigned resource.
Required Hrs | Expected hours needed to complete the order.
Days +/- | Negative means early, positive means late relative to plan.
Utilization % | Required Hrs divided by Capacity Hrs.