## Main Template
Project Budget Cost Tracker
Executive Project Summary | [7 empty] | Status
Project Name | Aurora Commerce Platform Rollout |  | Start Date | 2026-01-05 |  |  |  | Reporting Month | 2026-03-01
Project Code | PRJ-ACR-2026-014 |  | End Date | 2026-08-28 |  |  |  | Budget Utilized | 75.42%
Client | Northwind Retail Group |  | Approved Budget | 625000 |  |  |  | Schedule Progress | 53.71%
Project Manager | Amelia Hart |  | Contingency | 8% |  |  |  | Forecast at Completion | 471400
Location | Austin, Texas |  | Tax Rate | 7% |  |  |  | Budget Health | On Track
Approved Budget |  |  | Actual Cost to Date |  |  | Remaining Budget |  |  | Variance
625000 |  |  | 471400 |  |  | 153600 |  |  | 153600
Budget by Phase | [6 empty] | Budget by Cost Category
Phase | Budget | Actual | Variance | % Complete | Status |  | Category | Budget | Actual | Variance | Share of Budget
Initiation | 55000 | 48000 | 7000 | 100% | Complete |  | Labor | 325000 | 252000 | 73000 | 52%
Planning | 70000 | 64500 | 5500 | 100% | Complete |  | Software & Licenses | 72000 | 64850 | 7150 | 11.52%
Design | 95000 | 88250 | 6750 | 95% | On Track |  | Hardware / Equipment | 45000 | 42750 | 2250 | 7.2%
Build | 210000 | 134500 | 75500 | 58% | On Track |  | Travel & Workshops | 28000 | 16500 | 11500 | 4.48%
Testing | 85000 | 15000 | 70000 | 18% | Upcoming |  | External Vendors | 108000 | 78500 | 29500 | 17.28%
Deployment | 65000 | 5000 | 60000 | 5% | Upcoming |  | Training & Change Mgmt | 22000 | 9800 | 12200 | 3.52%
Hypercare | 45000 | 0 | 45000 | 0% | Upcoming |  | Contingency Reserve | 25000 | 7000 | 18000 | 4%
Total | 625000 | 355250 | 269750 | 53.71% | 0 |  | Total | 625000 | 471400 | 153600 | 100%
Monthly Spend, Commitments & Payments | [7 empty] | Change Request & Risk Monitor
Month | Planned | Actual | Committed | Paid | Cost Variance | Collection Gap | Invoice Status | Ref | Description | Impact | Status
2026-01-01 | 45000 | 43500 | 45000 | 42000 | 1500 | 3000 | Paid | CR-01 | Additional warehouse scanner integrations | 18500 | Approved
2026-02-01 | 70000 | 69000 | 70000 | 66500 | 1000 | 3500 | Paid | CR-02 | Extended UAT support for store pilot | 9500 | Under Review
2026-03-01 | 85000 | 78200 | 82000 | 75000 | 6800 | 7000 | Part Paid | R-04 | Travel cost volatility for on-site workshops | 6500 | Mitigating
2026-04-01 | 98000 | 91500 | 96500 | 88000 | 6500 | 8500 | Part Paid | R-07 | Vendor response delays affecting deployment | 12000 | Open
2026-05-01 | 102000 | 95000 | 99000 | 62000 | 7000 | 37000 | Pending
2026-06-01 | 88000 | 0 | 84500 | 0 | 88000 | 84500 | Not Due | This executive tracker explains the full project budget story: approved funding, actual spend, remaining funds, phase performance, category-level cost control, monthly cash flow, commitments, payment status, and change impacts. Use the Data Entry sheet to update assumptions and actuals; the dashboard refreshes automatically.
2026-07-01 | 76000 | 0 | 32000 | 0 | 76000 | 32000 | Not Due
2026-08-01 | 61000 | 0 | 12000 | 0 | 61000 | 12000 | Not Due
Total | 625000 | 377200 | 521000 | 333500 | 247800 | 187500

## Data Entry
Project Budget Cost Tracker – Data Entry
Project Setup & Controls
Project Name | Aurora Commerce Platform Rollout |  | Company | BluePeak Delivery Solutions |  | Approved Budget | 625000
Project Code | PRJ-ACR-2026-014 |  | Location | Austin, Texas |  | Contingency % | 8%
Client | Northwind Retail Group |  | Start Date | 2026-01-05 |  | Tax % | 7%
Project Manager | Amelia Hart |  | End Date | 2026-08-28 |  | Reporting Month | 2026-03-01
Budget by Phase | [8 empty] | Budget by Cost Category
Phase | Owner | Start | End | Budget | Actual | % Complete | Status |  | Category | Budget | Actual
Initiation | Amelia Hart | 2026-01-05 | 2026-01-23 | 55000 | 48000 | 100% | Complete |  | Labor | 325000 | 252000
Planning | Victor Chen | 2026-01-26 | 2026-02-20 | 70000 | 64500 | 100% | Complete |  | Software & Licenses | 72000 | 64850
Design | Sofia Bennett | 2026-02-23 | 2026-03-27 | 95000 | 88250 | 95% | On Track |  | Hardware / Equipment | 45000 | 42750
Build | Marcus Doyle | 2026-03-30 | 2026-06-19 | 210000 | 134500 | 58% | On Track |  | Travel & Workshops | 28000 | 16500
Testing | Priya Raman | 2026-06-22 | 2026-07-24 | 85000 | 15000 | 18% | Upcoming |  | External Vendors | 108000 | 78500
Deployment | Noah Alvarez | 2026-07-27 | 2026-08-14 | 65000 | 5000 | 5% | Upcoming |  | Training & Change Mgmt | 22000 | 9800
Hypercare | Elena Brooks | 2026-08-17 | 2026-08-28 | 45000 | 0 | 0% | Upcoming |  | Contingency Reserve | 25000 | 7000
Monthly Cost Plan vs Actual | [6 empty] | Change Requests / Notes
Month | Planned Spend | Actual Spend | Committed Cost | Paid to Date | Invoice Status |  | Ref | Description | Impact | Owner | Status
2026-01-01 | 45000 | 43500 | 45000 | 42000 | Paid |  | CR-01 | Additional warehouse scanner integrations | 18500 | Marcus Doyle | Approved
2026-02-01 | 70000 | 69000 | 70000 | 66500 | Paid |  | CR-02 | Extended UAT support for store pilot | 9500 | Priya Raman | Under Review
2026-03-01 | 85000 | 78200 | 82000 | 75000 | Part Paid |  | R-04 | Travel cost volatility for on-site workshops | 6500 | Amelia Hart | Mitigating
2026-04-01 | 98000 | 91500 | 96500 | 88000 | Part Paid |  | R-07 | Vendor response delays affecting deployment | 12000 | Elena Brooks | Open
2026-05-01 | 102000 | 95000 | 99000 | 62000 | Pending
2026-06-01 | 88000 | 0 | 84500 | 0 | Not Due
2026-07-01 | 76000 | 0 | 32000 | 0 | Not Due
2026-08-01 | 61000 | 0 | 12000 | 0 | Not Due
Note on H4: Approved project budget in USD. Update only when formal budget approval changes.
Note on H5: Contingency reserve as % of approved budget.
Note on H6: Illustrative tax rate for forecasted gross cost calculation.

## Instructions
Instructions – How to Use This Project Budget Cost Tracker
Purpose
This workbook helps a senior project manager plan, monitor, and control budget performance across project phases, cost categories, monthly spend, commitments, payments, and change impacts.
Sheet 1 – Main Template
Executive dashboard with project summary, KPI cards, budget vs actual by phase, category-level tracking, monthly cost control, payment visibility, change log monitoring, and charts.
Sheet 2 – Data Entry
Update all editable inputs here: project setup, approved budget, contingency, tax rate, phase budgets, category actuals, monthly spend, and change requests.
Sheet 3 – Instructions
Contains user guidance, field definitions, design legend, and recommended operating rhythm for budget governance.
Recommended Workflow
1 | Confirm project setup details, approved budget, reporting month, contingency, and tax assumptions on Data Entry.
2 | Update phase budgets and actuals weekly or at each reporting cycle.
3 | Record category-level actual costs to understand where spending pressure is coming from.
4 | Update monthly planned, actual, committed, and paid values to manage cash flow and invoice exposure.
5 | Log approved changes, risks, or additional costs in the Change Requests / Notes section.
6 | Review the Main Template for budget utilization, forecast at completion, remaining budget, and variance.
What This Template Explains
Project Details | Identity, ownership, client, location, and reporting period for governance reporting.
Approved Budget | The formal funding baseline against which all costs are measured.
Cost Categories | Where money is allocated: labor, software, equipment, travel, vendors, training, and contingency.
Phase Tracking | Budget, actual cost, and completion status for each project phase.
Variance Analysis | Difference between budget and actual values to flag under- or over-spend.
Remaining Budget | Unspent funding still available to complete the project.
Forecast at Completion | Expected total cost at project completion based on current performance.
Cash Flow Visibility | Planned, actual, committed, and paid monthly values.
Payment Status | Whether invoices are paid, partially paid, pending, or not yet due.
Change Control | Financial impact of approved changes and active risks.
Design & Color Legend
Core dashboard sections / executive reporting blocks
Workbook title bars and high-emphasis headers
Positive performance / key control sections
Supportive highlight for healthy items
Cash flow and operational monitoring areas
Risk, change control, and management attention areas
Executive notes / items requiring awareness
Supplemental positive section headers
Input emphasis and editable data references
Tip: Blue-toned inputs on the Data Entry sheet are the primary areas to update. The Main Template sheet contains formulas and executive views designed for leadership reporting.