## Main Tracker
Project Budget Cost Tracker
Executive project budget dashboard, cost tracking, payment control, forecast, and variance management
PROJECT PROFILE | [5 empty] | Total Budget |  | Actual Spend |  | Committed Cost |  | Remaining Budget
Project Name | Northgate Smart Campus Rollout | Project Manager | Maya Richardson, PMP | Currency | USD | 980000 |  | 730750 |  | 128000 |  | 121250
Project Code | NGS-2026-014 | Location | Riverton, Colorado | Budget Version | Baseline v1.2
Client | Aurora Civic Holdings | Start Date | 2026-02-02 | Reporting Period | March 2026 | Forecast at Completion |  | Budget Variance |  | % Budget Used |  | Invoices Overdue
Company | BluePeak Project Advisory | End Date | 2026-11-20 | Project Status | Execution | 1018250 |  | -38250 |  | 74.57% |  | 1
STATUS LEGEND
On Track | At Risk | Critical | Paid | Overdue
ID | Cost Category | Owner | Vendor | Budget | Actual | Committed | Forecast | Variance | % Var | Invoice # | Due Date | Payment Status
CB-001 | Labor | Maya Richardson | NorthPeak Staffing | 180000 | 172500 | 12000 | 184500 | -4500 | -2.5% | INV-1045 | 2026-03-22 | Paid
CB-002 | Design & Engineering | Leo Foster | Vertex Design Group | 95000 | 88000 | 5000 | 96000 | -1000 | -1.053% | INV-1061 | 2026-03-29 | Pending
CB-003 | Permits & Compliance | Nadia Bennett | CityWorks Compliance | 24000 | 21500 | 2000 | 23500 | 500 | 2.083% | INV-1078 | 2026-03-18 | Overdue
CB-004 | Site Preparation | Arun Shah | Riverton Civil LLC | 110000 | 126500 | 8500 | 137500 | -27500 | -25% | INV-1092 | 2026-03-27 | Pending
CB-005 | Hardware & Devices | Elena Brooks | Helios Tech Supply | 210000 | 154000 | 42000 | 212000 | -2000 | -0.9524% | INV-1120 | 2026-04-15 | Pending
CB-006 | Software Licenses | Omar Diaz | CloudHarbor Systems | 58000 | 43000 | 12000 | 60000 | -2000 | -3.448% | INV-1128 | 2026-04-18 | Pending
CB-007 | Network Installation | Grace Turner | SignalSpan Networks | 146000 | 118000 | 21000 | 151000 | -5000 | -3.425% | INV-1144 | 2026-04-25 | Pending
CB-008 | Testing & Commissioning | Ethan Cole | PrimeQA Labs | 46000 | 0 | 14000 | 44000 | 2000 | 4.348% | TBD | 2026-05-21 | Pending
CB-009 | Training & Change Mgmt | Sophia Lane | BrightPath Learning | 32000 | 0 | 9000 | 31500 | 500 | 1.562% | TBD | 2026-06-11 | Pending
CB-010 | Travel & Accommodation | Maya Richardson | Summit Corporate Travel | 18000 | 7250 | 2500 | 17250 | 750 | 4.167% | INV-1018 | 2026-03-16 | Paid
CB-011 | Contingency Reserve | Nadia Bennett | Internal Reserve | 45000 | 0 | 0 | 45000 | 0 | 0% | N/A | 2026-07-31 | Pending
CB-012 | Project Closeout | Maya Richardson | BluePeak Project Advisory | 16000 | 0 | 0 | 16000 | 0 | 0% | TBD | 2026-07-31 | Pending
TOTAL |  |  |  | 980000 | 730750 | 128000 | 1018250 | -38250 | -3.903%
MONTHLY SPEND PROFILE | [5 empty] | APPROVAL, RISK & CONTROL
Month | Planned | Actual | Variance | Cumulative Actual |  | Cost Change Requests Approved |  |  | 3
Feb-26 | 95000 | 88500 | 6500 | 88500 |  | Contingency Reserve |  |  | $45,000
Mar-26 | 145000 | 138750 | 6250 | 227250 |  | Largest Overrun Area |  |  | Site Preparation
Apr-26 | 165000 | 0 | 165000 | 227250 |  | Next Steering Committee |  |  | 31-Mar-2026
May-26 | 185000 | 0 | 185000 | 227250 |  | Budget Health Status |  |  | Over Budget
Jun-26 | 140000 | 0 | 140000 | 227250 |  | Finance Review Owner |  |  | Nadia Bennett
Jul-26 | 120000 | 0 | 120000 | 227250
Management note: This tracker combines baseline budget, actual cost, committed cost, forecast at completion, invoice controls, monthly burn monitoring, and budget variance analytics to support strong governance.
Note on B40: All names, places, and companies in this workbook are hypothetical.

## Data Entry
Data Entry - Editable Working Sheet
Enter or update budget line items here. The main tracker reads from this sheet automatically.
ID | Cost Category | Owner | Vendor | Cost Type | Budget | Actual | Committed | Forecast | Approved? | Month | Invoice # | Due Date | Payment Status | Notes / Assumptions
CB-001 | Labor | Maya Richardson | NorthPeak Staffing | OPEX | 180000 | 172500 | 12000 | 184500 | Yes | Mar-26 | INV-1045 | 2026-03-22 | Paid | Core PMO and implementation consultants
CB-002 | Design & Engineering | Leo Foster | Vertex Design Group | CAPEX | 95000 | 88000 | 5000 | 96000 | Yes | Mar-26 | INV-1061 | 2026-03-29 | Pending | Detailed design package and revisions
CB-003 | Permits & Compliance | Nadia Bennett | CityWorks Compliance | OPEX | 24000 | 21500 | 2000 | 23500 | Yes | Mar-26 | INV-1078 | 2026-03-18 | Overdue | Utility permits and inspection fees
CB-004 | Site Preparation | Arun Shah | Riverton Civil LLC | CAPEX | 110000 | 126500 | 8500 | 137500 | Yes | Mar-26 | INV-1092 | 2026-03-27 | Pending | Unexpected rock excavation increased cost
CB-005 | Hardware & Devices | Elena Brooks | Helios Tech Supply | CAPEX | 210000 | 154000 | 42000 | 212000 | Yes | Apr-26 | INV-1120 | 2026-04-15 | Pending | Controllers, gateways, smart sensors
CB-006 | Software Licenses | Omar Diaz | CloudHarbor Systems | OPEX | 58000 | 43000 | 12000 | 60000 | Yes | Apr-26 | INV-1128 | 2026-04-18 | Pending | 12-month platform and analytics licenses
CB-007 | Network Installation | Grace Turner | SignalSpan Networks | CAPEX | 146000 | 118000 | 21000 | 151000 | Yes | Apr-26 | INV-1144 | 2026-04-25 | Pending | Fiber, switching, and field cabling
CB-008 | Testing & Commissioning | Ethan Cole | PrimeQA Labs | OPEX | 46000 | 0 | 14000 | 44000 | No | May-26 | TBD | 2026-05-21 | Pending | Performance test scripts and commissioning
CB-009 | Training & Change Mgmt | Sophia Lane | BrightPath Learning | OPEX | 32000 | 0 | 9000 | 31500 | No | Jun-26 | TBD | 2026-06-11 | Pending | End-user training sessions across campus
CB-010 | Travel & Accommodation | Maya Richardson | Summit Corporate Travel | OPEX | 18000 | 7250 | 2500 | 17250 | Yes | Mar-26 | INV-1018 | 2026-03-16 | Paid | Site visits, workshops, executive reviews
CB-011 | Contingency Reserve | Nadia Bennett | Internal Reserve | CAPEX | 45000 | 0 | 0 | 45000 | Approved | Jul-26 | N/A | 2026-07-31 | Pending | Held for approved change requests only
CB-012 | Project Closeout | Maya Richardson | BluePeak Project Advisory | OPEX | 16000 | 0 | 0 | 16000 | No | Jul-26 | TBD | 2026-07-31 | Pending | Documentation, punch list, handover support
QUICK ENTRY GUIDANCE
Editable fields |  | All columns on this sheet
Do not edit |  | Main Tracker formulas, KPI cards, and charts
Required minimum fields |  | ID, Cost Category, Budget, Actual, Forecast, Due Date, Payment Status
Variance logic |  | Main Tracker calculates Budget - Forecast
Recommended review cycle |  | Update weekly; review monthly with finance
Note on F6: Example input for demonstration only; replace with your project's figures.
Note on G6: Example input for demonstration only; replace with your project's figures.
Note on H6: Example input for demonstration only; replace with your project's figures.
Note on I6: Example input for demonstration only; replace with your project's figures.

## Instructions
Instructions & Best-Practice Guide
Designed as a senior-project-manager-ready template for planning, monitoring, controlling, and reporting project cost performance.
1. Purpose
Use this workbook to manage baseline budget, actual cost, committed cost, forecast at completion, invoice due dates, payment status, and budget variance for a single project or program workstream.
2. Workbook Structure
Main Tracker = executive view and reporting dashboard. Data Entry = editable line-item table. Instructions = operating guide and governance rules.
3. How to Update
Enter new cost lines or revise existing amounts on the Data Entry sheet only. The Main Tracker updates automatically through linked formulas and charts.
4. Key Metrics Explained
Budget = approved baseline amount. Actual = incurred or posted spend. Committed = approved spend not yet invoiced or posted. Forecast = expected final cost for that line item. Variance = Budget minus Forecast. Positive variance means potential savings; negative variance means overrun.
5. Payment Control
Maintain Invoice #, Due Date, and Payment Status to monitor accounts payable exposure. Overdue items should be discussed in weekly commercial and finance reviews.
6. Governance Advice
Review the sheet weekly with workstream leads and monthly with finance. Record reasons for material movements in the Notes / Assumptions column.
7. Customization Tips
Duplicate additional rows in Data Entry if needed. Update month lists and chart ranges for longer projects. Protect formula cells before distributing broadly.
8. Example Scenario
This sample models a smart-campus deployment for Aurora Civic Holdings managed by BluePeak Project Advisory in Riverton, Colorado. All names, places, and companies are hypothetical.
Color Guide
Deep Navy | Primary title bars and executive headers
Sky Blue | Dashboard strips and linked summary sections
Teal | Data-entry headers and emphasis labels
Soft Mist | Readable input areas and note backgrounds
Indigo / Violet | Secondary accents, section dividers, and visual highlights