## Main Tracker
Project Budget Cost Tracker
Apex Horizon Construction ¦ NorthGate Innovation Campus Fit-Out ¦ Fictional sample project
Project Profile & Controls | [6 empty] | Executive Cost Dashboard
Company | Apex Horizon Construction |  | Project Sponsor | Olivia Mercer |  |  | Total Budget |  | Actual Cost |  | Committed Cost
Project Name | NorthGate Innovation Campus Fit-Out |  | Project Manager | Daniel Whitmore, Sr. PM |  |  | 1318000 |  | 557305 |  | 617900
Client | NovaCore Biotech |  | Project Location | Riverton Business District, Colorado
Start Date | 2026-01-12 |  | End Date | 2026-10-30 |  |  | Remaining Budget |  | % Budget Spent |  | Forecast at Completion
Report Date | 2026-06-30 |  | Status | Execution / Monitor & Control |  |  | 142795 |  | 42.28% |  | 1071740.3846
% Complete | 52% |  | Contingency Reserve | 85000
[7 empty] | Budget Variance |  | Cost Performance Index
[7 empty] | 246259.6154 |  | 1.2298
Category Budget vs Actual Analysis | [6 empty] | Phase Budget & Delivery Performance
Category | Budget | Actual | Committed | Variance | Utilization |  | Phase | Budget | Actual | Committed | Variance | Phase Lead | Status
Labor | 220000 | 140910 | 0 | 79090 | 64.05% |  | Initiation & Design | 90000 | 39050 | 0 | 50950 | Sophia Lane | Closed
Materials | 400000 | 39800 | 339900 | 20300 | 94.92% |  | Procurement | 160000 | 17920 | 84000 | 58080 | Ethan Cole | Active
Equipment | 65000 | 24370 | 22000 | 18630 | 71.34% |  | Construction | 760000 | 480515 | 483400 | -203915 | Maya Bennett | Active
Subcontractors | 480000 | 301120 | 236000 | -57120 | 111.9% |  | Systems Commissioning | 160000 | 14220 | 38700 | 107080 | Liam Hart | Upcoming
Travel | 18000 | 10605 | 0 | 7395 | 58.92% |  | Handover & Closeout | 148000 | 5600 | 11800 | 130600 | Ava Sinclair | Upcoming
Training | 30000 | 6200 | 20000 | 3800 | 87.33% |  | Total | 1318000 | 557305 | 617900 | 142795 | Program Team | Mixed
Permits & Compliance | 20000 | 14500 | 0 | 5500 | 72.5%
Contingency | 85000 | 19800 | 0 | 65200 | 23.29%
Total | 1318000 | 557305 | 617900 | 142795 | 89.17%
Monthly Spend Trend & Run-Rate Forecast | [7 empty] | Senior PM Review Notes & Controls
Month | Actual | Committed | Cumulative Actual | Cumulative Plan | Variance vs Plan | Avg Monthly Burn |  | Control Area |  | Health |  | Comment / Action
2026-01-01 | 39050 | 0 | 39050 | 131800 | -92750 | 39050 |  | Labor utilization |  | Watch |  | Overtime increased during construction. Review crew mix and resequence weekend work.
2026-02-01 | 17920 | 62000 | 56970 | 263600 | -206630 | 28485 |  | Materials lead time |  | Good |  | Steel framing and specialty glass are fully committed and tracking to plan.
2026-03-01 | 125950 | 96500 | 182920 | 395400 | -212480 | 60973.3333 |  | Subcontractor claims |  | Risk |  | Monitor change request NCR-04 from Zenith MEP Services before July governance review.
2026-04-01 | 53425 | 132000 | 236345 | 527200 | -290855 | 59086.25 |  | Travel & lodging |  | Good |  | Site visits remain below budget due to virtual coordination sessions.
2026-05-01 | 141710 | 108500 | 378055 | 659000 | -280945 | 75611 |  | Contingency drawdown |  | Watch |  | Use contingency only for approved scope changes and safety-related actions.
2026-06-01 | 179250 | 58000 | 557305 | 790800 | -233495 | 92884.1667 |  | Closeout readiness |  | Good |  | Digital punch list and commissioning file structure are already established.
2026-07-01 | 0 | 118600 | 557305 | 922600 | -365295 | 79615
2026-08-01 | 0 | 30500 | 557305 | 1054400 | -497095 | 69663.125
2026-09-01 | 0 | 11800 | 557305 | 1186200 | -628895 | 61922.7778
2026-10-01 | 0 | 0 | 557305 | 1318000 | -760695 | 55730.5

## Data Entry
Data Entry ¦ Hypothetical live project transactions, category budgets, and phase budgets
Update the Expense Log only. The Main Tracker dashboard refreshes automatically when opened in Excel.
Cost ID | Date | Month | Phase | Category | Cost Type | Description | Vendor / Payee | Owner | Location | Status | Budgeted | Committed | Actual | Notes | Category Budget | Budget (USD) | Phase Budget | Budget (USD)
C-001 | 2026-01-15 | 2026-01-01 | Initiation & Design | Labor | Timesheet | Program mobilization workshop | BrightPath PMO | Daniel Whitmore | Riverton HQ | Approved | 22000 | 0 | 21000 | Kickoff facilitation and planning | Labor | 220000 | Initiation & Design | 90000
C-002 | 2026-01-20 | 2026-01-01 | Initiation & Design | Training | Training | Safety induction for field supervisors | Summit Learning Group | Sophia Lane | Riverton HQ | Approved | 6500 | 0 | 6200 | Mandatory HSE training | Materials | 400000 | Procurement | 160000
C-003 | 2026-01-28 | 2026-01-01 | Initiation & Design | Permits & Compliance | Permit | Early works permit package | City of Riverton | Sophia Lane | Riverton | Approved | 12000 | 0 | 11850 | Permit fees | Equipment | 65000 | Construction | 760000
C-004 | 2026-02-05 | 2026-02-01 | Procurement | Materials | Purchase Order | Steel framing release 1 | NorthPeak Steel | Ethan Cole | Denver | Committed | 68000 | 62000 | 0 | Long lead package | Subcontractors | 480000 | Systems Commissioning | 160000
C-005 | 2026-02-12 | 2026-02-01 | Procurement | Labor | Consulting | Procurement planning support | Beacon Commercial Advisors | Ethan Cole | Remote | Approved | 14000 | 0 | 13600 | Bid tabulation support | Travel | 18000 | Handover & Closeout | 148000
C-006 | 2026-02-16 | 2026-02-01 | Procurement | Travel | Travel | Client design review travel | Skyline Travel Co. | Olivia Mercer | Chicago | Approved | 4800 | 0 | 4320 | Air + hotel | Training | 30000
C-007 | 2026-03-03 | 2026-03-01 | Procurement | Equipment | Rental | Temporary site offices | MetroSite Rentals | Maya Bennett | Riverton Site | Committed | 24000 | 22000 | 0 | 3-month rental | Permits & Compliance | 20000
C-008 | 2026-03-07 | 2026-03-01 | Construction | Subcontractors | Subcontract | Demolition package | Granite Demo Services | Maya Bennett | Riverton Site | Approved | 95000 | 0 | 93200 | Phase 1 demo complete | Contingency | 85000
C-009 | 2026-03-10 | 2026-03-01 | Construction | Materials | Purchase Order | Interior partition framing | NorthPeak Steel | Maya Bennett | Riverton Site | Committed | 78000 | 74500 | 0 | Partition package
C-010 | 2026-03-18 | 2026-03-01 | Construction | Labor | Timesheet | Site supervision - March | Apex Horizon Construction | Maya Bennett | Riverton Site | Approved | 31000 | 0 | 32750 | Includes weekend coordination
C-011 | 2026-04-02 | 2026-04-01 | Construction | Subcontractors | Subcontract | MEP rough-in mobilization | Zenith MEP Services | Maya Bennett | Riverton Site | Committed | 140000 | 132000 | 0 | Notice to proceed issued
C-012 | 2026-04-06 | 2026-04-01 | Construction | Materials | Purchase Order | Electrical cable trays | VoltEdge Supply | Maya Bennett | Riverton Site | Approved | 41000 | 0 | 39800 | Invoice paid
C-013 | 2026-04-14 | 2026-04-01 | Construction | Equipment | Rental | Scissor lifts and access gear | MetroSite Rentals | Maya Bennett | Riverton Site | Approved | 9800 | 0 | 10150 | Extended by 2 weeks
C-014 | 2026-04-26 | 2026-04-01 | Construction | Travel | Travel | Executive site audit visit | Skyline Travel Co. | Daniel Whitmore | Riverton Site | Approved | 3600 | 0 | 3475 | Sponsor walkdown
C-015 | 2026-05-04 | 2026-05-01 | Construction | Labor | Timesheet | Site supervision - May | Apex Horizon Construction | Maya Bennett | Riverton Site | Approved | 32500 | 0 | 33840 | Peak workfront coverage
C-016 | 2026-05-08 | 2026-05-01 | Construction | Materials | Purchase Order | Specialty glass order | ClearSpan Architectural | Ethan Cole | Denver | Committed | 112000 | 108500 | 0 | Fabrication started
C-017 | 2026-05-11 | 2026-05-01 | Construction | Subcontractors | Subcontract | Interior drywall package | Cobalt Interiors | Maya Bennett | Riverton Site | Approved | 88000 | 0 | 85420 | Progress application #1
C-018 | 2026-05-17 | 2026-05-01 | Construction | Permits & Compliance | Inspection | Mid-project safety inspection | Riverton Safety Bureau | Sophia Lane | Riverton | Approved | 2800 | 0 | 2650 | No major findings
C-019 | 2026-05-22 | 2026-05-01 | Construction | Contingency | Change Control | Unforeseen slab repair | Apex Horizon Construction | Daniel Whitmore | Riverton Site | Approved | 22000 | 0 | 19800 | Approved change NCR-02
C-020 | 2026-06-03 | 2026-06-01 | Construction | Labor | Timesheet | Site supervision - June | Apex Horizon Construction | Maya Bennett | Riverton Site | Approved | 33400 | 0 | 34120 | High coordination effort
C-021 | 2026-06-05 | 2026-06-01 | Construction | Subcontractors | Subcontract | MEP rough-in progress claim | Zenith MEP Services | Maya Bennett | Riverton Site | Approved | 126000 | 0 | 122500 | Application #2
C-022 | 2026-06-07 | 2026-06-01 | Construction | Materials | Purchase Order | Flooring materials | UrbanSurface Finishings | Ethan Cole | Riverton Site | Committed | 54000 | 49800 | 0 | Delivery in July
C-023 | 2026-06-09 | 2026-06-01 | Systems Commissioning | Equipment | Purchase | BMS testing kit | ControlGrid Systems | Liam Hart | Riverton Site | Approved | 14500 | 0 | 14220 | Commissioning prep
C-024 | 2026-06-14 | 2026-06-01 | Systems Commissioning | Training | Training | Client operator training design | Summit Learning Group | Liam Hart | Remote | Committed | 9000 | 8200 | 0 | Training deck development
C-025 | 2026-06-21 | 2026-06-01 | Construction | Travel | Travel | Supplier coordination visit | Skyline Travel Co. | Ethan Cole | Phoenix | Approved | 2950 | 0 | 2810 | Glass vendor quality review
C-026 | 2026-06-24 | 2026-06-01 | Handover & Closeout | Labor | Admin | Closeout documentation setup | BrightPath PMO | Ava Sinclair | Remote | Approved | 5800 | 0 | 5600 | Folder structure and templates
C-027 | 2026-07-02 | 2026-07-01 | Construction | Subcontractors | Subcontract | Interior finishes progress claim | Cobalt Interiors | Maya Bennett | Riverton Site | Committed | 76000 | 73500 | 0 | July payment cycle
C-028 | 2026-07-10 | 2026-07-01 | Construction | Materials | Purchase Order | Ceiling grid & tiles | UrbanSurface Finishings | Ethan Cole | Riverton Site | Committed | 47000 | 45100 | 0 | Scheduled for August install
C-029 | 2026-08-05 | 2026-08-01 | Systems Commissioning | Subcontractors | Specialist | TAB contractor mobilization | Precision Air Balance | Liam Hart | Riverton Site | Committed | 32000 | 30500 | 0 | Testing in August
C-030 | 2026-09-04 | 2026-09-01 | Handover & Closeout | Training | Training | Client handover workshops | Summit Learning Group | Ava Sinclair | Riverton HQ | Committed | 12500 | 11800 | 0 | September readiness
Note on R5: Hypothetical planning baseline created for demonstration only. Reference: https://support.microsoft.com/excel
Note on U5: Hypothetical phase baseline. General PM guidance reference: https://www.pmi.org/

## Instructions
Instructions ¦ How to use this Project Budget Cost Tracker
Designed by a senior project manager for disciplined cost control, executive reporting, and audit-ready tracking.
1) Purpose of the workbook
This workbook manages the full project cost picture: baseline budget, committed cost, actual cost, remaining budget, forecast at completion, category variance, phase performance, monthly spend trend, and control comments. The sample data is fictional and uses hypothetical companies, people, and places to feel realistic.
2) How to update the tracker
Step 1: Go to the Data Entry sheet. Step 2: Add or edit transactions only in the Expense Log table. Step 3: Update Date, Phase, Category, Cost Type, Description, Vendor, Owner, Status, and the Budgeted / Committed / Actual values. Step 4: Update Category Budget or Phase Budget tables if the approved baseline changes. Step 5: Open the Main Tracker sheet to review KPI cards, category analysis, phase analysis, charts, and PM control notes. Step 6: Use the tracker at weekly site meetings, monthly cost reviews, and change control boards.
3) What the main dashboard explains
The Main Tracker sheet explains: • Total approved budget and cost consumed • Budget spent percentage and remaining available funds • Forecast at completion based on progress burn rate • Budget variance and cost performance index • Category-level budget vs actual vs committed performance • Phase-level budget performance and accountabilities • Monthly cumulative spend trend against plan • Senior PM review notes for action, risk, and governance
4) Color legend & management signals
Dark navy / blue headers = executive reporting zones Green shades = healthy or positive control signals Orange = review focus or active management attention Red = cost risk, issue, or negative variance requiring action Yellow = totals or watch areas White cells in the Expense Log = data entry fields Charts on Main Tracker = decision support visuals for steering committees
Best practice | Keep one row per cost event, PO, invoice, accrual, or approved change.
PM tip | Separate committed cost from actual cost to see future cash exposure early.
Governance | Review negative variance, CPI below 1.00x, and contingency drawdown at each monthly review.