## Main Template
PROJECT BUDGET REVIEW
Executive financial review for a live project — with budget control, trend analysis, forecast and actions.
Project Snapshot
Project Name | Aurora CRM Modernization | Project Manager | Aisha Rahman | Client | Northwind Consumer Brands | Location | Seattle, Washington | Reporting Period | March 2026 | Status | Amber
Budget Control Dashboard
550000 |  | 230500 |  | 543500 |  | -6500 |  | 41.91% |  | 18000
Approved Budget |  | Actual to Date |  | Forecast at Completion |  | Variance vs Budget |  | % Budget Used |  | Contingency Remaining
Cost Category Review | [7 empty] | Monthly Trend
Category | Owner | Approved Budget | Actual to Date | Forecast to Complete | EAC | Variance |  | Month | Planned | Actual | Variance
Labor - Internal | PMO | 185000 | 72500 | 104000 | 176500 | -8500 |  | Jan-26 | 85000 | 82000 | -3000
Labor - External | Delivery Partner | 160000 | 83000 | 92000 | 175000 | 15000 |  | Feb-26 | 94000 | 97000 | 3000
Software & Licenses | IT Procurement | 68000 | 29000 | 42000 | 71000 | 3000 |  | Mar-26 | 91000 | 88500 | -2500
Infrastructure / Cloud | Platform Ops | 54000 | 21000 | 35000 | 56000 | 2000 |  | Apr-26 | 76000 | 0 | -76000
Travel & Workshops | PMO | 22000 | 9000 | 12000 | 21000 | -1000 |  | May-26 | 72000 | 0 | -72000
Training & Change Mgmt | HR Enablement | 36000 | 14000 | 23000 | 37000 | 1000 |  | Jun-26 | 69000 | 0 | -69000
Contingency | Project Sponsor | 25000 | 2000 | 5000 | 7000 | -18000 |  | Jul-26 | 64000 | 0 | -64000
TOTAL |  | 550000 | 230500 | 313000 | 543500 | -6500 |  | Aug-26 | 39000 | 0 | -39000
Variance Analysis & Management Actions | [6 empty] | Executive Review Flags
Key Drivers |  |  | Corrective Actions |  | Approvals & Decisions |  | Budget Health | On Budget
1) External design workshops ran longer than planned. 2) New compliance requirements added modest software costs. 3) Travel remained below plan due to hybrid sessions. |  |  | 1) Shift two contractor roles to blended onshore/offshore mix. 2) Freeze non-essential travel through May. 3) Draw contingency only with sponsor approval. |  | Finance Reviewer: Elena Brooks PM Review Complete: Yes Sponsor Decision: Proceed within revised ETC assumptions. |  | SPI-style Read | Ahead / Efficient
[7 empty] | Governance | Next review: monthly steering committee
[7 empty] | Travel Spend | Below Plan
[7 empty] | Change Control | Active CRs

## Data Entry
PROJECT BUDGET REVIEW TEMPLATE — DATA ENTRY HUB
Populate only the blue/yellow cells. The Main Template sheet updates automatically.
1) Project Profile |  |  |  |  | 2) Budget by Cost Category
Project Name | Aurora CRM Modernization |  |  |  | Cost Category | Owner | Approved Budget | Actual to Date | Forecast to Complete
Project Code | ACM-2026-017 |  |  |  | Labor - Internal | PMO | 185000 | 72500 | 104000
Client / Business Unit | Northwind Consumer Brands |  |  |  | Labor - External | Delivery Partner | 160000 | 83000 | 92000
Delivery Company | BluePeak Advisory Group |  |  |  | Software & Licenses | IT Procurement | 68000 | 29000 | 42000
Project Manager | Aisha Rahman |  |  |  | Infrastructure / Cloud | Platform Ops | 54000 | 21000 | 35000
Sponsor | Daniel Mercer |  |  |  | Travel & Workshops | PMO | 22000 | 9000 | 12000
Project Location | Seattle, Washington |  |  |  | Training & Change Mgmt | HR Enablement | 36000 | 14000 | 23000
Reporting Period | March 2026 |  |  |  | Contingency | Project Sponsor | 25000 | 2000 | 5000
Review Date | 2026-03-28 |  |  |  | TOTAL |  | 550000 | 230500 | 313000
Start Date | 2026-01-06
Planned Finish | 2026-08-28
Status | Amber
3) Monthly Spend Plan vs Actual
Month | Planned Spend | Actual Spend | Change Requests | Notes | Forecast Commentary
Jan-26 | 85000 | 82000 | 0 | Kick-off, architecture & discovery | Vendor labor rates stabilized in March; major forecast pressure sits in April data migration and change enablement.
Feb-26 | 94000 | 97000 | 5000 | CRM design workshops expanded
Mar-26 | 91000 | 88500 | 0 | Integration sprint on track
Apr-26 | 76000 | 0 | 12000 | Data migration rehearsal planned
May-26 | 72000 | 0 | 8000 | Training content build
Jun-26 | 69000 | 0 | 0 | UAT and remediation
Jul-26 | 64000 | 0 | 0 | Go-live cutover prep
Aug-26 | 39000 | 0 | 0 | Hypercare & project close
4) Review Narrative & Actions
Variance Drivers |  |  |  | Corrective Actions |  |  |  | Approvals / Notes
1) External design workshops ran longer than planned. 2) New compliance requirements added modest software costs. 3) Travel remained below plan due to hybrid sessions. |  |  |  | 1) Shift two contractor roles to blended onshore/offshore mix. 2) Freeze non-essential travel through May. 3) Draw contingency only with sponsor approval. |  |  |  | Finance Reviewer: Elena Brooks PM Review Complete: Yes Sponsor Decision: Proceed within revised ETC assumptions.
Note on H6: Hypothetical approved budget input for demonstration.
Note on B7: All names, companies, and places in this workbook are fictional examples.

## Instructions
INSTRUCTIONS & USER GUIDE
This workbook is designed like a senior-project-manager budget review pack: enter data once, then present from the Main Template.
Workbook Structure
Sheet | Purpose | What You Update | Notes
Main Template | Executive review page with project snapshot, KPIs, category analysis, monthly trend, review flags and management actions. | Read-only presentation sheet | Dark blue / green / orange theme
Data Entry | Single place to update profile, budget lines, monthly actuals, risks, comments and approvals. | Update blue input cells | Includes hypothetical project data
Instructions | How to use, what each section means, and interpretation notes. | Reference sheet | Safe to print or share
How to Use This Template
1. Update the Project Profile | Enter the latest project metadata in Data Entry!B5:B16, including PM, sponsor, review date and RAG status.
2. Refresh category-level costs | Maintain each cost category's Approved Budget, Actual to Date and Forecast to Complete in Data Entry!H6:J12.
3. Update monthly performance | Enter plan vs actual monthly spend in Data Entry!A21:D28. The monthly trend chart updates on the Main Template.
4. Capture the story behind the numbers | Use the narrative blocks for variance drivers, corrective actions and approvals so the review is decision-ready.
5. Present from Main Template | Use the Main Template sheet for steering committees, PMO reviews, sponsor checkpoints and finance governance.
What This Template Explains
Project information | Who owns the project, where it is delivered, who sponsors it, what period is under review.
Approved budget summary | The financially approved baseline against which all actuals and forecasts are tested.
Plan vs actual performance | Whether costs are landing as expected at both category and month levels.
Variance analysis | The amount by which expected end cost differs from the approved budget.
Forecast at completion | What the total project cost is likely to be if current trends continue.
Remaining contingency | How much financial buffer remains for genuine uncertainty.
Management action plan | What the project manager and sponsor will do to correct or contain overruns.
Approvals and governance | The review trail needed for PMO, finance and sponsor sign-off.
Interpretation Guide
Variance vs Budget | Positive value means forecasted overspend; zero or negative means the project is within approved budget.
% Budget Used | Useful for judging burn rate against overall delivery progress.
Contingency Remaining | If close to zero too early, reforecast carefully and tighten change control.
Monthly Variance | A positive month variance means actual spend exceeded plan that month.