## Main Template
PROJECT CALENDAR
One-page portfolio-style calendar view for dates, milestones, meetings, owners, holidays, priority and progress
| Project Overview | [6 empty] | Executive Snapshot |  |  |  | Legend & Status Guide
| Project Name |  | Aurora Nexus ERP Rollout |  |  |  |  | Total Activities | Completed | In Progress |  | Completed | Done and closed
| Company |  | Northbridge Horizon Consulting |  |  |  |  | 21 | 3 | 2 |  | In Progress | Currently active
| Client |  | Sterling Retail Group | [8 empty] | Planned | Approved but not started
| Project Manager |  | Layla Bennett |  |  |  |  | Upcoming Milestones | Overdue | Team Members |  | Delayed / Overdue | Needs intervention
| Project Dates |  | 01-Apr-2026 to 30-Jun-2026 |  |  |  |  | 2 | 2 | 7 |  | Holiday | No working day
| Primary Location |  | Chicago, Illinois | [8 empty] | Milestone | Decision or approval gate
APRIL 2026 ¦ MONTHLY CALENDAR VIEW
| MONDAY |  |  | TUESDAY |  |  | WEDNESDAY |  | THURSDAY |  | FRIDAY |  | SATURDAY |  |  | SUNDAY
| 30 |  |  | 31 |  |  | 1 Kickoff meeting Sponsor brief |  | 2 Scope charter |  | 3 Comms plan |  | 4 |  |  | 5
| 6 Open for planning |  |  | 7 Workshop 1 |  |  | 8 Migration strategy |  | 9 Open for planning |  | 10 Spring closure |  | 11 |  |  | 12
| 13 Open for planning |  |  | 14 Open for planning |  |  | 15 Open for planning |  | 16 Blueprint sign-off |  | 17 Open for planning |  | 18 |  |  | 19
| 20 Integration review |  |  | 21 Training plan |  |  | 22 Open for planning |  | 23 Open for planning |  | 24 Risk board |  | 25 |  |  | 26
| 27 Open for planning |  |  | 28 Sprint 1 in flight |  |  | 29 Open for planning |  | 30 Open for planning |  | 1 |  | 2 |  |  | 3
| 60-Day Workstream Schedule | [10 empty] | Milestone & Holiday Tracker
| ID | Workstream | Task / Event | Owner | Start | Finish | Status | Priority |  |  |  | Date | Category | Event | Owner
| AUR-001 | Initiation | Executive kickoff meeting | Layla Bennett | 2026-04-01 | 2026-04-01 | Completed | High |  |  |  | 2026-04-10 | Holiday | Spring Office Closure | All Teams
| AUR-002 | Planning | Finalize scope & charter | Marcus Hale | 2026-04-01 | 2026-04-03 | Completed | High |  |  |  | 2026-04-16 | Milestone | Solution blueprint sign-off | Layla Bennett
| AUR-003 | Planning | Publish communication plan | Sofia Ramirez | 2026-04-02 | 2026-04-05 | Completed | Medium |  |  |  | 2026-04-24 | Meeting | Risk review board | Layla Bennett
| AUR-004 | Design | Process mapping workshops | Noah Chen | 2026-04-06 | 2026-04-10 | In Progress | High |  |  |  | 2026-05-08 | Task | Mock migration rehearsal ends | Priya Nasser
| AUR-005 | Design | Data migration strategy | Priya Nasser | 2026-04-08 | 2026-04-15 | In Progress | High |  |  |  | 2026-06-18 | Milestone | Go-live readiness gate | Layla Bennett
| AUR-006 | Design | Solution blueprint sign-off | Layla Bennett | 2026-04-16 | 2026-04-16 | Planned | High
| AUR-007 | Build | Configuration sprint 1 | Ethan Brooks | 2026-04-17 | 2026-04-30 | Planned | High
| AUR-008 | Build | Integration design review | Ava Patel | 2026-04-20 | 2026-04-20 | Planned | Medium
Tip: Replace example activities with your real task list in the Data Entry sheet; the overview and KPI cards will update automatically.
Note on D10: These fields are linked to the Data Entry sheet so you only maintain data once.

## Data Entry
Project Calendar Template ¦ Data Entry Hub
Control | Value
Project Name | Aurora Nexus ERP Rollout
Company | Northbridge Horizon Consulting
Client | Sterling Retail Group
Project Manager | Layla Bennett
Location | Chicago, Illinois
Project Start | 2026-04-01
Project End | 2026-06-30
Reporting Month | 2026-04-01
[12 empty] | Name | Availability
Task & Event Register | [11 empty] | Layla | 100
ID | Workstream | Task / Event | Owner | Start Date | End Date | Status | Priority | Type | Location | Dependency | Notes | Marcus | 80
AUR-001 | Initiation | Executive kickoff meeting | Layla Bennett | 2026-04-01 | 2026-04-01 | Completed | High | Meeting | Chicago HQ | - | Formal project launch with sponsors | Sofia | 60
AUR-002 | Planning | Finalize scope & charter | Marcus Hale | 2026-04-01 | 2026-04-03 | Completed | High | Task | Chicago HQ | AUR-001 | Scope baseline approved | Noah | 100
AUR-003 | Planning | Publish communication plan | Sofia Ramirez | 2026-04-02 | 2026-04-05 | Completed | Medium | Task | Remote | AUR-002 | Stakeholder cadence agreed | Priya | 90
AUR-004 | Design | Process mapping workshops | Noah Chen | 2026-04-06 | 2026-04-10 | In Progress | High | Meeting | Chicago HQ | AUR-002 | 4 workshops across operations and finance
AUR-005 | Design | Data migration strategy | Priya Nasser | 2026-04-08 | 2026-04-15 | In Progress | High | Task | Remote | AUR-004 | Includes cleansing rules
AUR-006 | Design | Solution blueprint sign-off | Layla Bennett | 2026-04-16 | 2026-04-16 | Planned | High | Milestone | Chicago HQ | AUR-004 | Gate review for build start
AUR-007 | Build | Configuration sprint 1 | Ethan Brooks | 2026-04-17 | 2026-04-30 | Planned | High | Task | Remote | AUR-006 | Core finance modules
AUR-008 | Build | Integration design review | Ava Patel | 2026-04-20 | 2026-04-20 | Planned | Medium | Meeting | Remote | AUR-006 | Interfaces and API readiness
AUR-009 | Build | Training plan draft | Mila Carter | 2026-04-21 | 2026-04-24 | Planned | Medium | Task | Chicago HQ | AUR-006 | End-user curriculum outline
AUR-010 | Quality | Risk review board | Layla Bennett | 2026-04-24 | 2026-04-24 | Planned | High | Meeting | Chicago HQ | AUR-004 | Monthly governance meeting
AUR-011 | Quality | Mock migration rehearsal | Priya Nasser | 2026-05-06 | 2026-05-08 | Planned | High | Task | Dallas DC | AUR-007 | Dry run with sample data
AUR-012 | Deployment | Go-live readiness gate | Layla Bennett | 2026-06-18 | 2026-06-18 | Planned | High | Milestone | Chicago HQ | AUR-011 | All workstreams approve readiness
Team Allocation | [6 empty] | Holiday & Non-Working Days
Team Member | Role | Workstream | Base Location | Availability % | Manager |  | Date | Holiday | Region | Impacted Team | Work Status
Layla Bennett | Senior Project Manager | PMO | Chicago | 100 | Elena Ward |  | 2026-04-10 | Spring Office Closure | US | All | No Work
Marcus Hale | Business Analyst Lead | Planning | Chicago | 80 | Layla Bennett |  | 2026-05-25 | Memorial Day | US | All | No Work
Sofia Ramirez | Change Manager | Change | Remote | 60 | Layla Bennett |  | 2026-06-19 | Juneteenth | US | All | No Work
Noah Chen | Process Architect | Design | Chicago | 100 | Layla Bennett
Priya Nasser | Data Migration Lead | Data | Dallas | 90 | Layla Bennett
Ethan Brooks | ERP Config Lead | Build | Remote | 100 | Layla Bennett
Ava Patel | Integration Manager | Technology | Remote | 75 | Layla Bennett
Mila Carter | Training Lead | Adoption | Chicago | 50 | Sofia Ramirez
Note on B11: Change this to the first day of the month you want to present on the main calendar.
Note on G15: Use the dropdown for consistency.
Note on H15: Use the dropdown for consistency.
Note on I15: Use the dropdown for consistency.

## Instructions
HOW TO USE THIS PROJECT CALENDAR TEMPLATE
Built for PMO reporting, steering committee reviews, and weekly operating rhythm
| 1. Start in Data Entry |  | Update the control section with your project name, company, manager, location, start/end dates and the reporting month shown on the calendar.
| 2. Maintain the Task Register |  | Add one line per task, meeting, milestone or holiday. Complete the dropdowns for Status, Priority and Type so the main template stays consistent.
| 3. Review the Main Template |  | Use the dashboard view for weekly reviews: it shows project context, KPIs, a monthly calendar, a 60-day schedule and milestone tracker.
| 4. Refresh the Calendar Manually |  | The provided month is a polished example for April 2026. Duplicate the layout for the next month or replace the example notes with your own monthly highlights.
| 5. Track Realistic Constraints |  | Capture holidays, office closures and leave days in the Holiday section so dates and resource expectations stay realistic.
| 6. Use It in Governance |  | Present the main sheet in sponsor meetings, PMO updates, risk reviews and portfolio status packs.
Color System Used
| #2F5597 / #1F3A5F | Headings, banners, navigation
| #548235 / #70AD47 / #92D050 | Progress, success, active project health
| #ED7D31 / #FFC000 | Milestones, cautions, focus areas
| #C00000 | Escalation, overdue items, critical flags
| #4472C4 | Input / linked information and secondary accents
Hypothetical scenario used in this workbook: Northbridge Horizon Consulting delivering the Aurora Nexus ERP Rollout for Sterling Retail Group.