## Project Charter
PROJECT CHARTER
Executive summary and formal authorization for project initiation | [6 empty] | Prepared for BluePeak Infrastructure Ltd.
Project |  |  |  | Sponsor |  |  | Project Manager | Status
Aurora ERP Modernization Program |  |  |  | Elena Marquez, COO |  |  | Daniel Reed, Sr. PMO Lead | Amber
PROJECT OVERVIEW
Company |  |  | Project Code |  | Business Unit |  | Location | Target Go-Live
BluePeak Infrastructure Ltd. |  |  | AUR-ERP-26 |  | Operations & Finance |  | Chicago, Illinois | 2026-11-16
BUSINESS CASE & STRATEGIC ALIGNMENT
Business Need |  |  |  |  | Project Purpose
Legacy ERP tools across finance, procurement, and warehouse operations create duplicate data, slow month-end close, and limit real-time reporting. |  |  |  |  | Unify planning, procurement, finance, and inventory management in a single cloud ERP platform to improve controls, visibility, and scalability.
Objectives | [5 empty] | Success Criteria
Reduce month-end close from 10 days to 4 days; improve inventory accuracy to 98.5%; retire 5 legacy applications; enable executive dashboards. | [5 empty] | ERP deployed on time and within ±5% budget, adoption exceeds 90% for target users, close cycle reaches 4 days by Quarter 1 post go-live.
SCOPE & DELIVERABLES
In Scope | [5 empty] | Out of Scope
ERP core finance, procurement, inventory, supplier portal integration, data migration, training, reporting, and change management. | [5 empty] | CRM redesign, manufacturing execution system replacement, and global HRIS transformation.
TIMELINE, BUDGET & PERFORMANCE SNAPSHOT
Planned Budget |  |  | Forecast Budget |  |  | Budget Variance |  | Priority
1630000 |  |  | 1657500 |  |  | 27500 |  | High
Milestone Roadmap | [6 empty] | Delivery Health
Milestone | Date | Status |  |  |  |  | Schedule Health | On Plan
Project Kickoff | 2026-04-06 | Completed
Solution Design Sign-off | 2026-05-22 | On Track |  |  |  |  | Cost Health | Controlled
Build & Configuration Complete | 2026-07-31 | On Track
System Integration Testing | 2026-08-17 | Planned |  |  |  |  | Adoption Readiness | Developing
User Acceptance Testing | 2026-09-21 | Planned
Training & Change Readiness | 2026-10-19 | Planned |  |  |  |  | Data Readiness | Early cleanse in progress
Go-Live | 2026-11-16 | Planned
Hypercare Exit | 2026-12-18 | Planned |  |  |  |  | Governance Cadence | Weekly + monthly steering
STAKEHOLDERS, RISKS & FORMAL APPROVAL
Key Stakeholders | [5 empty] | Top Risks / Assumptions / Constraints
Stakeholder | Role | Influence |  |  |  | Type | Statement |  | Rating
Elena Marquez | Executive Sponsor | High |  |  |  | Risk | Data cleansing effort may exceed plan due to inconsistent vendor master records. |  | High
Nina Patel | Finance Director | High |  |  |  | Risk | Business SMEs may have limited availability during quarter-end close cycles. |  | Medium
Marcus Liu | IT Applications Lead | High |  |  |  | Assumption | Implementation partner staffing remains stable through testing and go-live. |  | Medium
Sofia Bennett | Warehouse Ops Manager | Medium |  |  |  | Constraint | Go-live must occur after peak season freeze ends and before year-end audit window. |  | High
Priya Shah | Change Manager | Medium
AUTHORIZATION & SIGN-OFF
Prepared By |  |  |  | Reviewed By |  |  | Approved By
Daniel Reed, Sr. PMO Lead |  |  |  | Nina Patel, Finance Director |  |  | Elena Marquez, COO
Approval Date |  |  | 2026-04-02 |  |  | This charter authorizes initiation of the Aurora ERP Modernization Program and aligns executive sponsorship, funding, scope, and governance.
Sample scenario included for demonstration: BluePeak Infrastructure Ltd. — Aurora ERP Modernization Program.

## Data Entry
PROJECT CHARTER — DATA ENTRY & SOURCE INPUTS
Edit highlighted input cells only. The main charter sheet populates automatically from this page.
1. PROJECT IDENTITY
Company Name | BluePeak Infrastructure Ltd.
Project Name | Aurora ERP Modernization Program
Project Code | AUR-ERP-26
Project Sponsor | Elena Marquez, COO
Project Manager | Daniel Reed, Sr. PMO Lead
Business Unit | Operations & Finance
Primary Location | Chicago, Illinois
Target Go-Live Date | 2026-11-16
RAG Status | Amber
Project Priority | High
2. STRATEGIC CASE & CHARTER NARRATIVE
Business Need | Legacy ERP tools across finance, procurement, and warehouse operations create duplicate data, slow month-end close, and limit real-time reporting.
Project Purpose | Unify planning, procurement, finance, and inventory management in a single cloud ERP platform to improve controls, visibility, and scalability.
Objectives | Reduce month-end close from 10 days to 4 days; improve inventory accuracy to 98.5%; retire 5 legacy applications; enable executive dashboards.
In Scope | ERP core finance, procurement, inventory, supplier portal integration, data migration, training, reporting, and change management.
Out of Scope | CRM redesign, manufacturing execution system replacement, and global HRIS transformation.
Success Criteria | ERP deployed on time and within ±5% budget, adoption exceeds 90% for target users, close cycle reaches 4 days by Quarter 1 post go-live.
3. HIGH-LEVEL TIMELINE & MILESTONES
Milestone | Date | Status
Project Kickoff | 2026-04-06 | Completed
Solution Design Sign-off | 2026-05-22 | On Track
Build & Configuration Complete | 2026-07-31 | On Track
System Integration Testing | 2026-08-17 | Planned
User Acceptance Testing | 2026-09-21 | Planned
Training & Change Readiness | 2026-10-19 | Planned
Go-Live | 2026-11-16 | Planned
Hypercare Exit | 2026-12-18 | Planned
4. BUDGET SUMMARY
Cost Category | Planned Budget | Forecast | Variance
Software Licenses | 420000 | 420000 | 0
Implementation Partner | 680000 | 702500 | 22500
Internal Project Team | 310000 | 298000 | -12000
Training & Change | 95000 | 112000 | 17000
Contingency Reserve | 125000 | 125000 | 0
Total | 1630000 | 1657500 | 27500
5. STAKEHOLDERS & GOVERNANCE
Stakeholder | Role | Department | Influence | Engagement Plan
Elena Marquez | Executive Sponsor | Operations | High | Monthly steering committee
Nina Patel | Finance Director | Finance | High | Weekly project review
Marcus Liu | IT Applications Lead | Technology | High | Daily delivery standup
Sofia Bennett | Warehouse Ops Manager | Supply Chain | Medium | Biweekly readiness workshop
Priya Shah | Change Manager | PMO | Medium | Training & communications cadence
6. KEY RISKS, ASSUMPTIONS & CONSTRAINTS
Type | Statement | Owner | Rating | Response
Risk | Data cleansing effort may exceed plan due to inconsistent vendor master records. | Daniel Reed | High | Run early mock migration and dedicate data stewards.
Risk | Business SMEs may have limited availability during quarter-end close cycles. | Nina Patel | Medium | Lock calendar coverage and use backup SMEs.
Assumption | Implementation partner staffing remains stable through testing and go-live. | Elena Marquez | Medium | Monitor through weekly commercial review.
Constraint | Go-live must occur after peak season freeze ends and before year-end audit window. | Steering Committee | High | Preserve date discipline and track dependencies.
7. APPROVALS
Prepared By | Daniel Reed, Sr. PMO Lead
Reviewed By | Nina Patel, Finance Director
Approved By | Elena Marquez, COO
Approval Date | 2026-04-02

## Instructions
HOW TO USE THIS PROJECT CHARTER TEMPLATE
Template Purpose
Use this workbook to define, authorize, and communicate a project's purpose, scope, funding, milestones, governance, risks, and approval path. It is designed for steering committees, PMOs, sponsors, and delivery teams.
Recommended Workflow
1 | Go to the Data Entry sheet and replace the sample data in highlighted cells.
2 | Keep milestone dates, budget lines, stakeholders, and risks current.
3 | Review the Project Charter sheet for executive-ready presentation quality.
4 | Print or export the Project Charter sheet for approvals and governance packs.
What the Charter Explains
Project overview | Who owns the initiative, where it happens, and when it targets go-live.
Business case | Why the project matters and what operational or strategic problem it solves.
Objectives | What measurable outcomes the initiative must achieve.
Scope boundaries | What is included and intentionally excluded.
Timeline | What key milestones determine delivery success.
Funding | What budget is approved and where forecast risk is emerging.
Governance | Who the key stakeholders are and how decisions are made.
Risk posture | What assumptions, constraints, and major risks need active management.
Authorization | Who prepared, reviewed, and approved the work.
Color Guide
Title / authority banner
Section headers
Information blocks and key headings
Approvals / positive governance areas
Success / healthy outlook
Warnings / attention / out-of-scope
Risks / critical focus
Totals / highlights
Professional Tips from a Senior Project Manager
Keep the charter concise but decisive. If a topic needs operational detail, reference a separate project plan. Use measurable objectives, explicitly state out-of-scope items, and secure sponsor approval before detailed planning begins. Refresh the charter if funding, timeline, or scope materially changes.