## Main Template
Project Cost Control
Executive dashboard for budget, actuals, commitments, forecast, cost performance and corrective actions
Project Overview |  | BAC / Approved Budget |  | Actual Cost |  | Committed Cost |  | Remaining Balance |  | Estimate at Completion (EAC) |  | Control Status
Project Name | Harbor Point Innovation Hub Fit-Out | 1088000 |  | 568000 |  | 196000 |  | 324000 |  | 995000 |  | WITHIN BUDGET
Project ID | VM-HP-2026-041 | [10 empty] | FORECAST OK
Company | Vertex Meridian Solutions
Client / Sponsor | Northbridge Health Systems | Cost Performance Indicators |  |  |  | Budget Utilization Snapshot
Project Manager | Samantha Reeves, PMP | Budget at Completion (BAC) | 1088000 |  |  | Budget Used % | 52.21% | PM Note: This dashboard is designed to flag spend pressure early, separate committed cost from paid cost, and provide a realistic forecast at completion using ETC plus live transactions.
Location | Rivergate Business Park, Austin | Estimate at Completion (EAC) | 995000 |  |  | Committed % | 18.01%
Start Date | 2026-01-05 | Variance at Completion (VAC) | 93000 |  |  | Forecast % of BAC | 91.45%
Finish Date | 2026-12-18 | Earned Value (EV) | 769850 |  |  | Contingency Draw | 12000
|  | Cost Variance (CV = EV - AC) | 0 |  |  | Open Commitments | 7
|  | Cost Performance Index (CPI) | 0
Category Cost Control Matrix
WBS | Category | Baseline Budget | Actual Cost | Committed Cost | ETC Forecast | Remaining Budget | % Complete | Earned Value | EAC | Variance to BAC | Variance % | Status
WBS-01 | Design & Engineering | 125000 | 54000 | 0 | 18000 | 71000 | 95% | 118750 | 72000 | 53000 | 42.4% | On Track
WBS-02 | Permits & Compliance | 48000 | 13000 | 9000 | 5000 | 26000 | 90% | 43200 | 27000 | 21000 | 43.75% | On Track
WBS-03 | Procurement | 265000 | 70000 | 124000 | 42000 | 71000 | 72% | 190800 | 236000 | 29000 | 10.94% | On Track
WBS-04 | Site Preparation | 78000 | 44000 | 0 | 4000 | 34000 | 100% | 78000 | 48000 | 30000 | 38.46% | On Track
WBS-05 | Construction | 420000 | 361000 | 28000 | 93000 | 31000 | 68% | 285600 | 482000 | -62000 | -14.76% | Intervene
WBS-06 | Testing & Commissioning | 62000 | 20000 | 14000 | 36000 | 28000 | 35% | 21700 | 70000 | -8000 | -12.9% | Intervene
WBS-07 | Training & Handover | 35000 | 6000 | 9000 | 21000 | 20000 | 28% | 9800 | 36000 | -1000 | -2.857% | Watch
WBS-08 | Contingency Reserve | 55000 | 0 | 12000 | 12000 | 43000 | 40% | 22000 | 24000 | 31000 | 56.36% | On Track
Monthly Cost Trend
Month | Baseline Plan | Actual | Committed | Total Exposure | Var vs Plan | Cum Actual | Cum Plan
Jan-26 | 78000 | 25000 | 0 | 25000 | -53000 | 25000 | 78000
Feb-26 | 82000 | 26000 | 48000 | 74000 | -8000 | 51000 | 160000
Mar-26 | 91000 | 77000 | 0 | 77000 | -14000 | 128000 | 251000
Apr-26 | 96000 | 36000 | 28000 | 64000 | -32000 | 164000 | 347000
May-26 | 105000 | 150000 | 0 | 150000 | 45000 | 314000 | 452000
Jun-26 | 110000 | 71000 | 9000 | 80000 | -30000 | 385000 | 562000
Jul-26 | 120000 | 0 | 90000 | 90000 | -30000 | 385000 | 682000
Aug-26 | 108000 | 105000 | 0 | 105000 | -3000 | 490000 | 790000
Sep-26 | 98000 | 11000 | 12000 | 23000 | -75000 | 501000 | 888000
Oct-26 | 83000 | 46000 | 9000 | 55000 | -28000 | 547000 | 971000
Nov-26 | 72000 | 15000 | 0 | 15000 | -57000 | 562000 | 1043000
Dec-26 | 45000 | 6000 | 0 | 6000 | -39000 | 568000 | 1088000
Latest Corrective Actions & Control Commentary
Latest issue |  |  |  | Owner |  | Response
Construction cost trending high due to extended night access |  |  |  | S. Reeves |  | Negotiate blended labor rate and resequence low-risk areas to daytime shifts
All names, locations, suppliers and values are hypothetical for demonstration. Update the Data Entry sheet only; the Main Template sheet is driven by formulas and will refresh automatically in Excel.

## Data Entry
Project Cost Control – Data Entry & Assumptions
Project Setup | [9 empty] | Monthly Baseline Budget Plan
Project Name | Harbor Point Innovation Hub Fit-Out | [7 empty] | Metric | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Project ID | VM-HP-2026-041 | [7 empty] | Baseline Spend Plan | 78000 | 82000 | 91000 | 96000 | 105000 | 110000 | 120000 | 108000 | 98000 | 83000 | 72000 | 45000
Company | Vertex Meridian Solutions
Client / Sponsor | Northbridge Health Systems
Project Manager | Samantha Reeves, PMP
Location | Rivergate Business Park, Austin
Start Date | 2026-01-05
Finish Date | 2026-12-18
Reporting Currency | USD
Category Budget, Forecast & Progress Inputs
WBS Code | Category | Cost Owner | Baseline Budget | ETC Forecast | % Complete | Priority | Control Threshold | Notes
WBS-01 | Design & Engineering | Olivia Chen | 125000 | 18000 | 95% | Medium | 8% | Final snag updates only
WBS-02 | Permits & Compliance | Marco Diaz | 48000 | 5000 | 90% | Low | 5% | Two inspections still open
WBS-03 | Procurement | Lena Foster | 265000 | 42000 | 72% | High | 8% | Furniture and AV balance outstanding
WBS-04 | Site Preparation | Ethan Cole | 78000 | 4000 | 100% | Low | 5% | Closed
WBS-05 | Construction | Nina Patel | 420000 | 93000 | 68% | High | 10% | Night-shift premium under review
WBS-06 | Testing & Commissioning | Grace Morgan | 62000 | 36000 | 35% | Medium | 7% | Lab testing starts in Q3
WBS-07 | Training & Handover | Victor Hale | 35000 | 21000 | 28% | Medium | 7% | Leadership walk-through booked
WBS-08 | Contingency Reserve | Samantha Reeves | 55000 | 12000 | 40% | Critical | 0% | Sponsor approval required for drawdown
Transaction Log (Actual & Committed Cost Entries) | [13 empty] | Actions & Corrective Measures
Date | Month | WBS Code | Category | Cost Type | Vendor | Description | PO / Invoice # | Budget Line | Amount | Status | Approved By | Payment Terms |  | Date | Owner | Issue / Risk | Action
2026-01-08 | Jan-26 | WBS-01 | Design & Engineering | Actual | ArcSphere Studio | Concept design package | INV-1001 | Design | 18000 | Paid | S. Reeves | Net 15 |  | 2026-06-20 | S. Reeves | Construction cost trending high due to extended night access | Negotiate blended labor rate and resequence low-risk areas to daytime shifts
2026-01-19 | Jan-26 | WBS-02 | Permits & Compliance | Actual | CityLine Permits | Zoning filing fees | INV-1012 | Permits | 7000 | Paid | S. Reeves | Due on receipt |  | 2026-07-25 | L. Foster | AV procurement lead time slipped by two weeks | Release hardware in split shipment and prioritize conference rooms first
2026-02-02 | Feb-26 | WBS-04 | Site Preparation | Actual | GroundGrid Works | Selective demolition | INV-1031 | Site Prep | 26000 | Paid | E. Cole | Net 30 |  | 2026-09-18 | N. Patel | Contingency reserve draw requested for productivity loss | Escalate to sponsor for approval and freeze discretionary finishes scope
2026-02-16 | Feb-26 | WBS-03 | Procurement | Committed | Nova Office Supply | Furniture deposit | PO-2040 | Furniture | 48000 | Open | L. Foster | 30/70 |  | 2026-10-20 | G. Morgan | Commissioning plan requires extra witness testing | Combine test windows to reduce repeat vendor mobilization costs
2026-03-03 | Mar-26 | WBS-05 | Construction | Actual | IronPeak Contractors | Partition framing package | INV-1099 | Build | 65000 | Paid | N. Patel | Net 30
2026-03-21 | Mar-26 | WBS-03 | Procurement | Actual | BrightWave AV | AV design retainer | INV-1107 | AV | 12000 | Paid | L. Foster | Net 15
2026-04-12 | Apr-26 | WBS-05 | Construction | Committed | IronPeak Contractors | MEP rough-in change order | CO-1141 | Build | 28000 | Approved | N. Patel | Net 30
2026-04-27 | Apr-26 | WBS-01 | Design & Engineering | Actual | ArcSphere Studio | Detailed IFC drawings | INV-1152 | Design | 36000 | Paid | O. Chen | Net 15
2026-05-14 | May-26 | WBS-03 | Procurement | Actual | Nova Office Supply | Task seating batch 1 | INV-1188 | Furniture | 58000 | Paid | L. Foster | Net 30
2026-05-28 | May-26 | WBS-05 | Construction | Actual | IronPeak Contractors | Drywall and finishes | INV-1205 | Build | 92000 | Paid | N. Patel | Net 30
2026-06-09 | Jun-26 | WBS-02 | Permits & Compliance | Committed | Regency Safety Labs | Air quality certification | PO-1211 | Compliance | 9000 | Open | M. Diaz | Net 20
2026-06-18 | Jun-26 | WBS-05 | Construction | Actual | VoltForge Electrical | Lighting installation | INV-1237 | Build | 71000 | Paid | N. Patel | Net 30
2026-07-07 | Jul-26 | WBS-06 | Testing & Commissioning | Committed | QualiTest Systems | Systems commissioning plan | PO-1270 | Testing | 14000 | Open | G. Morgan | Net 30
2026-07-22 | Jul-26 | WBS-03 | Procurement | Committed | BrightWave AV | AV hardware release | PO-1288 | AV | 76000 | Approved | L. Foster | 40/60
2026-08-05 | Aug-26 | WBS-05 | Construction | Actual | IronPeak Contractors | Ceiling grid and paint | INV-1304 | Build | 87000 | Paid | N. Patel | Net 30
2026-08-19 | Aug-26 | WBS-04 | Site Preparation | Actual | GroundGrid Works | Waste haul and clean-down | INV-1319 | Site Prep | 18000 | Paid | E. Cole | Net 15
2026-09-03 | Sep-26 | WBS-06 | Testing & Commissioning | Actual | QualiTest Systems | Pre-functional tests | INV-1331 | Testing | 11000 | Paid | G. Morgan | Net 20
2026-09-15 | Sep-26 | WBS-08 | Contingency Reserve | Committed | Reserve Draw | Night-shift productivity allowance | CR-901 | Contingency | 12000 | Reserved | S. Reeves | N/A
2026-10-01 | Oct-26 | WBS-07 | Training & Handover | Committed | EnablePath Learning | End-user training package | PO-1360 | Training | 9000 | Open | V. Hale | Net 30
2026-10-17 | Oct-26 | WBS-05 | Construction | Actual | VoltForge Electrical | Controls integration | INV-1384 | Build | 46000 | Paid | N. Patel | Net 30
2026-11-06 | Nov-26 | WBS-06 | Testing & Commissioning | Actual | QualiTest Systems | Integrated systems testing | INV-1412 | Testing | 9000 | Paid | G. Morgan | Net 20
2026-11-24 | Nov-26 | WBS-07 | Training & Handover | Actual | EnablePath Learning | Pilot training wave | INV-1426 | Training | 6000 | Paid | V. Hale | Net 15
2026-12-08 | Dec-26 | WBS-02 | Permits & Compliance | Actual | CityLine Permits | Occupancy certificate fee | INV-1455 | Permits | 6000 | Paid | M. Diaz | Due on receipt
Note on D16: Baseline approved budget by category. Hypothetical values for demonstration only.
Note on E16: ETC = Estimate to Complete. Enter the best current forecast of remaining spend required.
Note on F16: Physical progress estimate used to derive earned value style indicators.

## Instructions
Instructions – How to Use This Project Cost Control Template
Step | Area | Guidance | Owner
1 | Project setup | Go to the Data Entry sheet and update the project profile in cells A5:B13. These details feed the dashboard header and overview section automatically. | PMO
2 | Budget inputs | Update category budgets, ETC forecasts, percent complete and thresholds in the Budget Inputs table (A16:I24). BAC, EAC, EV, VAC and status are derived from this section. | Cost Controller
3 | Monthly plan | Replace the baseline monthly budget plan in J5:V6 with your approved spend plan. The Monthly Cost Trend chart on the main sheet reads from this line. | Project Controls
4 | Transactions | Add every paid invoice as Cost Type = Actual and every approved PO/commitment as Cost Type = Committed in the transaction log starting at row 29. | Cost Controller
5 | Variance review | On the Main Template, review category variance to BAC, remaining budget, and red/yellow status highlights. Intervene when a category moves negative beyond tolerance. | Senior PM
6 | Forecasting | Keep ETC Forecast realistic. EAC = Actual + Committed + ETC. This makes the template useful for forward-looking cost control, not just historic tracking. | Project Manager
7 | Corrective actions | Document cost issues and actions in the Actions & Corrective Measures block on the Data Entry sheet. The latest action is surfaced on the dashboard for executive reporting. | Project Manager
8 | What the template explains | This workbook covers project overview, approved budget, actual costs, commitments, remaining balance, monthly tracking, variance, forecast/EAC, earned value style indicators, alerts, and corrective actions. | Executive Team
Color Legend
Dark blue | Section headers and executive bands
Blue | Primary KPI budget card and major reference areas
Green shades | Health, performance, progress and positive control states
Orange / gold | Spend snapshots, planning emphasis and caution areas
Red | Issues, corrective actions and overrun warnings
Professional recommendation: Protect formula cells on the Main Template before sharing the workbook broadly, and limit edits to the Data Entry sheet. In live use, review actuals weekly and refresh ETC at least monthly during formal cost reporting.