## Main Estimate
PROJECT COST ESTIMATE
Senior Project Manager Edition ¦ Built for realistic planning, cost control, approvals, and stakeholder review
Project Name | Apollo Nexus Distribution Center |  |  |  |  | Estimate Date | 28-Mar-2026
Company | Northwind Urban Systems Ltd. |  |  |  |  | Currency | USD
Client | Summit Retail Group |  |  |  |  | Tax Rate | 8.25%
Project Manager | Avery Bennett, PMP |  |  |  |  | Contingency Rate | 7.5%
Location | Austin, Texas |  |  |  |  | Schedule Buffer | 12
Base Cost |  |  | Contingency |  |  | Tax |  |  | Grand Total
162150 |  |  | 9688.5 |  |  | 10692.6187 |  |  | 182531.1187
COST BREAKDOWN STRUCTURE (WHAT THIS TEMPLATE EXPLAINS) | [7 empty] | TOP COST DRIVERS
Area Explained | Description | Base Cost | Contingency | Tax | Total | % of Total | Status | Cost Item | Owner/Vendor | Total | % of Total
Labor Cost Estimation | Hours x rates for PM, design, QA, training, and specialist resources | 39500 | 2731 | 0 | 42231 | 23.14% | Included | Warehouse layout design | Mason & Vale Studio | 21384 | 11.72%
Material Cost Estimation | Physical materials and supply packages required for project delivery | 80000 | 4800 | 6996 | 91796 | 50.29% | Included | Structural steel package | RedRiver Industrial Supply | 91796 | 50.29%
Equipment & Tools | Rented or purchased equipment, software tools, and temporary assets | 19650 | 967.5 | 1700.9437 | 22318.4437 | 12.23% | Included | Warehouse management licenses | BluePeak Software | 15888.3937 | 8.704%
Vendor / Subcontractor Cost | Third-party services, advisory support, and implementation packages | 7000 | 350 | 606.375 | 7956.375 | 4.359% | Included | Hypercare support | VectorOps Advisory | 7956.375 | 4.359%
Direct Costs | Items directly attributable to project execution | 99650 | 5767.5 | 8696.9438 | 114114.4438 | 62.52% | Included
Indirect Costs | Travel, overhead, admin, insurance, and enablement expenses | 16000 | 840 | 1389.3 | 18229.3 | 9.987% | Included
Contingency Reserve | Risk-based allowance for uncertainty and minor scope volatility | 0 | 9688.5 | 0 | 9688.5 | 5.308% | Included
Tax & Additional Charges | Applicable taxes on selected taxable items | 0 | 0 | 10692.6187 | 10692.6187 | 5.858% | Included
ASSUMPTIONS, CONTROLS & APPROVALS
Key Assumption 1 | Estimate based on current market rates in Austin, Texas as of Mar 28, 2026.
Key Assumption 2 | Labor rates assume standard 8-hour workdays and normal weekday scheduling.
Key Assumption 3 | Tax applies only to line items marked Taxable? = Yes on the Data Entry sheet.
Key Assumption 4 | Contingency is intended for uncertainty, not approved scope expansion.
Prepared By | Avery Bennett, PMP
Reviewed By | Jordan Sinclair, Director PMO
Approved By | Morgan Hale, CFO
Approval Date | 2026-04-15

## Data Entry
PROJECT COST ESTIMATE TEMPLATE DATA ENTRY
Project Name | Apollo Nexus Distribution Center |  | Enter or update project assumptions and line-item costs below. Blue-font cells are intended for user edits. Formulas and summaries on the Main Estimate sheet update automatically.
Company | Northwind Urban Systems Ltd.
Client | Summit Retail Group
Project Manager | Avery Bennett, PMP
Project Location | Austin, Texas
Estimate Date | 28-Mar-2026
Currency | USD
Tax Rate | 8.25%
Contingency Rate | 7.5%
Schedule Buffer Days | 12
ID | Cost Category | Workstream | Cost Type | Cost Item | Vendor / Resource | Qty | Unit | Unit Rate | Base Cost | Risk % | Contingency $ | Taxable? | Tax $ | Total Cost
1 | Initiation & Planning | Project Management | Labor | Project planning & kickoff | Avery Bennett | 80 | Hours | 145 | 11600 | 5% | 580 | No | 0 | 12180
2 | Design & Engineering | Architecture | Labor | Warehouse layout design | Mason & Vale Studio | 120 | Hours | 165 | 19800 | 8% | 1584 | No | 0 | 21384
3 | Procurement | Materials | Direct | Structural steel package | RedRiver Industrial Supply | 25 | Tons | 3200 | 80000 | 6% | 4800 | Yes | 6996 | 91796
4 | Construction | Equipment | Direct | Forklift rental | Lone Star Fleet Services | 3 | Months | 1800 | 5400 | 10% | 540 | Yes | 490.05 | 6430.05
5 | Technology | Software | Direct | Warehouse management licenses | BluePeak Software | 15 | Licenses | 950 | 14250 | 3% | 427.5 | Yes | 1210.8937 | 15888.3937
6 | Quality & Testing | Testing | Labor | Commissioning & QA | Harbor QA Partners | 60 | Hours | 135 | 8100 | 7% | 567 | No | 0 | 8667
7 | Training & Change | Training | Indirect | Supervisor training program | Crestline Learning Co. | 4 | Sessions | 1250 | 5000 | 4% | 200 | Yes | 429 | 5629
8 | Deployment | Travel | Indirect | Go-live travel & lodging | Various | 1 | Lot | 4200 | 4200 | 12% | 504 | Yes | 388.08 | 5092.08
9 | Post Go-Live | Support | Vendor | Hypercare support | VectorOps Advisory | 2 | Weeks | 3500 | 7000 | 5% | 350 | Yes | 606.375 | 7956.375
10 | Project Controls | Admin Overhead | Indirect | Permits, signage & insurance | Civic Compliance Bureau | 1 | Lot | 6800 | 6800 | 2% | 136 | Yes | 572.22 | 7508.22
AUTOMATED CATEGORY SUMMARY
Type | Base Cost | Contingency | Tax | Total | % of Total |  | Taxable Total | 140300.1187
Labor | 39500 | 2731 | 0 | 42231 | 23.14% |  | Non-Taxable Total | 42231
Direct | 99650 | 5767.5 | 8696.9438 | 114114.4438 | 62.52%
Indirect | 16000 | 840 | 1389.3 | 18229.3 | 9.987%
Vendor | 7000 | 350 | 606.375 | 7956.375 | 4.359%
Note on B9: Input current sales/use tax applicable to taxable costs.
Note on B10: Input contingency reserve rate to cover uncertainty and identified risks.

## Instructions
HOW TO USE THIS PROJECT COST ESTIMATE TEMPLATE
Designed by a Senior Project Manager perspective for realistic planning, governance, and executive review
Step | What to do | Why it matters
1 | Update the project profile on the Data Entry sheet (name, company, client, PM, location, date, tax, contingency). | These assumptions flow into the main estimate and establish the financial context.
2 | Review or replace the hypothetical line items in rows 14–200 on the Data Entry sheet. | Each line item represents a realistic cost driver tied to scope, workstream, and delivery method.
3 | Enter Qty and Unit Rate for each cost item. Base Cost, Contingency, Tax, and Total calculate automatically. | This reduces manual errors and keeps the estimate auditable.
4 | Use the drop-down fields for Cost Category, Cost Type, Unit, and Taxable?. | Standardized classifications make reporting cleaner and executive summaries more reliable.
5 | Go to Main Estimate to review KPIs, cost breakdown structure, major cost drivers, and charts. | This sheet is intended for stakeholder review, approvals, and budget discussions.
6 | Tailor contingency based on project uncertainty, design maturity, procurement risk, and schedule complexity. | High-risk projects should carry stronger reserves than routine repeatable work.
7 | Document assumptions, exclusions, and pricing validity before circulating the estimate. | A strong estimate is not only numeric—it clearly explains its basis.
8 | Capture Prepared By, Reviewed By, Approved By, and Approval Date before baseline sign-off. | This supports governance and creates a formal reference point for later cost control.
COLOR & USAGE LEGEND
Blue Font Input | Cells intended for user edits or assumptions
Dark Blue Header | Primary navigation, branding, and executive header sections
Green Sections | Operational categories, summaries, and instructional areas
Orange Sections | Assumptions, governance, and caution/review areas
Red Sections | Critical review zones such as top cost drivers or key flags
Gold Highlights | High-value items or fields that deserve management attention
WHAT THIS TEMPLATE EXPLAINS
• | Project information and estimate controls
• | Cost breakdown structure by category and workstream
• | Labor, material, equipment, vendor, direct, and indirect costs
• | Risk-based contingency reserve and tax treatment
• | Major cost drivers, executive summary KPIs, and approval workflow