## Main Tracker
Project Cost Tracker
Budget control, cost performance, forecast visibility, payment exposure, and phase health in one senior-PM dashboard.
Project | Northwind Civic Center Expansion | Project ID | NCCE-2026-041 | Company | BluePeak Infrastructure Ltd. | Client | Harborview Municipal Authority | Project Manager | Avery Bennett
Location | Riverton, Oregon | Start Date | 2026-01-12 | Planned End Date | 2026-11-27 | Report Date | 2026-03-28 |  |  | Overall Cost Status | GREEN
Total Budget |  |  | Actual Cost |  |  | Committed Cost |  |  | Forecast at Completion
925500 |  |  | 469150 |  |  | 133050 |  |  | 890150
Budget Variance |  |  | Variance % |  |  | Paid to Date |  |  | Outstanding Balance
-35350 |  |  | -3.82% |  |  | 32000 |  |  | 74250
Category Cost Performance | [8 empty] | Phase Summary
Category | Budget | Actual | Committed | ETC | Forecast | Variance | Variance % | Status | Phase | Actual | Forecast
Labor | 265000 | 148400 | 22400 | 101500 | 272300 | 7300 | 2.755% | Green | Initiation | 48750 | 52000
Materials | 185000 | 96350 | 40750 | 43800 | 180900 | -4100 | -2.216% | Green | Design | 91300 | 97500
Equipment | 118000 | 69200 | 12000 | 35750 | 116950 | -1050 | -0.8898% | Green | Procurement | 88500 | 181500
Subcontractors | 222000 | 125000 | 51000 | 42000 | 218000 | -4000 | -1.802% | Green | Build | 240600 | 404200
Travel & Logistics | 28000 | 14600 | 2200 | 9200 | 26000 | -2000 | -7.143% | Amber | Testing & Handover | 0 | 154950
Permits & Compliance | 19500 | 10400 | 1200 | 6500 | 18100 | -1400 | -7.179% | Amber | TOTAL | 469150 | 890150
Training & Handover | 24000 | 5200 | 3500 | 13200 | 21900 | -2100 | -8.75% | Amber
Contingency Reserve | 64000 | 0 | 0 | 36000 | 36000 | -28000 | -43.75% | Red | Vendors paid to date: $32,000 Open balance awaiting payment: $74,250 Highest current exposure: Civic Design Studio
TOTAL | 925500 | 469150 | 133050 | 287950 | 890150 | -35350 | -3.82% | GREEN

## Data Entry
Project Cost Tracker — Data Entry & Assumptions
Update this sheet only. The Main Tracker reads from here automatically.
1) Project Profile
Project Name | Northwind Civic Center Expansion
Project ID | NCCE-2026-041
Company | BluePeak Infrastructure Ltd.
Client | Harborview Municipal Authority
Project Manager | Avery Bennett
Project Sponsor | Sophia Clarke
Location | Riverton, Oregon
Start Date | 2026-01-12
Planned End Date | 2026-11-27
Report Date | 2026-03-28
Currency | USD
Contingency % | 8%
Amber Variance Threshold % | 5%
Red Variance Threshold % | 10%
2) Cost Categories — Budget, Actual, Commitment, Forecast
Category | Owner | Budget | Actual to Date | Committed | ETC | Forecast at Completion | Variance to Budget | Status
Labor | PMO | 265000 | 148400 | 22400 | 101500 | 272300 | 7300 | Green
Materials | Procurement | 185000 | 96350 | 40750 | 43800 | 180900 | -4100 | Green
Equipment | Site Ops | 118000 | 69200 | 12000 | 35750 | 116950 | -1050 | Green
Subcontractors | Delivery | 222000 | 125000 | 51000 | 42000 | 218000 | -4000 | Green
Travel & Logistics | PMO | 28000 | 14600 | 2200 | 9200 | 26000 | -2000 | Amber
Permits & Compliance | Legal | 19500 | 10400 | 1200 | 6500 | 18100 | -1400 | Amber
Training & Handover | HR | 24000 | 5200 | 3500 | 13200 | 21900 | -2100 | Amber
Contingency Reserve | Sponsor | 64000 | 0 | 0 | 36000 | 36000 | -28000 | Red
TOTAL |  | 925500 | 469150 | 133050 | 287950 | 890150 | -35350 | Green
3) Phase-Level Plan
Phase | Planned Start | Planned Finish | Phase Budget | Actual to Date | Forecast | Phase Lead
Initiation | 2026-01-12 | 2026-01-30 | 52000 | 48750 | 52000 | Avery Bennett
Design | 2026-02-02 | 2026-03-20 | 96000 | 91300 | 97500 | Mia Torres
Procurement | 2026-03-09 | 2026-05-08 | 174000 | 88500 | 181500 | Noah Price
Build | 2026-04-06 | 2026-09-18 | 455000 | 240600 | 404200 | Lena Brooks
Testing & Handover | 2026-09-21 | 2026-11-27 | 148500 | 0 | 154950 | Ethan Cole
TOTAL |  |  | 925500 | 469150 | 890150
4) Invoice & Payment Register
Invoice No. | Vendor | Category | Invoice Date | Due Date | Amount | Paid Amount | Balance | Payment Status
INV-26031 | Atlas Steel Co. | Materials | 2026-03-03 | 2026-04-02 | 28150 | 10000 | 18150 | Part Paid
INV-26042 | Pioneer Rentals | Equipment | 2026-03-06 | 2026-03-30 | 16400 | 16400 | 0 | Paid
INV-26056 | Civic Design Studio | Subcontractors | 2026-03-11 | 2026-04-10 | 32250 | 0 | 32250 | Due
INV-26077 | Skyline Logistics | Travel & Logistics | 2026-03-15 | 2026-03-29 | 4200 | 0 | 4200 | Due
INV-26084 | Northstar Compliance | Permits & Compliance | 2026-03-18 | 2026-04-17 | 5600 | 5600 | 0 | Paid
INV-26091 | ForgeWorks LLC | Materials | 2026-03-21 | 2026-04-20 | 19650 | 0 | 19650 | Approved
Note on B5: Fictional sample project created for demonstration.
Note on C23: Approved budget input — replace with your baseline budget.
Note on D23: Actual incurred cost to date — typically sourced from ERP/AP cost reports.

## Instructions
Instructions & Operating Guide
How to use this workbook like a disciplined project controls lead.
1 | Purpose | This workbook tracks project financial performance across the full control cycle: approved budget, actual cost, committed cost, estimate to complete (ETC), forecast at completion (FAC), cost variance, payment exposure, and phase-level health.
2 | Where to update | Enter changes only on the Data Entry sheet. The Main Tracker is formula-driven and designed for executive reporting.
3 | Project profile | Update the project name, ID, company, client, location, manager, sponsor, dates, currency, and thresholds in rows 5:18 of Data Entry.
4 | Category costs | Update the category table in Data Entry rows 23:30. Budget = approved amount. Actual = incurred cost. Committed = contracted/not yet paid. ETC = expected remaining cost. FAC is calculated automatically as Actual + Committed + ETC.
5 | Status logic | Green = variance below amber threshold. Amber = variance at or above amber threshold. Red = variance at or above red threshold. Thresholds are user-editable in Data Entry.
6 | Phase planning | Use the phase section to monitor where the money is being consumed across Initiation, Design, Procurement, Build, and Handover.
7 | Invoices & payments | Maintain invoice number, vendor, category, dates, amount, paid amount, balance, and payment status in the register. The dashboard summarizes paid value and outstanding exposure.
8 | Recommended governance cadence | Update actuals weekly, commitments when POs/contracts are approved, ETC during forecast reviews, and payment status whenever AP confirms settlement.
9 | Good PM practice | Use this tracker in monthly cost review meetings, governance packs, contractor reviews, and change-control sessions. Escalate items that move into amber/red before they become overruns.
10 | Color legend | Primary headers: #2F5597 and #1F3A5F ¦ Healthy: #70AD47 / #92D050 ¦ Watch: #FFC000 / #ED7D31 ¦ Risk: #C00000 ¦ Accent blue: #4472C4.
11 | Sample project context | This workbook includes realistic fictional content for Northwind Civic Center Expansion, delivered by BluePeak Infrastructure Ltd. for Harborview Municipal Authority in Riverton, Oregon.