## Main Template
Cost Trend Analysis
Professional PMO cost control dashboard | [9 empty] | Hypothetical case ¦ Prepared for portfolio review
Project Summary |  |  |  |  | Executive Cost Performance Snapshot
Project Name | Aurora Nexus ERP Rollout |  |  |  | Baseline Budget |  | 1661400 |  | Forecast at Completion |  | 1874395
Company | Northwind Meridian Holdings |  |  |  | Actual Cost to Date |  | 1765300 |  | Remaining Budget |  | -103900
Client | Helios Retail Group |  |  |  | Cost Variance |  | 103900 |  | Burn Rate / Month |  | 147108.3333
Project Manager | Ava Sinclair |  |  |  | Variance % |  | 6.254% |  | Cost Status |  | Monitor Closely
Location | Chicago, Illinois
Currency | USD
Monthly Cost Trend Analysis
Month | Phase | Budget Total | Actual Total | Variance | Variance % | Cumulative Budget | Cumulative Actual | Forecast EAC | Labor % | Material % | Vendor % | Travel % | Overhead %
Jan-2026 | Initiation | 94200 | 100000 | 5800 | 6.157% | 94200 | 100000 | 106090 | 52% | 18% | 12% | 3% | 7%
Feb-2026 | Planning | 123000 | 130500 | 7500 | 6.098% | 217200 | 230500 | 238375 | 52.11% | 18.39% | 13.79% | 2.682% | 5.747%
Mar-2026 | Planning | 123200 | 130800 | 7600 | 6.169% | 340400 | 361300 | 369280 | 54.28% | 16.82% | 12.23% | 3.44% | 5.963%
Apr-2026 | Execution | 159200 | 169200 | 10000 | 6.281% | 499600 | 530500 | 541000 | 49.65% | 18.32% | 16.55% | 3.546% | 4.846%
May-2026 | Execution | 173300 | 184400 | 11100 | 6.405% | 672900 | 714900 | 726555 | 49.35% | 19.52% | 16.27% | 3.796% | 4.555%
Jun-2026 | Execution | 187000 | 199100 | 12100 | 6.471% | 859900 | 914000 | 926705 | 47.71% | 21.09% | 16.07% | 3.265% | 4.319%
Jul-2026 | Execution | 186500 | 198300 | 11800 | 6.327% | 1046400 | 1112300 | 1124690 | 49.42% | 19.16% | 16.64% | 2.774% | 4.438%
Aug-2026 | Monitoring | 160500 | 170600 | 10100 | 6.293% | 1206900 | 1282900 | 1293505 | 51% | 19.93% | 14.07% | 2.931% | 5.041%
Sep-2026 | Monitoring | 142900 | 151900 | 9000 | 6.298% | 1349800 | 1434800 | 1444250 | 52.01% | 19.09% | 14.48% | 2.962% | 5.53%
Oct-2026 | Monitoring | 131100 | 139200 | 8100 | 6.178% | 1480900 | 1574000 | 1582505 | 51.72% | 18.68% | 15.09% | 2.874% | 5.891%
Nov-2026 | Closing | 103800 | 110000 | 6200 | 5.973% | 1584700 | 1684000 | 1690510 | 55.45% | 16.36% | 12.73% | 2.727% | 7.273%
Dec-2026 | Closing | 76700 | 81300 | 4600 | 5.997% | 1661400 | 1765300 | 1770130 | 54.12% | 14.76% | 13.53% | 3.075% | 9.594%
TOTAL |  | 1661400 | 1765300 | 103900 | 6.254% | 1661400 | 1765300 | 1770130
Cost Category Breakdown | [6 empty] | Phase-wise Cost Performance
Category | Budget | Actual | Variance | Variance % | Risk Flag |  | Phase | Budget | Actual | Variance | Variance % | Comment | Owner
Labor |  |  | 0 | 0% | Normal |  | Initiation | 94200 | 100000 | 5800 | 6.157% | Within control band | PMO
Material |  |  | 0 | 0% | Normal |  | Planning | 246200 | 261300 | 15100 | 6.133% | Within control band | Finance PM
Equipment |  |  | 0 | 0% | Normal |  | Execution | 706000 | 751000 | 45000 | 6.374% | Within control band | Delivery Lead
Vendor |  |  | 0 | 0% | Normal |  | Monitoring | 434500 | 461700 | 27200 | 6.26% | Within control band | Control Tower
Travel |  |  | 0 | 0% | Normal |  | Closing | 180500 | 191300 | 10800 | 5.983% | Within control band | Project Office
Overhead |  |  | 0 | 0% | Normal
Cost Insights, Root Causes & Corrective Actions
Area | Observed Trend | Likely Reason | Recommended Action | Priority | Owner | Due Date
Labor | Overtime trending above baseline in execution months | Complex data migration and weekend cutovers | Re-balance team allocation and approve temporary automation support | High | Ava Sinclair | 15-Apr-2026
Vendor | External implementation partner costs exceed plan | Change requests not fully absorbed in fixed fee | Renegotiate rate card and freeze nonessential enhancements | High | Liam Patel | 20-Apr-2026
Travel | Travel peaked during pilot go-live | Multiple stakeholder workshops conducted onsite | Shift to hybrid governance reviews for next two months | Medium | Nora Hughes | 10-May-2026
Materials | Hardware and peripherals stabilized after pilot | Bulk purchasing captured volume discounts | Maintain centralized procurement gate | Low | Marco Chen | 30-Apr-2026
Note on F5: These KPIs are designed for steering committee reporting and roll up automatically from monthly data.

## Data Entry
Cost Trend Analysis - Data Entry
Project Profile |  |  |  |  | Control Assumptions
Project Name | Aurora Nexus ERP Rollout |  |  |  | Alert Variance Threshold | 8%
Company | Northwind Meridian Holdings |  |  |  | Forecast Factor on Open Trend | 1.05
Client | Helios Retail Group |  |  |  | Executive Summary Month | Mar-2026
Project Manager | Ava Sinclair
Location | Chicago, Illinois
Reporting Currency | USD
Start Date | 2026-01-01
Target Finish Date | 2026-12-31
Monthly cost inputs by phase and category. Blue cells are user-editable.
Month | Phase | Labor Budget | Material Budget | Equipment Budget | Vendor Budget | Travel Budget | Overhead Budget | Actual Labor | Actual Material | Actual Equipment | Actual Vendor | Actual Travel | Actual Overhead
Jan-2026 | Initiation | 49400 | 16700 | 7600 | 11000 | 2700 | 6800 | 52000 | 18000 | 8000 | 12000 | 3000 | 7000
Feb-2026 | Planning | 64600 | 22300 | 9000 | 16600 | 3200 | 7300 | 68000 | 24000 | 9500 | 18000 | 3500 | 7500
Mar-2026 | Planning | 67400 | 20500 | 9000 | 14700 | 4000 | 7600 | 71000 | 22000 | 9500 | 16000 | 4500 | 7800
Apr-2026 | Execution | 79800 | 28800 | 11400 | 25800 | 5400 | 8000 | 84000 | 31000 | 12000 | 28000 | 6000 | 8200
May-2026 | Execution | 86400 | 33500 | 11400 | 27600 | 6300 | 8100 | 91000 | 36000 | 12000 | 30000 | 7000 | 8400
Jun-2026 | Execution | 90200 | 39100 | 14200 | 29400 | 5800 | 8300 | 95000 | 42000 | 15000 | 32000 | 6500 | 8600
Jul-2026 | Execution | 93100 | 35300 | 14200 | 30400 | 5000 | 8500 | 98000 | 38000 | 15000 | 33000 | 5500 | 8800
Aug-2026 | Monitoring | 82600 | 31600 | 11400 | 22100 | 4500 | 8300 | 87000 | 34000 | 12000 | 24000 | 5000 | 8600
Sep-2026 | Monitoring | 75000 | 27000 | 8600 | 20200 | 4000 | 8100 | 79000 | 29000 | 9000 | 22000 | 4500 | 8400
Oct-2026 | Monitoring | 68400 | 24200 | 7600 | 19300 | 3600 | 8000 | 72000 | 26000 | 8000 | 21000 | 4000 | 8200
Nov-2026 | Closing | 58000 | 16700 | 5700 | 12900 | 2700 | 7800 | 61000 | 18000 | 6000 | 14000 | 3000 | 8000
Dec-2026 | Closing | 41800 | 11200 | 3800 | 10100 | 2200 | 7600 | 44000 | 12000 | 4000 | 11000 | 2500 | 7800
Note on A13: Enter planned budget and actual monthly spending by cost category. Main Template reads directly from this table.

## Instructions
Instructions & User Guide
Purpose | Use this workbook to monitor project spending trends, explain cost movement, forecast likely end-state cost, and present management-ready insights.
1. Data Entry | Go to the Data Entry sheet and update the blue cells only. Enter monthly budget and actual costs by category.
2. Main Dashboard | The Main Template sheet updates automatically using formulas. It summarizes KPIs, monthly trend, category analysis, phase analysis, charts, and actions.
3. KPI Logic | Baseline Budget = total planned spend. Actual Cost to Date = total actual spend. Cost Variance = Actual - Budget. Forecast at Completion extrapolates open variance using the forecast factor.
4. Interpreting Variance | Negative variance means savings against plan. Positive variance means overspend. Red-highlighted percentages indicate the variance threshold was exceeded.
5. Root Cause Review | Use the insight section to document the why behind variances: scope growth, overtime, vendor changes, procurement timing, travel spikes, or rework.
6. Corrective Actions | Capture actions with owners and due dates. This turns the dashboard into an active cost-control tool instead of a passive report.
7. Presentation Advice | Use the charts and executive snapshot for steering committee packs. Update monthly after financial close.
8. Color Legend | Dark blue = section headers. Green = healthy / controlled metrics. Orange = watchlist / management attention. Red = risk or action required. Gold = totals.
Suggested PMO Operating Rhythm
Step | Activity | Owner | Timing | Output
1 | Load prior month actuals | Project Controller | Month end +2 days | Updated actual cost data
2 | Refresh forecast and explain major deltas | Project Manager | Month end +3 days | EAC and root-cause notes
3 | Review with workstream leads | PMO / Delivery Leads | Month end +4 days | Agreed corrective actions
4 | Publish steering summary | Program Director | Month end +5 days | Executive cost trend pack
Customization Tips | Add more months, duplicate the monthly analysis formulas downward, or swap the hypothetical names with your real project details.