## Dashboard
Project Dashboard
Live project health view for senior leadership and PMO
Project |  | Company |  | Client |  | PM |  | Location |  | Finish
Aurora Nexus ERP Rollout |  | Helios Retail Group |  | Northbridge Holdings |  | Amelia Carter |  | Manchester, UK |  | 2026-09-30
Overall Completion |  | Tasks Complete |  | Budget Used |  | Open Risks |  | Critical Issues |  | Open Actions
49.5% |  | 2 |  | 67.2% |  | 5 |  | 1 |  | 4
Overall RAG Status |  |  |  | Leadership Summary
Project status overview: review KPI cards, open risks, critical issues, milestone tracker and budget variance on this dashboard.
RED
Schedule & Delivery |  |  |  | Budget & Priorities |  |  |  | Governance Watchlist
Workstream | Avg % Complete |  |  | Priority | Budget (£) |  |  | Metric | Value | Immediate Focus
Planning | 100% |  |  | High | 935000 |  |  | Open Risks | 5 | 1. Resolve 1 critical issues 2. Close blueprint approval 3. Secure extra UAT capacity 4. Watch integration vendor dependency
Design | 90% |  |  | Medium | 265000 |  |  | Critical Issues | 1
Build | 57% |  |  | Low | 50000 |  |  | Open Actions | 4
Test | 20% | [6 empty] | Milestones Off Track | 2
Change | 48% | [6 empty] | Schedule Health | Recovery
Deployment | 0% | [6 empty] | Budget Health | Within Budget
Governance | 65%
Milestone Tracker | [5 empty] | Issue & Risk Spotlight
Milestone | Planned | Actual | Status | Owner | Comment | Type | ID | Description | Owner | Status | Due/Action
Charter Approved | 2026-01-12 | 2026-01-12 | Complete | Amelia Carter | Delivered on time | Risk | R-01 | Vendor API delay may affect integrations | Lucas Murphy | Open | Weekly escalation with vendor
Requirements Signed Off | 2026-02-10 | 2026-02-12 | Delayed | Noah Patel | 2-day approval delay | Risk | R-02 | Business SMEs have limited UAT availability | Henry Walsh | Open | Reserve backup testers
Blueprint Approved | 2026-03-15 | 0 | At Risk | Sophia Hughes | Awaiting architecture board | Issue | I-01 | Integration test environment unstable | Grace Turner | Open | 46172
SIT Complete | 2026-06-25 | 0 | Pending | Grace Turner | Depends on integration fixes | Issue | I-02 | Duplicate customer records in legacy extract | Olivia Reed | Open | 46176
UAT Sign-off | 2026-08-05 | 0 | Pending | Henry Walsh | Future milestone
Go-live | 2026-09-08 | 0 | Pending | Mia Collins | Future milestone
Metric | Value |  | Workstream | Avg % Complete |  | Priority | Budget |  | Milestone Status | Count
Total Tasks | 12 |  | Planning | 1 |  | High | 935000 |  | Complete | 1
Completed Tasks | 2 |  | Design | 0.9 |  | Medium | 265000 |  | Delayed | 1
In Progress Tasks | 7 |  | Build | 0.57 |  | Low | 50000 |  | At Risk | 1
Not Started Tasks | 3 |  | Test | 0.2 |  |  |  |  | Pending | 3
Overall Completion | 0.495 |  | Change | 0.48
Planned Budget | 1250000 |  | Deployment | 0
Actual Cost | 840000 |  | Governance | 0.65
Budget Variance | 410000
Open Risks | 5
Critical Issues | 1
Open Actions | 4
Milestones Complete | 1
Milestones Delayed/At Risk | 2
Schedule Health | Recovery
Budget Health | Within Budget
Overall RAG | RED

## Data Entry
Project Dashboard Template - Data Entry
Project Profile
Project Name | Aurora Nexus ERP Rollout
Company | Helios Retail Group
Client | Northbridge Holdings
Project Manager | Amelia Carter
Executive Sponsor | Liam Bennett
Project Location | Manchester, UK
Start Date | 2026-01-05
Target Finish | 2026-09-30
Approved Budget | 1250000
Task ID | Workstream | Task Name | Owner | Start Date | Due Date | % Complete | Status | Priority | Budget (£) | Actual Cost (£) | Notes
T-001 | Planning | Kick-off & charter approval | Amelia Carter | 2026-01-05 | 2026-01-12 | 100% | Complete | High | 40000 | 38500 | Steering committee signed off
T-002 | Planning | Detailed requirements workshops | Noah Patel | 2026-01-13 | 2026-02-10 | 100% | Complete | High | 95000 | 97500 | Slight overrun due to extra sessions
T-003 | Design | Solution blueprint | Sophia Hughes | 2026-02-11 | 2026-03-12 | 90% | In Progress | High | 110000 | 98000 | Final approval pending
T-004 | Build | Core module configuration | Ethan Brooks | 2026-03-01 | 2026-04-30 | 72% | In Progress | High | 220000 | 205000 | On track
T-005 | Build | Data migration scripts | Olivia Reed | 2026-03-15 | 2026-05-20 | 55% | In Progress | Medium | 145000 | 132500 | Needs extra QA window
T-006 | Build | Integration development | Lucas Murphy | 2026-03-20 | 2026-06-15 | 44% | In Progress | High | 180000 | 176000 | Vendor dependency
T-007 | Test | System integration testing | Grace Turner | 2026-05-10 | 2026-06-25 | 20% | In Progress | High | 120000 | 35000 | Early test cases executed
T-008 | Change | Training material creation | Ella Foster | 2026-05-01 | 2026-06-10 | 48% | In Progress | Medium | 65000 | 29000 | Draft modules ready
T-009 | Deployment | UAT & business sign-off | Henry Walsh | 2026-06-26 | 2026-08-05 | 0% | Not Started | High | 80000 | 0 | Awaiting SIT exit
T-010 | Deployment | Go-live readiness | Mia Collins | 2026-08-01 | 2026-09-05 | 0% | Not Started | High | 90000 | 0 | Planned
T-011 | Deployment | Go-live support | Daniel Price | 2026-09-06 | 2026-09-30 | 0% | Not Started | Medium | 55000 | 0 | Planned
T-012 | Governance | Weekly PMO reporting | Ava Richardson | 2026-01-05 | 2026-09-30 | 65% | In Progress | Low | 50000 | 28500 | Ongoing
Milestone Register
Milestone | Owner | Planned Date | Actual Date | Status | Comments
Charter Approved | Amelia Carter | 2026-01-12 | 2026-01-12 | Complete | Delivered on time
Requirements Signed Off | Noah Patel | 2026-02-10 | 2026-02-12 | Delayed | 2-day approval delay
Blueprint Approved | Sophia Hughes | 2026-03-15 |  | At Risk | Awaiting architecture board
SIT Complete | Grace Turner | 2026-06-25 |  | Pending | Depends on integration fixes
UAT Sign-off | Henry Walsh | 2026-08-05 |  | Pending | Future milestone
Go-live | Mia Collins | 2026-09-08 |  | Pending | Future milestone
Risk Register
Risk ID | Risk Description | Probability | Impact | Score | Owner | Mitigation | Status
R-01 | Vendor API delay may affect integrations | High | High | 9 | Lucas Murphy | Weekly escalation with vendor | Open
R-02 | Business SMEs have limited UAT availability | Medium | High | 6 | Henry Walsh | Reserve backup testers | Open
R-03 | Data quality issues in legacy system | High | Medium | 6 | Olivia Reed | Data cleanse sprint | Mitigating
R-04 | Training adoption lower than expected | Medium | Medium | 4 | Ella Foster | Train-the-trainer sessions | Open
R-05 | Budget pressure from scope growth | Low | High | 3 | Amelia Carter | Change control board | Monitoring
Issue Log
Issue ID | Issue Description | Severity | Owner | Date Raised | Due Date | Status | Action
I-01 | Integration test environment unstable | Critical | Grace Turner | 2026-05-21 | 2026-05-30 | Open | Infrastructure patch
I-02 | Duplicate customer records in legacy extract | High | Olivia Reed | 2026-05-18 | 2026-06-03 | Open | Data cleanse
I-03 | Additional finance reports requested | Medium | Sophia Hughes | 2026-05-14 | 2026-05-29 | In Review | Assess via change request
I-04 | Training venue booking not confirmed | Low | Ella Foster | 2026-05-20 | 2026-05-27 | Closed | Alternative venue secured
Action Tracker
Action ID | Action | Owner | Due Date | Status | Priority | Related Area | Notes
A-01 | Approve final solution blueprint | Liam Bennett | 2026-05-31 | Open | High | Design | Required for build sign-off
A-02 | Confirm additional UAT testers | Henry Walsh | 2026-06-04 | Open | High | Test | Business dependency
A-03 | Complete data cleanse dry run | Olivia Reed | 2026-06-07 | In Progress | Medium | Migration | Track error rate
A-04 | Finalize training calendar | Ella Foster | 2026-06-02 | Open | Medium | Change | Share with region leads
Note on A15: Update task rows and extend formulas/charts if you add more tasks.
Note on A31: Keep milestone status aligned to actual vs planned date.

## Instructions
How to Use This Project Dashboard Template
Purpose | This workbook gives a senior-management view of project delivery, budget, schedule, milestones, issues, risks, and action ownership.
1 | Dashboard sheet | Review this page during weekly governance, client reviews, and steering committee meetings. It automatically pulls from Data Entry.
2 | Data Entry sheet | Update project profile, tasks, milestones, risks, issues, and actions. The dashboard refreshes from these ranges.
3 | Task status values | Use Complete, In Progress, or Not Started. Enter % Complete as a percentage value.
4 | Milestone status values | Use Complete, Delayed, At Risk, or Pending. Add actual dates as milestones are achieved.
5 | Risk management | Keep probability, impact, score, owner, and mitigation up to date. Focus first on high-score items.
6 | Issues and actions | Review due dates and owners weekly. Closed items may stay visible for audit trail or be archived.
7 | Budget tracking | Update planned budget and actual cost at task level for fast cost visibility and variance tracking.
8 | Customization | Replace all hypothetical names, locations, and companies with your real project details.
9 | Scaling up | If you add many more rows, copy formulas/formatting downward or convert trackers to Excel Tables.
10 | Color usage | Blue = structure; Green = positive progress; Orange/Gold = caution/focus; Red = issues and risks.
Recommended cadence | Daily: issues/actions ¦ Weekly: tasks, milestones, risks, costs ¦ Monthly: executive steering review