## Project Cost Template
Project Proposal Cost
Executive-ready estimate for a proposed smart infrastructure deployment
Project Name | Orion Smart Hub Rollout | Client / Sponsor | Northwind Renewables Ltd. | Proposal ID | PR-2026-047 | Prepared By | Amelia Grant
Project Manager | Liam Mercer | Location | Denver Innovation Campus | Start Date | 2026-05-18 | End Date | 2026-10-30
Direct Costs |  | Overhead |  | Contingency |  | Tax |  | Grand Total
140834 |  | 12675.06 |  | 10745.6342 |  | 13551.0123 |  | 177805.7065
Cost Breakdown by Category |  |  |  |  | Cost Breakdown by Project Phase
Category | Amount | Share of Direct Cost | Management Note |  | Phase | Amount | Share of Direct Cost | Target Outcome
Labor | 52504 | 0% | Delivery team and specialist effort |  | Initiation | 7320 | 0% | Charter, kickoff and alignment
Material | 37000 | 0% | Physical inputs and consumables |  | Planning | 11706 | 0% | Design, schedule and procurement prep
Equipment | 7170 | 0% | Rented/owned tools and machinery |  | Execution | 106400 | 0% | Build/install activities
Software | 3090 | 0% | Licenses and digital tools |  | Testing | 10098 | 0% | Quality control and commissioning
Vendor | 32950 | 0% | Subcontracted services and packages |  | Deployment | 4350 | 0% | Training and handover
Travel | 5720 | 0% | Client/site mobility and lodging |  | Closure | 960 | 0% | Closeout and archive
Admin/Overhead | 2400 | 0% | Support services charged as direct line items |  | Total by Phase | 140834 | 0% | Check should equal Direct Costs KPI
Total Direct Costs | 140834 | 0% | Check should equal Direct Costs KPI
Commercial Assumptions |  |  |  |  | Exclusions & Proposal Boundaries
• Labor rates are blended and based on current regional market assumptions. |  |  |  |  | • Utility company upgrade fees and permit escalation are excluded unless specifically approved.
• Material and vendor pricing reflect preliminary budgetary quotes, not final contracts. |  |  |  |  | • Client-side cybersecurity hardening and enterprise integrations are outside current scope.
• Contingency is intended for normal estimating uncertainty and minor scope refinement. |  |  |  |  | • Any work caused by major design changes after approval will be treated as a change order.
• Tax and overhead percentages are editable on the Data Entry sheet. |  |  |  |  | • Long-term support beyond 30 days after go-live is excluded from this proposal.
Approval Workflow
Role | Name | Status | Date | Signature / Notes
Prepared By | Amelia Grant | Draft | 2026-04-15 | Initial estimate issued for internal review
Reviewed By | Jordan Patel | Pending |  | PMO review pending
Approved By | Elena Brooks | Pending |  | Sponsor approval pending
Tip: Edit assumptions and line items on the Data Entry sheet; summary sections update automatically.

## Data Entry
Project Proposal Cost Template – Data Entry
Edit assumptions and cost line items below. All totals flow to the main template automatically. | [6 empty] | Category List | Phase List
[7 empty] | Labor | Initiation
Project & Commercial Assumptions | [6 empty] | Material | Planning
Project Name | Orion Smart Hub Rollout | [5 empty] | Equipment | Execution
Client / Sponsor | Northwind Renewables Ltd. | [5 empty] | Software | Testing
Proposal ID | PR-2026-047 | [5 empty] | Vendor | Deployment
Prepared By | Amelia Grant | [5 empty] | Travel | Closure
Project Manager | Liam Mercer | [5 empty] | Admin/Overhead
Location | Denver Innovation Campus
Start Date | 2026-05-18
End Date | 2026-10-30
Currency | USD
Tax Rate | 8.25%
Contingency % | 7%
Overhead % on Direct Costs | 9%
Detailed Cost Inputs
Cost Category | Project Phase | Description | Owner/Vendor | Units | Rate | Line Total
Labor | Initiation | Project kickoff and charter development | Amelia Grant | 40 | 145 | 5800
Labor | Planning | Work breakdown structure & schedule build | Liam Mercer | 72 | 128 | 9216
Labor | Execution | Electrical engineering design package | Apex Grid Consultants | 96 | 155 | 14880
Labor | Execution | Field installation supervision | Summit Site Services | 120 | 118 | 14160
Labor | Testing | Commissioning and QA checks | Helio QA Partners | 64 | 132 | 8448
Material | Execution | IoT control panels (12 units) | BluePeak Controls | 12 | 1850 | 22200
Material | Execution | Structured cabling and connectors | Cobalt Industrial Supply | 1 | 14800 | 14800
Equipment | Execution | Lift rental – 6 weeks | FrontRange Equipment Hire | 6 | 920 | 5520
Equipment | Testing | Thermal scanner rental | Metro Calibration Labs | 10 | 165 | 1650
Software | Planning | Project scheduling licenses | VertexPM Cloud | 5 | 210 | 1050
Software | Execution | Analytics dashboard subscription | Nimbus Insights | 6 | 340 | 2040
Vendor | Execution | Civil subcontract package | Red Rock Civil Works | 1 | 28600 | 28600
Vendor | Deployment | Operator training sessions | Prairie Learning Studio | 3 | 1450 | 4350
Travel | Initiation | Client workshop travel | Mile High Travel Desk | 4 | 380 | 1520
Travel | Execution | Biweekly site visits | Mile High Travel Desk | 10 | 420 | 4200
Admin/Overhead | Planning | Document control support | Northwind PMO Support | 30 | 48 | 1440
Admin/Overhead | Closure | Closeout documentation and archive | Northwind PMO Support | 20 | 48 | 960
Note on B15: Editable assumption: extra budget held for risk, uncertainty, and minor scope refinement.
Note on B16: Editable assumption: indirect support burden applied to direct costs.

## Instructions
Instructions – How to Use This Template
Audience | Project managers, proposal teams, PMO analysts, commercial leads, and department heads.
Workflow
1. Update assumptions | Go to the Data Entry sheet and adjust project name, sponsor, dates, tax, contingency, and overhead percentages.
2. Edit line items | Modify, add, or replace cost lines in rows 21–50. Enter Cost Category, Project Phase, Description, Owner/Vendor, Units, and Rate.
3. Review the summary | Return to the Project Cost Template sheet to review the executive summary, category totals, phase totals, and proposal grand total.
4. Validate scope | Review the assumptions and exclusions sections to ensure proposal boundaries are explicitly stated.
5. Seek approval | Complete the approval block once the estimate is reviewed and ready for sponsor sign-off.
What This Template Explains
• | Project identity and commercial context
• | Direct cost estimate and total proposal value
• | Labor, materials, equipment, software, vendor, travel, and support cost areas
• | Cost allocation by delivery phase
• | Overhead, contingency, and tax treatment
• | Assumptions, exclusions, and approval governance
Color Guide
Title / primary headers
Section banners
Data tables and positive workflow sections
Key assumptions / attention areas
Exclusions / commercial boundaries
Final approval / high-importance sign-off
Hypothetical Project Context Used in This Demo
Company | Northwind Renewables Ltd.
Project | Orion Smart Hub Rollout
Site | Denver Innovation Campus