## Resource Plan
Project Resource Plan
Project Snapshot
Company | Aurelia BuildWorks Ltd. |  |  |  | Total Planned Cost |  | Avg Allocation |  | Overallocated Resources |  | Open Planned Tasks
Project | Orion Smart Campus Rollout |  |  |  | 775189 |  | 72.5% |  | 3 |  | 6
Project Manager | Maya Bennett
Location | Austin, Texas
Start Date | 2026-04-01
End Date | 2026-09-30
Resource Portfolio & Workload Control
Resource ID | Resource Name | Role | Department | Location | Skill | Type | Availability % | Allocation % | Planned Hours | Rate | Planned Cost | Workload Flag | Status
R-001 | Maya Bennett | Project Manager | PMO | Austin | Program Leadership | Internal | 100% | 85% | 889 | 145 | 128905 | Balanced | Assigned
R-002 | Liam Ortega | Site Engineer | Engineering | Austin | Civil Execution | Internal | 100% | 90% | 787 | 110 | 86570 | Overallocated | Assigned
R-003 | Priya Nair | Design Lead | Design | Dallas | Space Planning | Internal | 80% | 70% | 291 | 125 | 36375 | Balanced | Assigned
R-004 | Noah Kim | Procurement Specialist | Supply Chain | Houston | Vendor Sourcing | Internal | 75% | 65% | 301 | 95 | 28595 | Balanced | Assigned
R-005 | Chloe Mercer | QA Manager | Quality | Austin | Commissioning QA | Internal | 100% | 75% | 394 | 120 | 47280 | Balanced | Planned
R-006 | Ethan Brooks | Controls Technician | Automation | Austin | BMS Integration | Contractor | 100% | 95% | 653 | 135 | 88155 | Overallocated | Planned
R-007 | Sofia Delgado | Data Analyst | PMO | Remote | Reporting & Analytics | Internal | 60% | 50% | 314 | 88 | 27632 | Balanced | Assigned
R-008 | Aiden Clarke | Field Supervisor | Operations | Austin | Subcontractor Coordination | Internal | 100% | 85% | 743 | 105 | 78015 | Balanced | Planned
R-009 | Harper Stone | Electrician Crew A | Electrical | Austin | Electrical Installation | Contractor | 100% | 100% | 2491 | 78 | 194298 | Overallocated | Planned
R-010 | Mason Reed | Network Engineer | Technology | Dallas | Network & WiFi | Internal | 75% | 60% | 195 | 118 | 23010 | Balanced | Planned
R-011 | Ella Winters | Change Manager | HR/Change | Remote | Training & Adoption | Internal | 70% | 55% | 172 | 102 | 17544 | Balanced | Planned
R-012 | Leo Hart | Safety Officer | EHS | Austin | Site Safety | Internal | 50% | 40% | 209 | 90 | 18810 | Underused | Assigned
Role Demand & Cost Summary | [6 empty] | Phase, Dependency & Constraint Control
Role | Headcount | Total Hours | Total Cost | Avg Allocation | Forecast Comment |  | Assignment ID | Phase | Task / Deliverable | Owner | Start | End | Hours | Dependency / Constraint
Project Manager | 1 | 889 | 128905 | 85% | On target |  | A-101 | Initiation | Kickoff & Governance Setup | R-001 | 2026-04-01 | 2026-04-10 | 60 | Client contract signature ¦ Executive steering committee approval
Site Engineer | 1 | 787 | 86570 | 90% | Secure backup capacity |  | A-102 | Design | Campus space survey & concept design | R-003 | 2026-04-05 | 2026-04-30 | 110 | Site access approval ¦ Weekend access only
Design Lead | 1 | 291 | 36375 | 70% | On target |  | A-103 | Planning | Master schedule & procurement plan | R-001 | 2026-04-11 | 2026-04-25 | 55 | Kickoff complete ¦ Align with budget gate
Procurement Specialist | 1 | 301 | 28595 | 65% | On target |  | A-104 | Procurement | Issue RFPs and evaluate vendors | R-004 | 2026-04-20 | 2026-05-20 | 90 | Approved BOM ¦ Long-lead items need early release
QA Manager | 1 | 394 | 47280 | 75% | On target |  | A-105 | Execution | Civil works and fit-out prep | R-002 | 2026-05-01 | 2026-06-20 | 180 | Design freeze ¦ Weather may impact deliveries
Controls Technician | 1 | 653 | 88155 | 95% | Secure backup capacity |  | A-106 | Execution | Electrical rough-in | R-009 | 2026-05-18 | 2026-07-15 | 300 | Civil complete by zone ¦ Night shifts required in live areas
Data Analyst | 1 | 314 | 27632 | 50% | On target |  | A-107 | Execution | Network backbone installation | R-010 | 2026-06-01 | 2026-07-10 | 120 | Cable trays installed ¦ Requires secure storage cage
Field Supervisor | 1 | 743 | 78015 | 85% | On target |  | A-108 | Execution | BMS / controls integration | R-006 | 2026-06-15 | 2026-08-05 | 210 | Power-up sequence complete ¦ Specialist vendor coordination
Electrician Crew A | 1 | 2491 | 194298 | 100% | Secure backup capacity |  | A-109 | Monitoring | Resource burn review & KPI reporting | R-007 | 2026-04-15 | 2026-09-25 | 130 | Weekly timesheet updates ¦ Use Friday cut-off
Network Engineer | 1 | 195 | 23010 | 60% | On target |  | A-110 | Quality | Testing, QA walkthroughs, punch list | R-005 | 2026-08-01 | 2026-09-10 | 160 | Install complete by zone ¦ No close-out without asset tags
Change Manager | 1 | 172 | 17544 | 55% | On target |  | A-111 | Change | Training plan and adoption sessions | R-011 | 2026-08-15 | 2026-09-20 | 95 | Client SME availability ¦ Remote sessions for regional staff
Safety Officer | 1 | 209 | 18810 | 40% | Can absorb more work |  | A-112 | Closeout | Final handover & lessons learned | R-001 | 2026-09-15 | 2026-09-30 | 45 | QA sign-off ¦ All O&M manuals required
Monthly Resource Forecast & Utilization View
Role | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Total Hrs | Peak Month | Risk Trigger |  | Planner Notes • Template covers resource identification, roles, allocation, availability, cost, skills, forecasting and constraints. • Update the Data Entry sheet only. • Red / yellow highlights indicate review actions. • Replace sample names, rates and dates with actual project data.
Project Manager | 138 | 148 | 148 | 158 | 158 | 138 | 888 | Jul-26 | Monitor normally
Site Engineer | 118 | 167 | 187 | 177 | 138 | 0 | 787 | Jun-26 | Add surge capacity
Design Lead | 116 | 103 | 71 | 0 | 0 | 0 | 290 | Apr-26 | Monitor normally
Procurement Specialist | 48 | 96 | 90 | 66 | 0 | 0 | 300 | May-26 | Monitor normally
QA Manager | 0 | 0 | 0 | 83 | 145 | 166 | 394 | Sep-26 | Add surge capacity
Controls Technician | 0 | 0 | 141 | 191 | 201 | 121 | 654 | Aug-26 | Add surge capacity
Data Analyst | 52 | 52 | 52 | 52 | 52 | 52 | 312 | Apr-26 | Monitor normally
Status | Count | 0 | 0 | 0 | 0 | 0 | 0 | May-26 | Review underutilization
Assigned | 6 | 0 | 0 | 0 | 0 | 0 | 6 | Apr-26 | Review underutilization
Planned | 6 | 0 | 0 | 0 | 0 | 0 | 6 | Apr-26 | Review underutilization
On Hold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Apr-26 | Review underutilization
Safety Officer | 29 | 33 | 38 | 38 | 38 | 33 | 209 | Jun-26 | Review underutilization

## Data Entry
Project Resource Plan Template – Data Entry
Project Profile
Company | Aurelia BuildWorks Ltd. |  | Tip:
Project | Orion Smart Campus Rollout |  | Update the blue-font input cells in this sheet.
Project Manager | Maya Bennett
Client | Northwind Learning Group
Primary Location | Austin, Texas
Start Date | 2026-04-01
End Date | 2026-09-30
Approved Budget | 1850000
Resource ID | Resource Name | Role | Department | Base Location | Primary Skill | Resource Type | Start Date | End Date | Availability % | Allocation % | Standard Rate | Weekly Capacity (hrs) | Planned Hours | Planned Cost | Status
R-001 | Maya Bennett | Project Manager | PMO | Austin | Program Leadership | Internal | 2026-04-01 | 2026-09-30 | 100% | 85% | 145 | 40 | 889 | 128905 | Assigned
R-002 | Liam Ortega | Site Engineer | Engineering | Austin | Civil Execution | Internal | 2026-04-01 | 2026-08-31 | 100% | 90% | 110 | 40 | 787 | 86570 | Assigned
R-003 | Priya Nair | Design Lead | Design | Dallas | Space Planning | Internal | 2026-04-01 | 2026-06-30 | 80% | 70% | 125 | 32 | 291 | 36375 | Assigned
R-004 | Noah Kim | Procurement Specialist | Supply Chain | Houston | Vendor Sourcing | Internal | 2026-04-15 | 2026-07-31 | 75% | 65% | 95 | 30 | 301 | 28595 | Assigned
R-005 | Chloe Mercer | QA Manager | Quality | Austin | Commissioning QA | Internal | 2026-07-01 | 2026-09-30 | 100% | 75% | 120 | 40 | 394 | 47280 | Planned
R-006 | Ethan Brooks | Controls Technician | Automation | Austin | BMS Integration | Contractor | 2026-06-01 | 2026-09-15 | 100% | 95% | 135 | 45 | 653 | 88155 | Planned
R-007 | Sofia Delgado | Data Analyst | PMO | Remote | Reporting & Analytics | Internal | 2026-04-01 | 2026-09-30 | 60% | 50% | 88 | 24 | 314 | 27632 | Assigned
R-008 | Aiden Clarke | Field Supervisor | Operations | Austin | Subcontractor Coordination | Internal | 2026-05-01 | 2026-09-30 | 100% | 85% | 105 | 40 | 743 | 78015 | Planned
R-009 | Harper Stone | Electrician Crew A | Electrical | Austin | Electrical Installation | Contractor | 2026-05-15 | 2026-08-31 | 100% | 100% | 78 | 160 | 2491 | 194298 | Planned
R-010 | Mason Reed | Network Engineer | Technology | Dallas | Network & WiFi | Internal | 2026-06-01 | 2026-08-15 | 75% | 60% | 118 | 30 | 195 | 23010 | Planned
R-011 | Ella Winters | Change Manager | HR/Change | Remote | Training & Adoption | Internal | 2026-07-15 | 2026-09-30 | 70% | 55% | 102 | 28 | 172 | 17544 | Planned
R-012 | Leo Hart | Safety Officer | EHS | Austin | Site Safety | Internal | 2026-04-01 | 2026-09-30 | 50% | 40% | 90 | 20 | 209 | 18810 | Assigned
Task Assignments / Phase Planning
Assignment ID | Phase | Task / Deliverable | Owner Resource ID | Priority | Dependency | Planned Start | Planned End | Planned Hours | Constraint / Note
A-101 | Initiation | Kickoff & Governance Setup | R-001 | High | Client contract signature | 2026-04-01 | 2026-04-10 | 60 | Executive steering committee approval
A-102 | Design | Campus space survey & concept design | R-003 | High | Site access approval | 2026-04-05 | 2026-04-30 | 110 | Weekend access only
A-103 | Planning | Master schedule & procurement plan | R-001 | High | Kickoff complete | 2026-04-11 | 2026-04-25 | 55 | Align with budget gate
A-104 | Procurement | Issue RFPs and evaluate vendors | R-004 | High | Approved BOM | 2026-04-20 | 2026-05-20 | 90 | Long-lead items need early release
A-105 | Execution | Civil works and fit-out prep | R-002 | High | Design freeze | 2026-05-01 | 2026-06-20 | 180 | Weather may impact deliveries
A-106 | Execution | Electrical rough-in | R-009 | High | Civil complete by zone | 2026-05-18 | 2026-07-15 | 300 | Night shifts required in live areas
A-107 | Execution | Network backbone installation | R-010 | Medium | Cable trays installed | 2026-06-01 | 2026-07-10 | 120 | Requires secure storage cage
A-108 | Execution | BMS / controls integration | R-006 | High | Power-up sequence complete | 2026-06-15 | 2026-08-05 | 210 | Specialist vendor coordination
A-109 | Monitoring | Resource burn review & KPI reporting | R-007 | Medium | Weekly timesheet updates | 2026-04-15 | 2026-09-25 | 130 | Use Friday cut-off
A-110 | Quality | Testing, QA walkthroughs, punch list | R-005 | High | Install complete by zone | 2026-08-01 | 2026-09-10 | 160 | No close-out without asset tags
A-111 | Change | Training plan and adoption sessions | R-011 | Medium | Client SME availability | 2026-08-15 | 2026-09-20 | 95 | Remote sessions for regional staff
A-112 | Closeout | Final handover & lessons learned | R-001 | High | QA sign-off | 2026-09-15 | 2026-09-30 | 45 | All O&M manuals required
Lists
[16 empty] | Initiation | High | Assigned
[16 empty] | Design | Medium | Planned
[16 empty] | Planning | Low | On Hold
Procurement
Execution
Monitoring
Quality
Change
Closeout
Note on A14: Master input table for project resources. Blue-font cells are intended as editable inputs.
Note on A29: Assignment planning table used for owner, phase, workload and constraints tracking.

## Instructions
How to Use This Project Resource Plan Template
No. | Section | Guidance
1 | Purpose | This workbook is a professional project resource planning template for people, roles, workload, cost, timeline and constraint control.
2 | Sheet 1 – Resource Plan | Executive planning sheet. Review KPIs, workload flags, role demand, phase ownership, forecast by month and key constraints.
3 | Sheet 2 – Data Entry | Update project profile, resource master records and assignment planning inputs. Blue-font cells are the main editable inputs.
4 | Sheet 3 – Instructions | Reference sheet for new users and handover.
5 | What it covers | Resource identification, responsibilities, allocation, availability, quantity, skills, cost planning, forecasting, utilization tracking, dependencies and constraints.
6 | Recommended process | 1) Update project profile. 2) Add or revise resources. 3) Add assignments by phase. 4) Review workload flags and forecast. 5) Rebalance or secure extra capacity.
7 | Allocation rules | Availability % = actual time available to the project. Allocation % = share of available time committed. Cells above 85% allocation should be reviewed for overloading.
8 | Cost logic | Planned Hours are estimated from duration × weekly capacity × allocation %. Planned Cost = Planned Hours × Standard Rate.
9 | Forecast logic | Monthly forecast distributes role hours across Apr–Sep using a realistic phase-weighting profile. Replace sample values if your project follows a different curve.
10 | Status colors | Blue / dark blue = structure and key headings. Green = healthy planning area. Yellow / orange = caution or action. Red highlights = overload or risk.
11 | Sample project context | This version uses hypothetical organizations, people and locations: Aurelia BuildWorks Ltd., Orion Smart Campus Rollout, and Northwind Learning Group.
12 | Customization ideas | Add actual-vs-plan columns, utilization by department, holiday calendars, recruitment lead times, subcontractor trackers or portfolio-level rollups.
Color Legend
| Dark Blue | Primary title / executive headers
| Blue | Operational table headers
| Green | Healthy planning summary sections
| Orange / Gold | Action, dependency or caution sections
| Light Red | Over-allocation / risk review