## Main Template
Project Status Report
Senior Project Manager template ¦ built for concise leadership reporting and stakeholder decisions
Selected Reporting Period | 2026-W12 |  |  | Project | Aurelia CRM Transformation |  |  | Sponsor | Helios Retail Group
Project Manager | Maya Bennett, Sr. PM |  |  | Company | Northbridge Dynamics Ltd. |  |  | Location | Seattle Innovation Hub
Overall Status |  |  | Progress |  |  | Budget Variance |  |  | Open Risks / Issues
Green |  |  | 78% |  |  | -10150 |  |  | 4
Status at a Glance |  |  |  |  | Executive Summary
Dimension | Current Status | Commentary |  |  | Healthy position overall with strong cost control and manageable scope watch items.
Schedule | Green | Timeline control against baseline milestones and critical path. |  |  | Accomplishments |  |  |  | Next Steps
Budget | Green | Actual spend versus approved plan and forecast. |  |  | UAT pack prepared; training content 80% complete; pilot users onboarded. |  |  |  | Launch UAT, finalize cutover rehearsal, and close medium risks.
Scope | Amber | Change control health and requirement stability.
Quality | Green | Testing quality, rework, defect trends, and acceptance readiness.
Resources | Green | Capacity, skills, and vendor support sufficiency. |  |  | Decisions Needed |  |  |  | Budget Snapshot
Risk | Amber | Exposure level across active risks and mitigation effectiveness. |  |  | Approve final training wave budget. |  |  |  | Planned Spend | 720000
[9 empty] | Actual Spend | 709850
[9 empty] | Variance | -10150
Milestone Tracker | [6 empty] | Top Risks & Issues
Milestone | Baseline | Forecast | Status | % Complete |  |  | Top Active Risks
Discovery & Requirements Sign-off | 2026-01-23 | 2026-01-23 | Complete | 100% | Approved by sponsor |  | R-01 | Legacy customer records contain duplicate profiles that may delay UAT data loads. |  |  | Critical | Open
Solution Design Baseline | 2026-02-06 | 2026-02-10 | Complete | 100% | Closed 2 business days late |  | R-02 | Vendor API throughput may be below target for launch volumes. |  |  | High | Mitigating
Sprint Build Complete | 2026-03-06 | 2026-03-06 | Complete | 100% | Recovered schedule |  | R-03 | Regional managers may request additional analytics outside current scope. |  |  | Medium | Open
UAT Launch | 2026-04-03 | 2026-04-07 | At Risk | 85% | Dependent on data fixes
Pilot Go-Live | 2026-05-15 | 2026-05-22 | Planned | 55% | Cutover rehearsal pending |  | Current Issues
National Rollout | 2026-07-31 | 2026-08-07 | Planned | 28% | Awaiting phase-2 scope close |  | I-01 | Duplicate customer IDs caused 7% mismatch in trial migration. |  |  | High | Open
[7 empty] | I-02 | One middleware specialist resigned mid-sprint. |  |  | Medium | Closed
Change Control Snapshot | [6 empty] | I-03 | Two training videos require legal review before release. |  |  | Medium | In Progress
CR ID | Description |  | Impact (Days) | Impact ($) | Decision | Status
CR-01 | Add advanced dashboard analytics to phase 1. |  | 12 | 42000 | Deferred to Phase 2 | Closed | Priority Actions
CR-02 | Expand training wave to include franchise supervisors. |  | 4 | 9500 | Approved | Open | A-01 | Approve final training wave budget. |  |  | High | Open
CR-03 | Move loyalty integration ahead of returns workflow. |  | 7 | 15000 | Under Review | Open | A-02 | Complete cutover rehearsal checklist. |  |  | High | In Progress
[7 empty] | A-03 | Validate API response times at peak load. |  |  | Medium | Open
Performance Trends
Note on C6: Choose the reporting period to refresh the entire dashboard view.

## Data Entry
Project Status Report - Data Entry & Source Tables
Blue-tinted cells are intended for editing. The dashboard sheet reads from these source tables.
Project Profile |  |  |  |  | Status Scale
Project Name | Aurelia CRM Transformation |  |  |  | Green | On Track
Company | Northbridge Dynamics Ltd. |  |  |  | Amber | Watch / Minor Variance
Client / Sponsor | Helios Retail Group |  |  |  | Red | Critical / Escalation
Project Manager | Maya Bennett, Sr. PM
PMO Office | Atlas Program Office
Location | Seattle Innovation Hub
Project Start | 2026-01-05
Target Finish | 2026-09-30
Reporting Periods (one row per reporting cycle)
Report Period | Report Date | Overall | Schedule | Budget | Scope | Quality | Resources | Risk | Progress % | Planned Spend | Actual Spend | Accomplishments | Next Steps | Decisions Needed | Executive Summary
2026-W02 | 2026-01-16 | Green | Green | Green | Green | Green | Green | Amber | 12% | 120000 | 116500 | Discovery workshops completed; CRM data model approved. | Finalize integration design and confirm vendor timeline. | Approve extended UAT environment capacity. | Aurelia remains on track with early design approvals completed.
2026-W04 | 2026-01-30 | Green | Green | Amber | Green | Green | Green | Amber | 24% | 240000 | 251200 | Process maps signed off; prototype screens reviewed with client. | Complete API mapping and begin sprint 1 build. | Decision needed on loyalty module sequencing. | Prototype feedback positive; minor cost pressure due to specialist contractor use.
2026-W06 | 2026-02-13 | Amber | Amber | Amber | Green | Green | Amber | Amber | 38% | 360000 | 372500 | Sprint 1 delivered; data cleansing started. | Stabilize middleware configuration and close staffing gap. | Approve temporary data analyst backfill. | Schedule under watch after vendor dependency slipped by 4 business days.
2026-W08 | 2026-02-27 | Amber | Amber | Green | Amber | Green | Amber | Red | 51% | 480000 | 476900 | Sprint 2 delivered; pilot migration test completed. | Resolve duplicate customer records and complete security review. | Decision on go/no-go for early pilot region. | Risk increased after duplicate records surfaced in legacy source data.
2026-W10 | 2026-03-13 | Amber | Green | Green | Amber | Green | Green | Amber | 66% | 600000 | 598400 | Security review passed; automation scripts reduced manual effort. | Close open change requests and prepare UAT pack. | Approve revised phase-2 reporting scope. | Project recovered schedule; scope clarity needed for advanced analytics asks.
2026-W12 | 2026-03-27 | Green | Green | Green | Amber | Green | Green | Amber | 78% | 720000 | 709850 | UAT pack prepared; training content 80% complete; pilot users onboarded. | Launch UAT, finalize cutover rehearsal, and close medium risks. | Approve final training wave budget. | Healthy position overall with strong cost control and manageable scope watch items.
Milestones
Milestone ID | Milestone | Owner | Baseline Date | Forecast Date | Status | % Complete | Notes
MS-01 | Discovery & Requirements Sign-off | Maya Bennett | 2026-01-23 | 2026-01-23 | Complete | 100% | Approved by sponsor
MS-02 | Solution Design Baseline | Ravi Solis | 2026-02-06 | 2026-02-10 | Complete | 100% | Closed 2 business days late
MS-03 | Sprint Build Complete | Nina Ortega | 2026-03-06 | 2026-03-06 | Complete | 100% | Recovered schedule
MS-04 | UAT Launch | Leah Kim | 2026-04-03 | 2026-04-07 | At Risk | 85% | Dependent on data fixes
MS-05 | Pilot Go-Live | Jonah Price | 2026-05-15 | 2026-05-22 | Planned | 55% | Cutover rehearsal pending
MS-06 | National Rollout | Maya Bennett | 2026-07-31 | 2026-08-07 | Planned | 28% | Awaiting phase-2 scope close
Risk Register
Risk ID | Risk Description | Owner | Probability | Impact | Rating | Response | Status
R-01 | Legacy customer records contain duplicate profiles that may delay UAT data loads. | Leah Kim | High | High | Critical | Run cleansing rules; add daily defect triage. | Open
R-02 | Vendor API throughput may be below target for launch volumes. | Ravi Solis | Medium | High | High | Performance test in rehearsal window. | Mitigating
R-03 | Regional managers may request additional analytics outside current scope. | Maya Bennett | Medium | Medium | Medium | Steer requests through change control. | Open
R-04 | Training attendance may dip during retail peak period. | Jonah Price | Low | Medium | Low | Offer recorded sessions and supervisor follow-up. | Monitoring
Issue Log
Issue ID | Issue Description | Owner | Raised | Target Close | Priority | Status | Resolution Action
I-01 | Duplicate customer IDs caused 7% mismatch in trial migration. | Data Team | 2026-03-05 | 2026-04-02 | High | Open | Cleanse source tables and rerun trial migration.
I-02 | One middleware specialist resigned mid-sprint. | PMO | 2026-02-11 | 2026-02-20 | Medium | Closed | Backfill contractor onboarded and knowledge transfer completed.
I-03 | Two training videos require legal review before release. | Change Lead | 2026-03-18 | 2026-04-01 | Medium | In Progress | Legal to complete review by end of month.
Action Items
Action ID | Action | Owner | Due Date | Status | Priority | Dependency | Comments
A-01 | Approve final training wave budget. | Executive Sponsor | 2026-04-01 | Open | High | Budget review | Needed before vendor booking.
A-02 | Complete cutover rehearsal checklist. | PMO | 2026-04-05 | In Progress | High | UAT readiness | 80% drafted.
A-03 | Validate API response times at peak load. | Tech Lead | 2026-04-08 | Open | Medium | Performance scripts | Scheduled in test window.
A-04 | Close legal review of training videos. | Legal | 2026-04-01 | Open | Medium | Compliance | Awaiting reviewer comments.
Change Requests
CR ID | Change Description | Requested By | Impact (Days) | Impact ($) | Decision | Status | Notes
CR-01 | Add advanced dashboard analytics to phase 1. | Regional Ops | 12 | 42000 | Deferred to Phase 2 | Closed | Avoided schedule impact on pilot.
CR-02 | Expand training wave to include franchise supervisors. | Change Lead | 4 | 9500 | Approved | Open | Budget approval pending.
CR-03 | Move loyalty integration ahead of returns workflow. | Client IT | 7 | 15000 | Under Review | Open | Architecture assessment underway.
Note on A16: Add one row per weekly / biweekly status period.
Note on A35: List the most material risks first to surface them on the dashboard.

## Instructions
How to Use This Project Status Report Template
Built for executive-ready reporting, fast updates, and repeatable PMO governance
Step | Guidance
1 | Purpose: Use the Main Template sheet to present a polished project status report for leadership, sponsors, clients, or steering committees.
2 | Where to edit: Enter and maintain source information on the Data Entry sheet. The Main Template reads from those source tables automatically.
3 | Reporting period selector: On Main Template, change the cell for Selected Reporting Period to switch the full report view between reporting cycles.
4 | What the template covers: This workbook captures project overview, overall health, progress, schedule, budget, scope, quality, resources, risk, milestones, issues, actions, change requests, decisions needed, and next steps.
5 | Status colors: Green = on track, Amber = watch / minor variance, Red = critical or needs escalation. Keep usage consistent across the workbook.
6 | Recommended cadence: Update weekly or biweekly. Refresh report data before governance meetings and month-end PMO reporting.
7 | Budget handling: Update Planned Spend and Actual Spend for each reporting period. Variance is calculated automatically on the dashboard.
8 | Milestone updates: Maintain baseline and forecast dates. Use status values such as Planned, At Risk, Complete, or Delayed and keep notes short but precise.
9 | Risk and issue management: Use concise descriptions, name an owner, and keep mitigation or resolution actions action-oriented. Review open items every cycle.
10 | Action items: Only include actions with clear ownership and due dates. High-priority actions should be ready for sponsor follow-up.
11 | Change requests: Log only formal changes. Capture time and cost impacts to support scope-control decisions.
12 | Presentation tip: Keep the Main Template clean. For live use, replace example content with your project details but preserve the structure and formulas.
Example organizations and names in this workbook are fictional and used only to make the template feel realistic.