## Main Template
PROJECT TIMELINE TEMPLATE
A polished, executive-ready project timeline with schedule, dependencies, milestones, budget and progress tracking
Project Snapshot | [8 empty] | Total Tasks |  |  | Milestones |  |  | Avg % Complete |  |  | Over Budget Tasks |  |  | At-Risk Items
Project | Aurora Campus Launch - Phase I |  |  | Project Manager | Jordan Hale |  |  |  | 12 |  |  | 2 |  |  | 45% |  |  | 1 |  |  | 2
Company | Northbridge Analytics |  |  | Sponsor | Elena Marquez
Client | City of Riverton Innovation Council |  |  | Location | Riverton, Colorado
Baseline Start | 2026-04-06 |  |  | Baseline Finish | 2026-09-18 |  |  |  | Legend
Budget | 1850000 |  |  | Cadence | Weekly |  |  |  | Completed
In Progress
Not Started
[9 empty] | Delayed | [6 empty] | Timeline View (Weekly)
[9 empty] | Milestone | [6 empty] | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21
WBS | Phase | Task / Milestone | Owner | Location | Start | Finish | Days | Dependency | Status | % | Plan $ | Actual $ | Var $ | Risk | Notes
1.0 | Initiation | Project Charter & Kickoff | Jordan Hale | Riverton HQ | 2026-04-06 | 2026-04-10 | 5 |  | Completed | 100% | 65000 | 62000 | -3000 | Low | Executive sign-off secured | bar: 2026-04-06
1.1 | Planning | Requirements Workshops | Maya Chen | Riverton HQ | 2026-04-13 | 2026-04-24 | 12 | 1.0 | Completed | 100% | 85000 | 83500 | -1500 | Low | Cross-functional requirements captured | bar: 2026-04-13 to 2026-04-20
1.2 | Planning | Site Survey & Permits | Liam Brooks | Riverton Campus | 2026-04-20 | 2026-05-15 | 26 | 1.0 | Completed | 100% | 120000 | 126000 | 6000 | Medium | Permit fees higher than planned | bar: 2026-04-20 to 2026-05-11
2.0 | Design | Concept Design Package | Sofia Patel | Denver Studio | 2026-04-27 | 2026-05-22 | 26 | 1.1 | Completed | 100% | 180000 | 176500 | -3500 | Low | Approved by sponsor | bar: 2026-04-27 to 2026-05-18
2.1 | Design | Detailed Design Review | Sofia Patel | Denver Studio | 2026-05-25 | 2026-06-05 | 12 | 2.0 | In Progress | 75% | 140000 | 110000 | -30000 | Medium | Awaiting fire safety comments | bar: 2026-05-25 to 2026-06-01
3.0 | Procurement | Vendor Sourcing & Bids | Noah Bennett | Remote / US | 2026-05-18 | 2026-06-12 | 26 | 1.2 | In Progress | 65% | 90000 | 58000 | -32000 | Medium | Two vendors shortlisted | bar: 2026-05-18 to 2026-06-08
3.1 | Procurement | Contract Award Milestone | Jordan Hale | Riverton HQ | 2026-06-15 | 2026-06-19 | 5 | 2.1,3.0 | Not Started | 0% | 25000 | 0 | -25000 | High | Board approval required | bar: 2026-06-15
4.0 | Execution | Core Construction | Ava Romero | Riverton Campus | 2026-06-22 | 2026-08-07 | 47 | 3.1 | Not Started | 0% | 720000 | 0 | -720000 | High | Weather and permit risk monitored | bar: 2026-06-22 to 2026-08-03
4.1 | Execution | Technology Installation | Ethan Cole | Riverton Campus | 2026-07-27 | 2026-08-21 | 26 | 4.0 | Not Started | 0% | 210000 | 0 | -210000 | Medium | Depends on utility activation | bar: 2026-07-27 to 2026-08-17
4.2 | Execution | Furniture & Wayfinding | Grace Monroe | Riverton Campus | 2026-08-03 | 2026-08-28 | 26 | 4.0 | Not Started | 0% | 110000 | 0 | -110000 | Low | Long lead items reserved | bar: 2026-08-03 to 2026-08-24
5.0 | Commissioning | Testing & Readiness | Priya Nair | Riverton Campus | 2026-08-24 | 2026-09-04 | 12 | 4.1,4.2 | Not Started | 0% | 65000 | 0 | -65000 | Medium | Readiness checklist prepared | bar: 2026-08-24 to 2026-08-31
5.1 | Closure | Launch Event Milestone | Elena Marquez | Riverton Campus | 2026-09-18 | 2026-09-18 | 1 | 5.0 | Not Started | 0% | 40000 | 0 | -40000 | Low | Media and stakeholder invites pending
Phase Progress Summary
Initiation | 100%
Planning | 100%
Design | 87.5%
Procurement | 32.5%
Execution | 0%
Commissioning | 0%
Closure | 0%
Sample data is fictional and can be replaced with your live project details.

## Data Entry
PROJECT TIMELINE — DATA ENTRY
This sample project is fictional and provided to make the template feel realistic.
Project Overview Inputs |  |  |  | Edit only white input cells in this sheet.
Project Name | Aurora Campus Launch - Phase I
Company | Northbridge Analytics
Client / Sponsor Organization | City of Riverton Innovation Council
Project Manager | Jordan Hale
Executive Sponsor | Elena Marquez
Primary Location | Riverton, Colorado
Baseline Start | 2026-04-06
Baseline Finish | 2026-09-18
Approved Budget | 1850000
Reporting Frequency | Weekly
WBS | Phase | Task / Milestone | Owner | Location | Start Date | Finish Date | Duration (Days) | Dependency | Status | % Complete | Planned Budget | Actual Cost | Variance | Risk | Notes
1.0 | Initiation | Project Charter & Kickoff | Jordan Hale | Riverton HQ | 2026-04-06 | 2026-04-10 | 5 |  | Completed | 100% | 65000 | 62000 | -3000 | Low | Executive sign-off secured
1.1 | Planning | Requirements Workshops | Maya Chen | Riverton HQ | 2026-04-13 | 2026-04-24 | 12 | 1.0 | Completed | 100% | 85000 | 83500 | -1500 | Low | Cross-functional requirements captured
1.2 | Planning | Site Survey & Permits | Liam Brooks | Riverton Campus | 2026-04-20 | 2026-05-15 | 26 | 1.0 | Completed | 100% | 120000 | 126000 | 6000 | Medium | Permit fees higher than planned
2.0 | Design | Concept Design Package | Sofia Patel | Denver Studio | 2026-04-27 | 2026-05-22 | 26 | 1.1 | Completed | 100% | 180000 | 176500 | -3500 | Low | Approved by sponsor
2.1 | Design | Detailed Design Review | Sofia Patel | Denver Studio | 2026-05-25 | 2026-06-05 | 12 | 2.0 | In Progress | 75% | 140000 | 110000 | -30000 | Medium | Awaiting fire safety comments
3.0 | Procurement | Vendor Sourcing & Bids | Noah Bennett | Remote / US | 2026-05-18 | 2026-06-12 | 26 | 1.2 | In Progress | 65% | 90000 | 58000 | -32000 | Medium | Two vendors shortlisted
3.1 | Procurement | Contract Award Milestone | Jordan Hale | Riverton HQ | 2026-06-15 | 2026-06-19 | 5 | 2.1,3.0 | Not Started | 0% | 25000 | 0 | -25000 | High | Board approval required
4.0 | Execution | Core Construction | Ava Romero | Riverton Campus | 2026-06-22 | 2026-08-07 | 47 | 3.1 | Not Started | 0% | 720000 | 0 | -720000 | High | Weather and permit risk monitored
4.1 | Execution | Technology Installation | Ethan Cole | Riverton Campus | 2026-07-27 | 2026-08-21 | 26 | 4.0 | Not Started | 0% | 210000 | 0 | -210000 | Medium | Depends on utility activation
4.2 | Execution | Furniture & Wayfinding | Grace Monroe | Riverton Campus | 2026-08-03 | 2026-08-28 | 26 | 4.0 | Not Started | 0% | 110000 | 0 | -110000 | Low | Long lead items reserved
5.0 | Commissioning | Testing & Readiness | Priya Nair | Riverton Campus | 2026-08-24 | 2026-09-04 | 12 | 4.1,4.2 | Not Started | 0% | 65000 | 0 | -65000 | Medium | Readiness checklist prepared
5.1 | Closure | Launch Event Milestone | Elena Marquez | Riverton Campus | 2026-09-18 | 2026-09-18 | 1 | 5.0 | Not Started | 0% | 40000 | 0 | -40000 | Low | Media and stakeholder invites pending
Sample data is fictional and can be replaced with your live project details.

## Instructions
HOW TO USE THIS PROJECT TIMELINE TEMPLATE
Built in a senior-project-manager style for schedule control, executive reporting and day-to-day project administration.
1. Purpose of the workbook
This workbook is designed to plan, track and communicate a full project timeline. The Main Template sheet gives leaders a polished view of schedule health, milestones, budget and risks. The Data Entry sheet is the controlled input area. The Instructions sheet explains setup and ongoing use.
2. What the template explains
The template covers project overview, task sequencing, dependencies, milestones, start and finish dates, durations, ownership, locations, status, percent complete, planned budget, actual cost, variance, risk level and a weekly Gantt-style timeline.
3. Recommended workflow
Step 1: Update project overview fields in Data Entry. Step 2: Add, remove or edit task rows in Data Entry. Step 3: Keep start date, finish date, status, percent complete, budget and cost current. Step 4: Review the Main Template for executive reporting. Step 5: Save a fresh version for each reporting cycle if you need historical snapshots.
4. Input guidance
Use Start Date and Finish Date for every row. Duration calculates automatically. Variance also calculates automatically as Actual Cost minus Planned Budget. Status and Risk use dropdown lists for consistency. Milestones can be identified by naming the task with the word 'Milestone'.
5. Color logic
Dark blue headers = structure and section titles. Green = completed or healthy progress. Gold / orange = in-progress or attention items. Red = delayed or budget pressure. Blue timeline bars = planned / not started work. Light fills = user input zones and supporting notes.
6. Good project-management practice
Keep dependencies realistic, update percent complete weekly, highlight high-risk tasks early, and compare planned vs actual cost before steering meetings. Use concise notes that explain exceptions, not routine work.
Color Reference
Executive headers
Section headers
Completed
In Progress
Delayed / critical
Milestone highlight
Planned / not started bar
Sample data is fictional and can be replaced with your live project details.