## Main Template
Projects Prioritization Matrix
Executive portfolio view for Aurora Meridian Holdings – hypothetical PMO example
Total Projects |  |  |  | Approved / Priority |  |  |  | Avg Weighted Score |  |  |  | High Risk Burdens
8 |  |  |  | 4 |  |  |  | 3.6812 |  |  |  | 4
What this template explains | [6 empty] | Weighted scoring model |  |  |  | Priority bands
Business Value | Growth, cost savings, productivity, and competitive advantage. | [5 empty] | Business Value | 20% |  |  | Tier 1 | 4.2–5.0 | Fund Immediately
Strategic Alignment | Fit with annual strategy, transformation agenda, and leadership priorities. | [5 empty] | Strategic Alignment | 15% |  |  | Tier 2 | 3.5–4.1 | Phase in this quarter
Urgency | Deadline pressure from market timing, commitments, or operational pain points. | [5 empty] | Urgency / Time Sensitivity | 10% |  |  | Tier 3 | 2.8–3.4 | Refine business case
Expected ROI | Relative measurable return compared with cost and effort. | [5 empty] | Expected ROI | 15% |  |  | Watchlist | <2.8 | Hold / re-scope
Customer Impact | Influence on clients, patients, employees, or service quality. | [5 empty] | Customer Impact | 10%
Compliance Need | Regulatory, audit, legal, or policy-driven necessity. | [5 empty] | Regulatory / Compliance Need | 10%
Feasibility | Likelihood of success with current capabilities, budget, and sponsorship. | [5 empty] | Feasibility | 8%
Burden Factors | Resource demand, complexity, and delivery risk reduce priority through inverse scoring. | [5 empty] | Resource Demand (inverse) | 5%
[7 empty] | Complexity (inverse) | 4%
[7 empty] | Risk Level (inverse) | 3%
[7 empty] | Weight Total | 100%
Rank | Project Name | Sponsor | Business Unit | Status | Value | Align. | Urgency | ROI | Impact | Compliance | Feasibility | Avg Burden | Weighted Score | Priority Band | Recommendation
5 | Orion ERP Modernization | Lena Brooks | Finance | In Review | 5 | 5 | 4 | 4 | 3 | 2 | 3 | 1.3333 | 3.64 | Tier 2 | Phase in this quarter
3 | Apollo CX Mobile App | Miguel Santos | Customer Experience | Approved | 4 | 4 | 5 | 5 | 5 | 1 | 4 | 3 | 3.93 | Tier 2 | Phase in this quarter
1 | Beacon Cyber Resilience | Aisha Morgan | Technology | Priority Candidate | 5 | 5 | 5 | 3 | 4 | 5 | 4 | 1.6667 | 4.13 | Tier 2 | Phase in this quarter
7 | Summit Warehouse Automation | Daniel Price | Operations | In Review | 4 | 4 | 3 | 4 | 3 | 1 | 3 | 1.6667 | 3.13 | Tier 3 | Refine business case
4 | Horizon ESG Reporting Hub | Priya Kapoor | Corporate Affairs | Approved | 3 | 5 | 4 | 3 | 3 | 5 | 4 | 4 | 3.8 | Tier 2 | Phase in this quarter
6 | Atlas Sales Intelligence | Noah Bennett | Commercial | Pipeline | 4 | 4 | 3 | 5 | 4 | 1 | 4 | 3 | 3.63 | Tier 2 | Phase in this quarter
8 | Nova Talent Learning Portal | Grace Chen | People & Culture | Pipeline | 3 | 3 | 2 | 3 | 4 | 1 | 5 | 4.3333 | 3.11 | Tier 3 | Refine business case
2 | Pulse Patient Portal Upgrade | Hannah Reed | Healthcare Services | Priority Candidate | 5 | 4 | 5 | 4 | 5 | 4 | 3 | 2 | 4.08 | Tier 2 | Phase in this quarter
Hypothetical example only — Aurora Meridian Holdings, Northstar Ventures PMO, sponsors, and locations are fictional and included for illustrative realism.

## Data Entry
Northstar Ventures PMO ¦ Projects Prioritization Matrix – Data Entry
Enter or update project attributes below. Scores use a 1–5 scale where 5 = strongest / highest positive impact.
Scoring Weights
| Business Value | 20%
| Strategic Alignment | 15%
| Urgency / Time Sensitivity | 10%
| Expected ROI | 15%
| Customer Impact | 10%
| Regulatory / Compliance Need | 10%
| Feasibility | 8%
| Resource Demand (inverse) | 5%
| Complexity (inverse) | 4%
| Risk Level (inverse) | 3%
| Total Weight | 100%
ID | Project Name | Sponsor | Business Unit | Location | Status | Business Value | Strategic Alignment | Urgency | Expected ROI | Customer Impact | Compliance Need | Feasibility | Resource Demand | Complexity | Risk Level
P-101 | Orion ERP Modernization | Lena Brooks | Finance | Chicago, IL | In Review | 5 | 5 | 4 | 4 | 3 | 2 | 3 | 5 | 5 | 4
P-102 | Apollo CX Mobile App | Miguel Santos | Customer Experience | Austin, TX | Approved | 4 | 4 | 5 | 5 | 5 | 1 | 4 | 3 | 3 | 3
P-103 | Beacon Cyber Resilience | Aisha Morgan | Technology | Seattle, WA | Priority Candidate | 5 | 5 | 5 | 3 | 4 | 5 | 4 | 4 | 4 | 5
P-104 | Summit Warehouse Automation | Daniel Price | Operations | Denver, CO | In Review | 4 | 4 | 3 | 4 | 3 | 1 | 3 | 5 | 4 | 4
P-105 | Horizon ESG Reporting Hub | Priya Kapoor | Corporate Affairs | New York, NY | Approved | 3 | 5 | 4 | 3 | 3 | 5 | 4 | 2 | 2 | 2
P-106 | Atlas Sales Intelligence | Noah Bennett | Commercial | Atlanta, GA | Pipeline | 4 | 4 | 3 | 5 | 4 | 1 | 4 | 3 | 3 | 3
P-107 | Nova Talent Learning Portal | Grace Chen | People & Culture | Boston, MA | Pipeline | 3 | 3 | 2 | 3 | 4 | 1 | 5 | 2 | 2 | 1
P-108 | Pulse Patient Portal Upgrade | Hannah Reed | Healthcare Services | Nashville, TN | Priority Candidate | 5 | 4 | 5 | 4 | 5 | 4 | 3 | 4 | 4 | 4
Note on G17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on H17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on I17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on J17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on K17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on L17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on M17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on N17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on O17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.
Note on P17: Scoring scale: 1 = low / unfavorable, 3 = moderate, 5 = high / favorable. For Resource Demand, Complexity, and Risk Level, high scores indicate more burden; the main template inverses them.

## Instructions
How to Use the Projects Prioritization Matrix
Designed as a PMO-ready decision tool for portfolio review, governance forums, and executive steering committees.
Step | Area | Guidance
1 | Update weights in Data Entry | Adjust the scoring weights in cells B4:C13 of the Data Entry sheet so the model reflects your organization's decision criteria. The total must remain 100.0%.
2 | Enter or replace projects | Overwrite the sample projects from row 18 onward in Data Entry with your own pipeline, active, or proposed initiatives. Keep scores on a 1–5 scale.
3 | Interpret inverse burden | Resource Demand, Complexity, and Risk Level are entered naturally (5 = high burden). The main template automatically converts them into inverse positive scores so high burden lowers priority.
4 | Read the main template | The Main Template sheet calculates weighted project scores, rank order, priority bands, and recommendations automatically using formulas linked to Data Entry.
5 | Use the matrix in governance | Use Tier 1 for immediate funding or executive backing, Tier 2 for near-term scheduling, Tier 3 for business-case refinement, and Watchlist for re-scope or defer decisions.
6 | Suggested scoring discipline | Use cross-functional scoring sessions with a sponsor, finance lead, PMO analyst, and delivery owner to reduce bias and improve consistency.
7 | Example context included | This workbook uses hypothetical organizations, sponsors, business units, and city locations to make the template feel realistic while remaining illustrative.
Scoring Reference
1 | Score Meaning | Very low / poor fit / weak case / severe burden
2 | Score Meaning | Low / below target / limited benefit
3 | Score Meaning | Moderate / acceptable / neutral
4 | Score Meaning | Strong / attractive / above average
5 | Score Meaning | Very strong / critical / exceptional impact