## Main Template
Punch List
Project | [6 empty] | Horizon Point HQ Fit-Out ¦ Apex Meridian Developments
Location |  |  | Riverside Business Park, Chicago |  |  |  | Client |  |  | NorthGate Capital Advisory
PM / Coordinator |  |  | Olivia Hart ¦ Senior Project Manager |  |  |  | Report Date |  |  | 2026-04-15
Total Items |  |  | Open |  |  | In Progress |  |  | Pending Verification |  |  | Closed
16 |  |  | 8 |  |  | 3 |  |  | 1 |  |  | 4
Management Summary | [7 empty] | Status Legend
High Priority Open |  |  | 3 |  |  |  |  | Open |  | In Progress |  | Pending Verification
Overdue Open / WIP |  |  | 12 |  |  |  |  | Closed |  | High Priority |  | Low Priority
Average Days Open |  |  | 32.5625
Estimated Open Cost |  |  | 3370 |  |  |  |  | Tip: Update the 'Data Entry' sheet only. The dashboard refreshes automatically.
Live Punch List Register (linked from Data Entry)
Item ID | Area / Location | Discipline | Issue Description | Priority | Assigned To | Date Identified | Target Date | Status | Days Open | Sign-Off | Cost Impact
PL-001 | North Tower Lobby | Finishes | Touch up paint scratches near reception desk. | Medium | Maya Patel | 2026-03-03 | 2026-03-08 | Open | 43 | Pending | 350 |  | Status | Count
PL-002 | Level 02 Boardroom | Electrical | Loose power outlet under conference table. | High | Owen Carter | 2026-03-01 | 2026-03-04 | Closed | 2 | Approved | 180 |  | Open | 8
PL-003 | Level 05 Pantry | Plumbing | Pantry sink trap leaking under basin. | High | Noah Bennett | 2026-03-02 | 2026-03-05 | In Progress | 44 | Pending | 420 |  | In Progress | 3
PL-004 | South Wing Corridor | Finishes | Replace cracked ceiling tile outside HR office. | Low | Emma Clarke | 2026-02-27 | 2026-03-06 | Open | 47 | Pending | 95 |  | Pending Verification | 1
PL-005 | Executive Suite 3A | Doors & Hardware | Install missing brushed-steel door handle. | Medium | Lucas Green | 2026-03-04 | 2026-03-07 | Open | 42 | Pending | 125 |  | Closed | 4
PL-006 | Main Server Room | HVAC | Air balancing required; room temperature above target. | High | Harper Lewis | 2026-03-01 | 2026-03-05 | Closed | 4 | Approved | 860
PL-007 | Cafeteria | Safety | Install anti-slip strip at service counter step. | High | Ethan Ross | 2026-03-05 | 2026-03-06 | Open | 41 | Pending | 210
PL-008 | Parking Ramp Entry | Civil | Repair chipped concrete edge at vehicle barrier. | Medium | Grace Turner | 2026-03-02 | 2026-03-10 | In Progress | 44 | Pending | 600 |  | Discipline | Open Items
PL-009 | Reception WC | Plumbing | Adjust flush valve to stop continuous running water. | Medium | Jack Wilson | 2026-03-03 | 2026-03-06 | Closed | 3 | Approved | 140 |  | Electrical | 0
PL-010 | Training Room B | Audio Visual | Projector alignment and image focus need correction. | Low | Chloe Adams | 2026-03-04 | 2026-03-09 | Open | 42 | Pending | 275 |  | Finishes | 4
PL-011 | Open Office East | Furniture | Replace damaged workstation privacy panel. | Low | Benjamin Hall | 2026-03-05 | 2026-03-12 | Open | 41 | Pending | 310 |  | Plumbing | 1
PL-012 | Roof Access Door | Safety | Add warning signage and self-closing check. | High | Ella Mitchell | 2026-03-05 | 2026-03-07 | Pending Verification | 41 | Pending | 155 |  | HVAC | 0
PL-013 | Gym & Wellness | MEP | Diffuser grille rattles during full-load operation. | Medium | James Parker | 2026-03-06 | 2026-03-11 | Open | 40 | Pending | 230 |  | Safety | 2
PL-014 | Client Experience Center | Finishes | Replace vinyl graphic with revised branding panel. | Medium | Aria Morgan | 2026-03-02 | 2026-03-09 | In Progress | 44 | Pending | 540 |  | Civil | 1
PL-015 | Stairwell B | Life Safety | Emergency light battery failed duration test. | High | Henry Scott | 2026-03-01 | 2026-03-04 | Closed | 3 | Approved | 260 |  | Audio Visual | 1
[13 empty] | MEP | 1

## Data Entry
Data Entry ¦ Apex Meridian Developments ¦ Horizon Point HQ Fit-Out Punch List Register
Item ID | Area / Location | Floor / Zone | Discipline | Issue Description | Priority | Assigned To | Reported By | Date Identified | Target Date | Actual Completion | Status | Days Open | Inspector Comments | QA / Client Sign-Off | Photo Ref. | Vendor / Contractor | Cost Impact ($)
PL-001 | North Tower Lobby | Ground | Finishes | Touch up paint scratches near reception desk. | Medium | Maya Patel | Daniel Brooks | 2026-03-03 | 2026-03-08 |  | Open | 43 | Awaiting painter visit. | Pending | IMG-NTL-001 | BluePeak Interiors | 350
PL-002 | Level 02 Boardroom | L2 | Electrical | Loose power outlet under conference table. | High | Owen Carter | Ava Simmons | 2026-03-01 | 2026-03-04 | 2026-03-03 | Closed | 2 | Verified safe after retest. | Approved | IMG-L2-004 | VoltEdge Services | 180
PL-003 | Level 05 Pantry | L5 | Plumbing | Pantry sink trap leaking under basin. | High | Noah Bennett | Liam Foster | 2026-03-02 | 2026-03-05 |  | In Progress | 44 | Parts delivered; final seal pending. | Pending | IMG-L5-002 | AquaWorks MEP | 420
PL-004 | South Wing Corridor | L3 | Finishes | Replace cracked ceiling tile outside HR office. | Low | Emma Clarke | Sofia Reed | 2026-02-27 | 2026-03-06 |  | Open | 47 | Material available in store. | Pending | IMG-SWC-008 | Vertex Build Co. | 95
PL-005 | Executive Suite 3A | L3 | Doors & Hardware | Install missing brushed-steel door handle. | Medium | Lucas Green | Daniel Brooks | 2026-03-04 | 2026-03-07 |  | Open | 42 | Door delivered to site. | Pending | IMG-EX3A-003 | NorthGate Projects | 125
PL-006 | Main Server Room | Ground | HVAC | Air balancing required; room temperature above target. | High | Harper Lewis | Ava Simmons | 2026-03-01 | 2026-03-05 | 2026-03-05 | Closed | 4 | Rebalanced and trend log accepted. | Approved | IMG-SR-010 | ClimaCore Systems | 860
PL-007 | Cafeteria | L1 | Safety | Install anti-slip strip at service counter step. | High | Ethan Ross | Liam Foster | 2026-03-05 | 2026-03-06 |  | Open | 41 | Safety risk noted during walkthrough. | Pending | IMG-CAF-005 | SafePath Facilities | 210
PL-008 | Parking Ramp Entry | Basement | Civil | Repair chipped concrete edge at vehicle barrier. | Medium | Grace Turner | Sofia Reed | 2026-03-02 | 2026-03-10 |  | In Progress | 44 | Concrete patch curing. | Pending | IMG-PR-002 | UrbanAxis Contractors | 600
PL-009 | Reception WC | Ground | Plumbing | Adjust flush valve to stop continuous running water. | Medium | Jack Wilson | Daniel Brooks | 2026-03-03 | 2026-03-06 | 2026-03-06 | Closed | 3 | Function tested successfully. | Approved | IMG-WC-007 | AquaWorks MEP | 140
PL-010 | Training Room B | L4 | Audio Visual | Projector alignment and image focus need correction. | Low | Chloe Adams | Ava Simmons | 2026-03-04 | 2026-03-09 |  | Open | 42 | Vendor revisit booked. | Pending | IMG-TRB-006 | SignalVista AV | 275
PL-011 | Open Office East | L2 | Furniture | Replace damaged workstation privacy panel. | Low | Benjamin Hall | Sofia Reed | 2026-03-05 | 2026-03-12 |  | Open | 41 | Manufacturer confirmed replacement. | Pending | IMG-OOE-011 | WorkSphere Furnishings | 310
PL-012 | Roof Access Door | Roof | Safety | Add warning signage and self-closing check. | High | Ella Mitchell | Liam Foster | 2026-03-05 | 2026-03-07 |  | Pending Verification | 41 | Waiting for consultant sign-off. | Pending | IMG-RAD-001 | NorthGate Projects | 155
PL-013 | Gym & Wellness | L1 | MEP | Diffuser grille rattles during full-load operation. | Medium | James Parker | Ava Simmons | 2026-03-06 | 2026-03-11 |  | Open | 40 | Noise observed only at max fan speed. | Pending | IMG-GYM-004 | ClimaCore Systems | 230
PL-014 | Client Experience Center | Ground | Finishes | Replace vinyl graphic with revised branding panel. | Medium | Aria Morgan | Daniel Brooks | 2026-03-02 | 2026-03-09 |  | In Progress | 44 | New artwork approved by client. | Pending | IMG-CEC-003 | BluePeak Interiors | 540
PL-015 | Stairwell B | All | Life Safety | Emergency light battery failed duration test. | High | Henry Scott | Liam Foster | 2026-03-01 | 2026-03-04 | 2026-03-04 | Closed | 3 | Retest passed 90-minute requirement. | Approved | IMG-STB-009 | VoltEdge Services | 260
PL-016 | Level 06 Quiet Room | L6 | Finishes | Silicone touch-up required at skirting joint. | Low | Scarlett King | Sofia Reed | 2026-03-06 | 2026-03-13 |  | Open | 40 | Minor cosmetic issue. | Pending | IMG-QR-002 | Vertex Build Co. | 60
Formulas:
Days Open = IF(OR([Date Identified]="",[Status]="Closed"),IF([Status]="Closed",[Actual Completion]-[Date Identified],""),TODAY()-[Date Identified])

## Instructions
How to Use This Punch List Workbook
1. Purpose | This workbook tracks defects, incomplete works, corrective actions, sign-offs, accountability, target dates, and close-out readiness for a project handover.
2. Where to update | Only type or edit records on the 'Data Entry' sheet. The 'Main Template' dashboard and linked register update automatically.
3. Required fields | Complete: Item ID, Area / Location, Discipline, Issue Description, Priority, Assigned To, Date Identified, Target Date, Status, and QA / Client Sign-Off.
4. Status logic | Use Open for new issues, In Progress while work is underway, Pending Verification when work is complete but awaiting inspection, and Closed only after acceptance.
5. Priority guidance | High = critical safety / business impact, Medium = important but manageable, Low = cosmetic or minor snag.
6. Sign-off workflow | Keep sign-off as Pending until the inspector or client verifies the work. Change to Approved or Rejected after review.
7. Formula fields | Days Open, KPI cards, charts, overdue counts, and summary metrics are formula-driven. Do not overwrite those cells.
8. Good PM practice | Review high-priority and overdue items first, assign one accountable owner per item, and update dates immediately after each site walk.
Color & Visual Guide
Dark Navy #000C7B | Major titles / section headers
Light Background #F4F8FF | Column headers and KPI cards
Teal #35B5A0 | Closed items, positive progress, approved completion
Blue Accent #1477C4 | Work in progress / caution
Purple #5E60CE | Pending verification / items awaiting checks
Violet #7A6FF0 | Open critical issues / risk / overdue focus
Recommended Review Cadence: Daily site walk + twice-weekly client close-out review + final pre-handover verification meeting.