## Main RACI Template
RACI Matrix
Project Name | Orion ERP Transformation |  |  |  | Primary Location | Chicago Innovation Hub |  |  |  | Project Phase | Execution & Hypercare Planning
Client | Northwind Foods Ltd. |  |  |  | Steering Committee | Executive PMO / Finance / Operations |  |  |  | Delivery Model | Hybrid Agile-Waterfall
Project Sponsor | Evelyn Brooks |  |  |  | Version | v1.0 |  |  |  | Status | Amber
Project Manager | Daniel Mercer, PMP |  |  |  | Report Date | 2026-04-15 |  |  |  | Purpose | Clarify ownership, approvals, consultation paths, and communications.
Total Tasks |  |  | Tasks w/ Missing R |  |  | Tasks w/ Missing A |  |  | High-Risk Rows |  |  | On-Track Tasks |  |  | Legend
14 |  |  | 1 |  |  | 0 |  |  | 4 |  |  | 10 |  |  | R | Responsible — does the work
[15 empty] | A | Accountable — final owner / approver
[15 empty] | C | Consulted — provides input
Work Breakdown, Stakeholders, RACI Assignments, and Governance Checks
WBS | Phase | Task / Activity | Deliverable / Decision | Department | Target Date | Status | Project Manager Daniel Mercer | Sponsor Evelyn Brooks | Ops Lead Marcus Hill | Finance Lead Priya Shah | QA Manager Sofia Ramirez | Client Rep Noah Chen | HRBP Ava Collins | IT Lead Liam Patel | Notes | R Check | A Check | Risk Flag | Health
1.0 | Initiation | Approve project charter | Signed charter | PMO | 2026-04-03 | Complete | I | A | C | C | I | R | I | I | Approved in steering committee | OK | OK | Controlled | On Track
1.1 | Initiation | Confirm business case assumptions | Validated benefits case | Finance | 2026-04-05 | Complete | R | A | C | R | I | C | I | I | Benefits refined for FY27 planning | OK | OK | Controlled | On Track
1.2 | Planning | Define scope baseline | Scope statement | PMO | 2026-04-08 | On Track | R | A | C | C | I | C | I | I | Includes plants in Chicago and Columbus | OK | OK | Controlled | On Track
1.3 | Planning | Build integrated plan | Master schedule | PMO | 2026-04-10 | On Track | A | I | C | I | I | I | I | R | Dependency map issued | OK | OK | Controlled | On Track
2.0 | Design | Document future-state process | Process design pack | Operations | 2026-04-14 | On Track | C | A | R | C | C | R | I | I | Cross-functional workshops ongoing | OK | OK | Controlled | On Track
2.1 | Design | Approve chart of accounts changes | COA decision | Finance | 2026-04-16 | At Risk | C | A | I | R | I | C | I | I | Pending tax input | OK | OK | Needs Attention | Review
2.2 | Design | Define testing strategy | Test strategy | Quality | 2026-04-18 | On Track | C | I | C | I | A | C | I | R | SIT/UAT entry-exit criteria included | OK | OK | Controlled | On Track
3.0 | Build | Configure ERP roles | Security role matrix | IT | 2026-04-22 | On Track | C | I | C | I | C | I | C | A | Segregation-of-duties review planned | Missing Responsible | OK | Needs Attention | Review
3.1 | Build | Create training curriculum | Training plan | HR | 2026-04-24 | Not Started | C | I | I | I | C | C | A | R | Change impact summary required | OK | OK | Controlled | On Track
3.2 | Build | Prepare cutover checklist | Cutover runbook | PMO | 2026-04-27 | At Risk | R | A | R | C | C | I | I | R | Weekend support model under review | Too Many R | OK | Needs Attention | Review
4.0 | Test | Execute SIT cycles | SIT defect log | Quality | 2026-05-01 | Not Started | I | I | C | I | A | C | I | R | Entry after build freeze | OK | OK | Controlled | On Track
4.1 | Test | Approve UAT readiness | UAT go/no-go | PMO | 2026-05-05 | Not Started | R | A | C | C | C | R | I | C | Requires training and data sign-off | OK | OK | Controlled | On Track
5.0 | Deploy | Authorize production cutover | Go-live approval | Executive PMO | 2026-05-10 | Not Started | C | A | R | C | C | R | I | R | Executive decision gate | Too Many R | OK | Needs Attention | Review
5.1 | Hypercare | Review adoption metrics | Hypercare dashboard | PMO | 2026-05-17 | Not Started | A | I | R | C | C | C | C | R | Daily stand-up for first 2 weeks | OK | OK | Controlled | On Track
Note on A1: Hypothetical workbook prepared for ApexNova Consulting and Northwind Foods Ltd. All names, organizations, and locations are fictional.

## Data Entry
Data Entry
Project Role Directory |  |  |  | Lookup Lists |  |  | Sample Task Bank
Role | Person | Function | Location | Statuses | Phases | Departments | WBS | Phase | Task | Department | Default Status | Suggested Notes
Project Manager | Daniel Mercer, PMP | PMO | Chicago | Not Started | Initiation | PMO | 1.0 | Initiation | Approve project charter | PMO | Complete | Approved in steering committee
Project Sponsor | Evelyn Brooks | Executive PMO | Chicago | On Track | Planning | Operations | 1.1 | Initiation | Confirm business case assumptions | Finance | Complete | Benefits refined for FY27 planning
Operations Lead | Marcus Hill | Operations | Columbus | At Risk | Design | Finance | 1.2 | Planning | Define scope baseline | PMO | On Track | Includes plants in Chicago and Columbus
Finance Lead | Priya Shah, CPA | Finance | Chicago | Complete | Build | Quality | 1.3 | Planning | Build integrated plan | PMO | On Track | Dependency map issued
QA Manager | Sofia Ramirez | Quality | Dallas |  | Test | HR | 2.0 | Design | Document future-state process | Operations | On Track | Cross-functional workshops ongoing
Client Representative | Noah Chen | Business | Chicago |  | Deploy | IT | 2.1 | Design | Approve chart of accounts changes | Finance | At Risk | Pending tax input
HR Business Partner | Ava Collins | HR | Columbus |  | Hypercare | Executive PMO | 2.2 | Design | Define testing strategy | Quality | On Track | SIT/UAT entry-exit criteria included
IT Lead | Liam Patel | IT | Austin |  |  |  | 3.0 | Build | Configure ERP roles | IT | On Track | Segregation-of-duties review planned
[7 empty] | 3.1 | Build | Create training curriculum | HR | Not Started | Change impact summary required
[7 empty] | 3.2 | Build | Prepare cutover checklist | PMO | At Risk | Weekend support model under review
Project Assumptions / Tailoring Notes | [6 empty] | 4.0 | Test | Execute SIT cycles | Quality | Not Started | Entry after build freeze
• Use one Accountable owner per row wherever possible. | [6 empty] | 4.1 | Test | Approve UAT readiness | PMO | Not Started | Requires training and data sign-off
• Use one or two Responsible roles; more than two may indicate unclear execution ownership. | [6 empty] | 5.0 | Deploy | Authorize production cutover | Executive PMO | Not Started | Executive decision gate
• Consulted should be limited to true subject-matter contributors. | [6 empty] | 5.1 | Hypercare | Review adoption metrics | PMO | Not Started | Daily stand-up for first 2 weeks
• Informed is for stakeholders who need visibility but not decision rights.
• Amber / At Risk tasks should be reviewed in weekly PMO governance.
Note on A1: Use this sheet to maintain standard dropdown values, role names, and sample tasks.

## Instructions
Instructions — How to Use This RACI Template
What this workbook explains
1. Project information: project identity, sponsor, manager, phase, status, and governance context.
2. Task ownership: who is Responsible, Accountable, Consulted, and Informed for each major activity or decision.
3. Workflow accountability: whether each row has a clear executor and a single final owner.
4. Department involvement: which teams participate in planning, design, build, testing, deployment, and hypercare.
5. Approval structure and communication needs: who approves, who advises, and who simply receives updates.
6. Governance checks: formulas flag missing owners, too many owners, and rows that need attention.
Recommended usage steps
Step 1 — Update the project information area on the Main RACI Template sheet.
Step 2 — Tailor the role names in row 13 so they match your actual team members or functions.
Step 3 — Add, remove, or edit tasks starting in row 14. Use one row per meaningful deliverable, decision, or activity.
Step 4 — Enter only R, A, C, or I in the stakeholder columns. Use the legend on the right for quick reference.
Step 5 — Review the R Check, A Check, Risk Flag, and Health columns weekly in governance meetings.
Step 6 — Use the Data Entry sheet for role lookups, sample tasks, and standardized dropdown values.
Best-practice rules | Color guide
• Each task should usually have exactly one A. | Dark Blue | Workbook titles / major headers
• Most tasks should have at least one R. | Deep Navy | Section bars / governance blocks
• Too many C's often slow decisions. | Blue | Column headers / Informed
• Use I for visibility, not approval. | Dark Green | Responsible
• Align the matrix with meeting cadence and reporting needs. | Red | Accountable / issue emphasis
| Gold | Consulted / caution
| Green | Healthy / complete / on track
Note on A1: Follow the steps here when adapting the template for a live project.