## Main Template
RESOURCE PLAN
Project Snapshot | [7 empty] | Control Metrics | [7 empty] | Decision Notes
Company | BluePeak Infrastructure Ltd. |  | Project Manager | Aisha Sterling |  |  |  | Total Resources | 12 |  | Total Planned Hours | 4110 |  |  |  | • Maintain overall team utilization between 80% and 90%.
Project | Aurora Metro Station Upgrade |  | Planning Start | 2026-04-01 | [11 empty] | • Escalate any negative gap, double-booked asset or unavailable critical skill.
Location | Riverton Central District |  | Planning End | 2026-09-30 |  |  |  | Total Capacity Hours | 10278 |  | Total Planned Cost | 559956 |  |  |  | • Refresh monthly demand forecast after every baseline change or approved variation.
Average Utilization |  |  |  | Overallocated Resources |  |  |  | Conflict Flags |  |  |  | High Priority Active Roles |  |  |  | External Spend |  |  | Available Headroom
38.17% |  |  |  | 0 |  |  |  | 0 |  |  |  | 4 |  |  |  | 130304 |  |  | 6168
MONTHLY DEMAND VS CAPACITY
Month | Demand Hrs | Planned Hrs | Variance Hrs | Coverage %
Apr-26 | 1680 | 596 | -1084 | 35.48%
May-26 | 1920 | 686 | -1234 | 35.73%
Jun-26 | 2080 | 764 | -1316 | 36.73%
Jul-26 | 2160 | 796 | -1364 | 36.85%
Aug-26 | 2000 | 688 | -1312 | 34.4%
Sep-26 | 1760 | 580 | -1180 | 32.95%
RESOURCE DEPLOYMENT REGISTER
Res ID | Resource | Role | Type | Source | Skill | Location | Status | Avail % | Monthly Cap | Total Alloc | Util % | Rate/hr | Cost | Gap | Conflict | Priority | Action Owner | Notes | Management Actions
R-001 | Noah Bennett | Project Director | Human | PMO | Governance & client steering | Riverton | Active | 60% | 104 | 266 | 42.63% | 185 | 49210 | 358 | OK | High | Aisha Sterling | Executive oversight; maintain stakeholder cadence | 1. Secure backup crane slots for July peak demand.
R-002 | Aisha Sterling | Project Manager | Human | PMO | Integrated project control | Riverton | Active | 100% | 173 | 772 | 74.37% | 145 | 111940 | 266 | OK | High | Aisha Sterling | Core owner of baseline, RAIDs and reporting | 2. Confirm commissioning engineer mobilization by June 15.
R-003 | Leo Park | Construction Lead | Human | Site Ops | Civil supervision | Riverton | Active | 100% | 173 | 630 | 60.69% | 118 | 74340 | 408 | OK | High | Maria Kline | Peak load in structural work packages | 3. Review subcontractor concrete productivity after May close.
R-004 | Mia Chen | Scheduler | Human | Project Controls | Primavera P6 & EV tracking | Riverton | Active | 90% | 156 | 490 | 52.35% | 110 | 53900 | 446 | OK | Medium | Aisha Sterling | Supports look-ahead and baseline updates | 4. Monitor PM and scheduler utilization weekly to avoid burnout.
R-005 | Ethan Brooks | Cost Engineer | Human | Project Controls | Forecasting & accruals | Riverton | Active | 85% | 147 | 434 | 49.21% | 105 | 45570 | 448 | OK | Medium | Aisha Sterling | Heavy close support month-end | 5. Shift survey drone support to twice-weekly during structural package.
R-006 | Sophia Alvarez | QA/QC Manager | Human | Quality | Testing & assurance | Riverton | Active | 85% | 147 | 254 | 28.8% | 98 | 24892 | 628 | OK | High | Leo Park | Demand rises during testing & handover
R-007 | Harbor Crane 12T | Equipment | Equipment | Fleet Vendor | Lifting operations | Riverton Yard | Booked | 95% | 164 | 328 | 33.33% | 320 | 104960 | 656 | OK | High | Vendor PM | Reserved until structural steel complete | Risk & Escalation Watchlist
R-008 | RapidMix Concrete Crew | External Crew | Human | BuildFast Contractors | Concrete pours | Riverton | Booked | 100% | 173 | 288 | 27.75% | 88 | 25344 | 750 | OK | High | Procurement Lead | Subcontractor supports mid-phase pours | • Crane is near full utilization; any delay may affect steel lift sequence.
R-009 | Nova Survey Drone | Equipment | Equipment | GeoSight Solutions | Progress survey | Riverton | Active | 50% | 87 | 76 | 14.56% | 140 | 10640 | 446 | OK | Low | Site Engineer | Used for weekly topographic checks | • QA/QC and commissioning ramp-up is required for successful handover.
R-010 | Olivia Hart | Procurement Lead | Human | Supply Chain | Vendor negotiations | Head Office | Active | 75% | 130 | 226 | 28.97% | 102 | 23052 | 554 | OK | Medium | Aisha Sterling | Key for long-lead package expediting | • External crew availability may tighten during regional infrastructure surge.
R-011 | Daniel Reed | Safety Manager | Human | HSE | Incident prevention | Riverton | Active | 70% | 121 | 212 | 29.2% | 97 | 20564 | 514 | OK | Medium | Leo Park | Daily briefings and permit-to-work checks | • Cost engineering cover is moderate; month-end close support must be protected.
R-012 | Riya Kapoor | Commissioning Engineer | Human | Systems | Testing & commissioning | Riverton | Planned | 80% | 138 | 134 | 16.18% | 116 | 15544 | 694 | OK | High | Aisha Sterling | Mobilize ahead of system integration
Tip: edit assumptions and resource rows in the Data Entry sheet only. The dashboard, KPIs, charts and alerts update automatically.
Note on B45: Dashboard cells are linked to Data Entry formulas. Avoid typing directly into dashboard areas.

## Data Entry
RESOURCE MASTER DATA
Project Profile Inputs | [6 empty] | Planning Assumptions | [7 empty] | Monthly Demand Drivers
Company | BluePeak Infrastructure Ltd. | [5 empty] | Std. Hours / Week | 40 | [6 empty] | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26
Project | Aurora Metro Station Upgrade | [5 empty] | Target Utilization | 85% | [6 empty] | 1680 | 1920 | 2080 | 2160 | 2000 | 1760
Location | Riverton Central District | [5 empty] | Overload Threshold | 100% | [6 empty] | Planned Total Demand (hrs) |  |  | 11600
Project Manager | Aisha Sterling | [5 empty] | Escalation Threshold | 90%
Planning Start | 2026-04-01 | [5 empty] | Default Overtime Rate | 1.25
Planning End | 2026-09-30 | [5 empty] | Currency | USD
Res ID | Resource Name | Role | Resource Type | Department / Source | Primary Skill | Location | Status | Start Date | End Date | Availability % | Monthly Capacity (hrs) | Apr Alloc | May Alloc | Jun Alloc | Jul Alloc | Aug Alloc | Sep Alloc | Total Alloc (hrs) | Utilization % | Rate / hr | Total Cost | Gap / Excess | Conflict Flag | Action Owner | Manager Notes | Priority
R-001 | Noah Bennett | Project Director | Human | PMO | Governance & client steering | Riverton | Active | 2026-04-01 | 2026-09-30 | 60% | 104 | 40 | 44 | 46 | 48 | 46 | 42 | 266 | 42.63% | 185 | 49210 | 358 | OK | Aisha Sterling | Executive oversight; maintain stakeholder cadence | High
R-002 | Aisha Sterling | Project Manager | Human | PMO | Integrated project control | Riverton | Active | 2026-04-01 | 2026-09-30 | 100% | 173 | 120 | 128 | 132 | 136 | 132 | 124 | 772 | 74.37% | 145 | 111940 | 266 | OK | Aisha Sterling | Core owner of baseline, RAIDs and reporting | High
R-003 | Leo Park | Construction Lead | Human | Site Ops | Civil supervision | Riverton | Active | 2026-04-01 | 2026-09-30 | 100% | 173 | 96 | 104 | 112 | 118 | 106 | 94 | 630 | 60.69% | 118 | 74340 | 408 | OK | Maria Kline | Peak load in structural work packages | High
R-004 | Mia Chen | Scheduler | Human | Project Controls | Primavera P6 & EV tracking | Riverton | Active | 2026-04-01 | 2026-09-30 | 90% | 156 | 72 | 80 | 88 | 92 | 82 | 76 | 490 | 52.35% | 110 | 53900 | 446 | OK | Aisha Sterling | Supports look-ahead and baseline updates | Medium
R-005 | Ethan Brooks | Cost Engineer | Human | Project Controls | Forecasting & accruals | Riverton | Active | 2026-04-01 | 2026-09-30 | 85% | 147 | 64 | 72 | 76 | 80 | 74 | 68 | 434 | 49.21% | 105 | 45570 | 448 | OK | Aisha Sterling | Heavy close support month-end | Medium
R-006 | Sophia Alvarez | QA/QC Manager | Human | Quality | Testing & assurance | Riverton | Active | 2026-04-15 | 2026-09-30 | 85% | 147 | 24 | 32 | 40 | 48 | 54 | 56 | 254 | 28.8% | 98 | 24892 | 628 | OK | Leo Park | Demand rises during testing & handover | High
R-007 | Harbor Crane 12T | Equipment | Equipment | Fleet Vendor | Lifting operations | Riverton Yard | Booked | 2026-04-01 | 2026-08-31 | 95% | 164 | 48 | 64 | 72 | 76 | 68 | 0 | 328 | 33.33% | 320 | 104960 | 656 | OK | Vendor PM | Reserved until structural steel complete | High
R-008 | RapidMix Concrete Crew | External Crew | Human | BuildFast Contractors | Concrete pours | Riverton | Booked | 2026-04-10 | 2026-07-31 | 100% | 173 | 56 | 72 | 84 | 76 | 0 | 0 | 288 | 27.75% | 88 | 25344 | 750 | OK | Procurement Lead | Subcontractor supports mid-phase pours | High
R-009 | Nova Survey Drone | Equipment | Equipment | GeoSight Solutions | Progress survey | Riverton | Active | 2026-04-01 | 2026-09-15 | 50% | 87 | 10 | 14 | 16 | 14 | 12 | 10 | 76 | 14.56% | 140 | 10640 | 446 | OK | Site Engineer | Used for weekly topographic checks | Low
R-010 | Olivia Hart | Procurement Lead | Human | Supply Chain | Vendor negotiations | Head Office | Active | 2026-04-01 | 2026-09-30 | 75% | 130 | 36 | 42 | 44 | 40 | 34 | 30 | 226 | 28.97% | 102 | 23052 | 554 | OK | Aisha Sterling | Key for long-lead package expediting | Medium
R-011 | Daniel Reed | Safety Manager | Human | HSE | Incident prevention | Riverton | Active | 2026-04-01 | 2026-09-30 | 70% | 121 | 30 | 34 | 38 | 40 | 38 | 32 | 212 | 29.2% | 97 | 20564 | 514 | OK | Leo Park | Daily briefings and permit-to-work checks | Medium
R-012 | Riya Kapoor | Commissioning Engineer | Human | Systems | Testing & commissioning | Riverton | Planned | 2026-07-01 | 2026-09-30 | 80% | 138 | 0 | 0 | 16 | 28 | 42 | 48 | 134 | 16.18% | 116 | 15544 | 694 | OK | Aisha Sterling | Mobilize ahead of system integration | High
Note on W12: Positive = spare capacity. Negative = shortage / over-allocation.

## Instructions
HOW TO USE THIS RESOURCE PLAN TEMPLATE
Template Purpose
This workbook gives a project manager one controlled view of resource need, availability, allocation, utilization, cost, conflicts, shortages and mitigation actions.
3-Sheet Structure
Main Template | Executive dashboard with KPIs, demand vs capacity, alerts and the live deployment register.
Data Entry | Edit project inputs, assumptions and resource-by-resource allocations here. All calculations flow automatically.
Instructions | Reference guide, data definitions, color legend and a recommended update process.
Recommended Update Process
1. Update project dates, thresholds and demand assumptions in Data Entry.
2. Edit resource rows, availability %, monthly allocations, rates and notes.
3. Review dashboard KPIs for overload, shortage, conflict and external spend.
4. Capture mitigation actions and escalations in the Main Template sheet.
5. Save a monthly baseline copy after formal plan approval.
Key Columns Explained
Availability % | Share of standard monthly capacity that is usable for this project.
Monthly Capacity (hrs) | Available hours per month after considering the availability %.
Apr–Sep Alloc | Planned assigned hours by month. Adjust these to model real workload.
Total Alloc (hrs) | Formula-driven total of all monthly assignment hours.
Utilization % | Total allocated hours divided by total available hours across the 6-month window.
Gap / Excess | Positive = available headroom; negative = shortage / over-allocation.
Conflict Flag | Turns to Conflict when utilization is above the overload threshold.
Priority | Criticality of the resource to project success; use High / Medium / Low.
Color Legend
#1F3A5F / #2F5597 | Title bars and major section headers
#4472C4 | Table subheaders and analytical blocks
#548235 / #70AD47 | Positive actions and healthy status areas
#92D050 | Supporting positive highlights
#FFC000 | Advisory messages and attention items
#ED7D31 | Escalation, conflicts and watchlist panels
#C00000 | Over-allocation, negative gap and critical alerts
Practical PM Guidance
• Aim for 80%–90% average utilization. Sustained values above 100% usually create delivery risk.
• Use the Gap / Excess field to justify recruitment, subcontracting, leveling or rescheduling decisions.
• Pair the demand chart with weekly look-ahead meetings to spot bottlenecks before they hit the schedule.
• Review the action list after each client meeting, baseline revision or approved change order.