## Main Template
Resource Planning
Prepared by: BluePeak Infrastructure Ltd. ¦ Portfolio: Orion Expansion Program | [12 empty] | Status Date | [5 empty] | 2026-03-28
Client | Northstar Utilities | Region | United States - Central | Reporting Start | 2026-04-01 | Reporting End | 2026-06-30 | Currency | USD | Overload Threshold | 100% | Utilization Warning | 90% | Portfolio Utilization | 83.82% | At-Risk Assignments | 4 | Open Gaps | 4
Total Resources |  |  | Critical Tasks |  |  | Planned Cost |  |  | Capacity Hours |  |  | Assigned Hours |  |  | Open Gaps
10 |  |  | 3 |  |  | 30848 |  |  | 467.65 |  |  | 392 |  |  | 4
resources in pool |  |  | must-staff activities |  |  | planned labor cost |  |  | available capacity |  |  | planned effort |  |  | assignments needing action
Detailed Resource Allocation Plan
Line # | Resource ID | Resource Name | Role | Department | Location | Task ID | Task / Deliverable | Priority | Status | Planned Start | Planned Finish | Duration (Days) | Availability % | Capacity Hrs | Assigned Hrs | Utilization % | Rate / Hr | Planned Cost | Risk Flag | Gap?
1 | R-001 | Ava Morgan | Project Manager | PMO | New York | T-101 | Kick-off & Baseline Plan | Critical | In Progress | 2026-04-01 | 2026-04-11 | 11 | 100% | 40 | 36 | 90% | 110 | 3960 | On Track | Covered
2 | R-002 | Liam Carter | Planning Engineer | Engineering | Chicago | T-101 | Kick-off & Baseline Plan | Critical | In Progress | 2026-04-01 | 2026-04-11 | 11 | 100% | 40 | 28 | 70% | 85 | 2380 | On Track | Covered
3 | R-003 | Noah Bennett | Site Engineer | Engineering | Dallas | T-102 | Site Survey & Mobilization | High | Not Started | 2026-04-05 | 2026-04-18 | 14 | 90% | 43.2 | 44 | 101.9% | 78 | 3432 | Overallocated | Gap
4 | R-004 | Sophia Reed | Procurement Lead | Supply Chain | Atlanta | T-103 | Procurement Long-Lead Items | Critical | In Progress | 2026-04-08 | 2026-05-20 | 43 | 80% | 32 | 38 | 118.8% | 72 | 2736 | Overallocated | Gap
5 | R-005 | Mason Patel | Cost Controller | Finance | Houston | T-108 | Cost Review & Forecast | Medium | Not Started | 2026-05-10 | 2026-05-16 | 7 | 75% | 30 | 20 | 66.67% | 68 | 1360 | On Track | Covered
6 | R-006 | Emma Brooks | QA/QC Manager | Quality | Phoenix | T-106 | QA/QC Inspection Gate 1 | Medium | Not Started | 2026-05-01 | 2026-05-07 | 7 | 100% | 40 | 30 | 75% | 80 | 2400 | On Track | Covered
7 | R-007 | Olivia Diaz | Safety Officer | HSE | Denver | T-107 | Safety Readiness Audit | High | In Progress | 2026-04-20 | 2026-04-27 | 8 | 100% | 45 | 34 | 75.56% | 70 | 2380 | On Track | Covered
8 | R-008 | Ethan Cooper | MEP Coordinator | Construction | Seattle | T-105 | MEP Coordination Package | High | Not Started | 2026-04-22 | 2026-05-30 | 39 | 85% | 38.25 | 42 | 109.8% | 76 | 3192 | Overallocated | Gap
9 | R-009 | Lucas Foster | Scheduler | PMO | Boston | T-109 | Master Schedule Update | High | Not Started | 2026-05-03 | 2026-05-09 | 7 | 90% | 36 | 24 | 66.67% | 82 | 1968 | On Track | Covered
10 | R-010 | Mia Richardson | Document Controller | PMO | Miami | T-110 | Document Control Turnover Pack | Low | Not Started | 2026-06-01 | 2026-06-20 | 20 | 100% | 40 | 32 | 80% | 46 | 1472 | On Track | Covered
11 | R-003 | Noah Bennett | Site Engineer | Engineering | Dallas | T-104 | Foundation Works | Critical | Not Started | 2026-04-15 | 2026-06-10 | 57 | 90% | 43.2 | 46 | 106.5% | 78 | 3588 | Overallocated | Gap
12 | R-001 | Ava Morgan | Project Manager | PMO | New York | T-103 | Procurement Long-Lead Items | Critical | In Progress | 2026-04-08 | 2026-05-20 | 43 | 100% | 40 | 18 | 45% | 110 | 1980 | On Track | Covered
Resource Demand Forecast by Month | [6 empty] | Department Capacity View | [6 empty] | Priority & Risk Notes
Month | Planned Hrs | Cost Forecast | Avg Utilization | Overallocated Lines | Comment |  | Department | Lines | Capacity Hrs | Assigned Hrs | Utilization | Planned Cost |  | Priority | Purpose | Manager Action
2026-04-01 | 286 | 23648 | 89.68% | 4 | Peak mobilization window |  | PMO | 4 | 156 | 110 | 70.51% | 9380 |  | Critical | Directly impacts baseline milestones, procurement, or field progress. | Staff first and escalate gaps immediately.
2026-05-01 | 74 | 5728 | 69.44% | 0 | Controls and QA focus |  | Engineering | 3 | 126.4 | 118 | 93.35% | 9400 |  | High | Important to coordination, compliance, or near-term delivery. | Review weekly and rebalance before overload.
2026-06-01 | 32 | 1472 | 80% | 0 | Closeout and documentation |  | Supply Chain | 1 | 32 | 38 | 118.8% | 2736 |  | Medium | Supports controls, reporting, or quality gates. | Schedule using remaining capacity or backups.
[7 empty] | Finance | 1 | 30 | 20 | 66.67% | 1360 |  | Low | Late-phase documentation or non-critical closeout support. | Use after critical and high-priority work is protected.
[7 empty] | Quality | 1 | 40 | 30 | 75% | 2400
[7 empty] | HSE | 1 | 45 | 34 | 75.56% | 2380
[7 empty] | Construction | 1 | 38.25 | 42 | 109.8% | 3192
Formulas:
Planned Start = IFERROR(VLOOKUP([Planned Cost],'Data Entry'!$J5:P14,6,FALSE),"")
Planned Finish = IFERROR(VLOOKUP([Planned Cost],'Data Entry'!$J5:P14,7,FALSE),"")
Resource ID = SUMIFS(P9:P20,K9:K20,">="&[Total Resources],K9:K20,"<"&EDATE([Total Resources],1))
Resource Name = SUMIFS(S9:S20,K9:K20,">="&[Total Resources],K9:K20,"<"&EDATE([Total Resources],1))
Critical Tasks = IFERROR(AVERAGEIFS(Q9:Q20,K9:K20,">="&[Total Resources],K9:K20,"<"&EDATE([Total Resources],1)),0)
Department = COUNTIFS(K9:K20,">="&[Total Resources],K9:K20,"<"&EDATE([Total Resources],1),T9:T20,"Overallocated")
Note on A7: Use this sheet for live planning. Update Resource ID, Task ID, Status, and Assigned Hrs; all dependent fields and roll-ups calculate automatically.

## Data Entry
Resource Planning Data Entry
Populate master data here. Blue text = editable input cells. This sheet feeds the planning logic on the main tab.
Resource Master | [7 empty] | Task / Work Package Master
Resource ID | Resource Name | Role | Department | Location | Std Hrs/Week | Bill Rate / Hr | Availability % | Task ID | Task / Deliverable | Workstream | Location | Priority | Planned Start | Planned Finish
R-001 | Ava Morgan | Project Manager | PMO | New York | 40 | 110 | 100% | T-101 | Kick-off & Baseline Plan | Program Mgmt | New York | Critical | 2026-04-01 | 2026-04-11
R-002 | Liam Carter | Planning Engineer | Engineering | Chicago | 40 | 85 | 100% | T-102 | Site Survey & Mobilization | Engineering | Dallas | High | 2026-04-05 | 2026-04-18
R-003 | Noah Bennett | Site Engineer | Engineering | Dallas | 48 | 78 | 90% | T-103 | Procurement Long-Lead Items | Supply Chain | Atlanta | Critical | 2026-04-08 | 2026-05-20
R-004 | Sophia Reed | Procurement Lead | Supply Chain | Atlanta | 40 | 72 | 80% | T-104 | Foundation Works | Construction | Dallas | Critical | 2026-04-15 | 2026-06-10
R-005 | Mason Patel | Cost Controller | Finance | Houston | 40 | 68 | 75% | T-105 | MEP Coordination Package | Construction | Seattle | High | 2026-04-22 | 2026-05-30
R-006 | Emma Brooks | QA/QC Manager | Quality | Phoenix | 40 | 80 | 100% | T-106 | QA/QC Inspection Gate 1 | Quality | Phoenix | Medium | 2026-05-01 | 2026-05-07
R-007 | Olivia Diaz | Safety Officer | HSE | Denver | 45 | 70 | 100% | T-107 | Safety Readiness Audit | HSE | Denver | High | 2026-04-20 | 2026-04-27
R-008 | Ethan Cooper | MEP Coordinator | Construction | Seattle | 45 | 76 | 85% | T-108 | Cost Review & Forecast | Finance | Houston | Medium | 2026-05-10 | 2026-05-16
R-009 | Lucas Foster | Scheduler | PMO | Boston | 40 | 82 | 90% | T-109 | Master Schedule Update | PMO | Boston | High | 2026-05-03 | 2026-05-09
R-010 | Mia Richardson | Document Controller | PMO | Miami | 40 | 46 | 100% | T-110 | Document Control Turnover Pack | PMO | Miami | Low | 2026-06-01 | 2026-06-20
Lists & Assumptions
Priority List | Critical |  | Portfolio | Orion Expansion Program
Priority List | High |  | Client | Northstar Utilities
Priority List | Medium |  | Region | United States - Central
Priority List | Low |  | Reporting Start Date | 2026-04-01
Status List | Not Started |  | Reporting End Date | 2026-06-30
Status List | In Progress |  | Currency | USD
Status List | At Risk |  | Overload Threshold | 100%
Status List | Complete |  | Utilization Warning | 90%
Note on A3: Maintain one clean row per resource. Add new resources below row 14 if needed and extend formulas/validation ranges if you expand the template.

## Instructions
How to Use This Resource Planning Worksheet
A project-manager-ready workbook for planning resource availability, workload, utilization, cost, and shortfall actions.
Step | Action | Expert Guidance
1 | Complete Data Entry first. | Load the Resource Master and Task Master with your actual team, roles, locations, rates, priorities, and plan dates. This is the single source of truth.
2 | Assign work on the Main Template. | Edit Resource ID, Task ID, Status, and Assigned Hrs. All lookup fields, utilization, risk flags, and cost calculations update automatically.
3 | Interpret utilization correctly. | Utilization = Assigned Hrs ÷ Capacity Hrs. Over 100% means the resource is overloaded; 90–100% means close monitoring is needed.
4 | Use gap flags to drive action. | When a line is marked Gap, reassign work, add temporary support, split the work package, or negotiate schedule changes.
5 | Review priority before moving people. | Critical tasks protect schedule and client commitments. High-priority work comes next, then medium and low.
6 | Use the monthly view for forecasting. | The month table gives forward demand and cost visibility for leadership and weekly planning meetings.
7 | Use the department view for balancing. | The department summary helps identify where engineering, PMO, QA, HSE, finance, or construction need reinforcement.
8 | Version the plan weekly. | Save a dated copy each reporting cycle, e.g., Resource_Plan_2026-04-01_v1.xlsx, so decisions and changes remain traceable.
What areas this worksheet explains
| • | Resource details, role, department, and work location
| • | Task allocation, priority, and current status
| • | Availability, capacity hours, assigned hours, and utilization
| • | Planned start and finish dates with duration tracking
| • | Labor rate, planned cost, and monthly cost forecast
| • | Shortfalls, overallocations, and risk flags
| • | Department-level balancing and future demand forecasting
Color legend
Title bars / executive framing
Section headers
Column headers
Healthy capacity / resource strength
On-track / balanced
Cost/commercial focus
Watch / caution
Critical overload / urgent action