## Risk Register
Risk Register
Aurelia Infrastructure Ltd. ¦ Project: Northbridge Logistics Hub ¦ Reporting Month: March 2026
| Prepared By | [5 empty] | Project Sponsor | [5 empty] | Primary Site | [5 empty] | Review Cadence
| Olivia Mercer, PMO Lead | [5 empty] | Henry Whitmore, COO | [5 empty] | Newcastle Yard | [5 empty] | Weekly Risk Review
Open Risks |  |  |  | Critical Risks |  |  |  | High Risks |  |  |  | Overdue Actions |  |  |  | Risk Exposure Avg |  |  |  | Risk Scale Legend
24 |  |  |  | 2 |  |  |  | 5 |  |  |  | 24 |  |  |  | 5.5833 |  |  |  | 1-5 Probability | 1 Rare → 5 Almost Certain
[20 empty] | 1-5 Impact | 1 Insignificant → 5 Severe
Comprehensive Risk Register
Risk ID | Project | Site | Date Identified | Department | Category | Risk Title | Risk Description | Trigger / Early Warning | Probability | Impact | Score | Priority | Status | Risk Owner | Target Action Date | Days to Target | Treatment Strategy | Mitigation / Response Action | Contingency Plan | Next Review | Escalation
R-001 | Northbridge Logistics Hub | Newcastle Yard | 2026-03-03 | Procurement | Vendor | Steel frame delivery delay | Primary supplier may miss shipment window for structural steel due to port congestion. | Supplier requests revised sailing schedule | 4 | 4 | 16 | Critical | Open | Daniel Hughes | 2026-03-20 | -27 | Mitigate | Lock alternate carrier slots and approve split deliveries. | Activate secondary supplier agreement for critical spans. | 2026-03-29 | Critical
R-002 | Northbridge Logistics Hub | Manchester Control Office | 2026-03-04 | IT | Cybersecurity | SCADA firewall misconfiguration | Network hardening tasks may remain incomplete before commissioning. | Unresolved penetration test findings | 3 | 5 | 15 | High | Escalated | Sophia Chen | 2026-03-26 | -21 | Avoid | Complete rule-base review and retest all inbound/outbound zones. | Isolate commissioning network and delay go-live by 48 hours. | 2026-03-30 | Critical
R-003 | Northbridge Logistics Hub | Leeds Distribution Park | 2026-03-07 | Construction | HSE | Heavy rainfall impacts earthworks | Prolonged rain could stop excavation and concrete pours. | 5-day adverse weather forecast | 4 | 3 | 12 | High | Monitoring | Marcus Reed | 2026-03-18 | -29 | Accept | Sequence indoor works forward and add drainage pumps. | Re-baseline earthworks package with weekend crews. | 2026-03-31 | High
R-004 | Northbridge Logistics Hub | Bristol Dock | 2026-03-09 | Legal | Regulatory | Permit approval lag | Traffic management permit approval may arrive after mobilization date. | Authority requests supplemental drawings | 2 | 4 | 8 | Moderate | Open | Ava Bennett | 2026-03-28 | -19 | Mitigate | Issue revised drawings and schedule authority workshop. | Stage works in non-restricted zone while permit clears. | 2026-04-01 | Moderate
R-005 | Northbridge Logistics Hub | Newcastle Yard | 2026-03-10 | Engineering | Technical | Conveyor controls integration failure | PLC-to-WMS interfaces may fail during SAT if message mapping is incomplete. | Defects repeated in integration test logs | 3 | 4 | 12 | High | Open | Ethan Brooks | 2026-03-25 | -22 | Mitigate | Freeze interface spec and run daily defect triage. | Deploy manual scan workflow for launch week. | 2026-03-29 | High
R-006 | Northbridge Logistics Hub | Manchester Control Office | 2026-03-11 | Finance | Cost | Foreign exchange uplift on imported equipment | GBP weakness may increase final equipment invoice value. | Supplier proposes updated FX clause | 2 | 3 | 6 | Moderate | Monitoring | Noah Patel | 2026-04-05 | -11 | Transfer | Hedge remaining euro exposure and revalidate contingency. | Use sponsor reserve if variance exceeds tolerance. | 2026-04-02 | Moderate
R-007 | Northbridge Logistics Hub | Leeds Distribution Park | 2026-03-12 | Quality | Quality | Racking tolerances out of spec | Installed uprights may not meet plumbness tolerance for high-bay operation. | Survey variance trend above tolerance | 3 | 4 | 12 | High | Open | Isabella Hart | 2026-03-22 | -25 | Mitigate | Hold installation, increase QA sampling, and retrain crew. | Replace non-compliant bays before commissioning. | 2026-03-30 | High
R-008 | Northbridge Logistics Hub | Newcastle Yard | 2026-03-13 | PMO | Schedule | Critical path slippage on MEP package | Late cable tray installation may delay energisation milestone. | Look-ahead schedule misses three successive tasks | 4 | 4 | 16 | Critical | Open | Olivia Mercer | 2026-03-24 | -23 | Mitigate | Add evening shift and recover through parallel workfronts. | Re-sequence commissioning and deploy temporary power. | 2026-03-29 | Critical
R-009 | Northbridge Logistics Hub | Bristol Dock | 2026-03-14 | Operations | Resource | Commissioning specialist availability | OEM commissioning lead may be unavailable for final SAT window. | Unconfirmed travel booking from OEM | 3 | 3 | 9 | Moderate | Monitoring | Liam Carter | 2026-04-03 | -13 | Transfer | Escalate reservation with OEM account director. | Contract local certified backup engineer. | 2026-04-01 | Moderate
R-010 | Northbridge Logistics Hub | Manchester Control Office | 2026-03-15 | HSE | HSE | Forklift-pedestrian interface incident | Temporary traffic routes increase chance of near miss in live warehouse areas. | Near miss reports increase over two shifts | 2 | 5 | 10 | Moderate | Escalated | Marcus Reed | 2026-03-21 | -26 | Avoid | Install barriers, marshals, and revised one-way routes. | Stop mixed traffic operations in affected zone. | 2026-03-29 | Critical
R-011 | Northbridge Logistics Hub | Newcastle Yard | 2026-03-16 | Procurement | Vendor | Long-lead sensor shortage | Optical sensors may not arrive in time for FAT retest. | Supplier lead time revised from 4 to 7 weeks | 4 | 3 | 12 | High | Open | Daniel Hughes | 2026-03-27 | -20 | Mitigate | Prioritise partial shipment and approve alternate brand. | Reassign spare units from Riverton project. | 2026-03-30 | High
R-012 | Northbridge Logistics Hub | Bristol Dock | 2026-03-17 | Stakeholder | Stakeholder | Community noise complaint escalation | Night works could trigger local complaints and council restrictions. | Increase in complaints logged by site hotline | 3 | 2 | 6 | Moderate | Monitoring | Priya Nair | 2026-04-04 | -12 | Mitigate | Issue community notices and use low-noise equipment. | Move noisiest activity to daytime shift. | 2026-04-03 | Moderate
Risk Summary by Category | [8 empty] | Portfolio Snapshot
Category | Count | Open | Critical/High | Avg Score |  |  |  |  | Status | Count
Schedule | 1 | 1 | 1 | 16 |  |  |  |  | Open | 6
Cost | 1 | 1 | 0 | 6 |  |  |  |  | Monitoring | 4
Technical | 1 | 1 | 1 | 12 |  |  |  |  | Mitigated | 0
Resource | 1 | 1 | 0 | 9 |  |  |  |  | Escalated | 2
Quality | 1 | 1 | 1 | 12 |  |  |  |  | Closed | 0
Vendor | 2 | 2 | 2 | 14
HSE | 2 | 2 | 1 | 11
Regulatory | 1 | 1 | 0 | 8
Cybersecurity | 1 | 1 | 1 | 15
Stakeholder | 1 | 1 | 0 | 6
Formulas:
Risk Exposure Avg = IF([Target Action Date]="","",[Target Action Date]-TODAY())
Note on L13: Risk score = Probability × Impact
Note on Q13: Days to target = Target Action Date minus TODAY(). Negative values are overdue.
Note on V13: Escalation is derived from priority and status.

## Data Entry
Data Entry
Risk Categories | Departments | Owners | Status | Treatment Strategy | Projects | Sites | Probability Scale | Impact Scale | Escalation Level
Schedule | PMO | Olivia Mercer | Open | Avoid | Northbridge Logistics Hub | Newcastle Yard | 1 - Rare | 1 - Insignificant | Low
Cost | Engineering | Daniel Hughes | Monitoring | Mitigate | Riverton Solar Yard | Bristol Dock | 2 - Unlikely | 2 - Minor | Moderate
Technical | Procurement | Priya Nair | Mitigated | Transfer | Aster Data Centre Upgrade | Leeds Distribution Park | 3 - Possible | 3 - Moderate | High
Resource | Construction | Ethan Brooks | Escalated | Accept |  | Manchester Control Office | 4 - Likely | 4 - Major | Critical
Quality | IT | Sophia Chen | Closed | Exploit |  |  | 5 - Almost Certain | 5 - Severe
Vendor | Legal | Marcus Reed
HSE | Finance | Ava Bennett
Regulatory | Quality | Liam Carter
Cybersecurity | HSE | Isabella Hart
Stakeholder | Operations | Noah Patel
Stakeholder
Illustrative Risk Intake Records (editable)
Risk ID | Project | Site | Date Identified | Department | Category | Risk Title | Detailed Description | Trigger / Early Warning Sign | Probability | Impact | Owner | Target Date | Status
R-001 | Northbridge Logistics Hub | Newcastle Yard | 2026-03-03 | Procurement | Vendor | Steel frame delivery delay | Primary supplier may miss shipment window for structural steel due to port congestion. | Supplier requests revised sailing schedule | 4 - Likely | 4 - Major | Daniel Hughes | 2026-03-20 | Open
R-002 | Northbridge Logistics Hub | Manchester Control Office | 2026-03-04 | IT | Cybersecurity | SCADA firewall misconfiguration | Network hardening tasks may be incomplete before commissioning. | Unresolved penetration test findings | 3 - Possible | 5 - Severe | Sophia Chen | 2026-03-26 | Escalated
R-003 | Northbridge Logistics Hub | Leeds Distribution Park | 2026-03-07 | Construction | HSE | Heavy rainfall impacts earthworks | Weather conditions may halt excavation and concrete pours. | 5-day adverse weather forecast | 4 - Likely | 3 - Moderate | Marcus Reed | 2026-03-18 | Monitoring
R-004 | Northbridge Logistics Hub | Bristol Dock | 2026-03-09 | Legal | Regulatory | Permit approval lag | Updated traffic management approval may not arrive before mobilization. | Authority requests supplemental drawings | 2 - Unlikely | 4 - Major | Ava Bennett | 2026-03-28 | Open

## Instructions
Instructions & Governance Notes
How to use this workbook for project risk identification, assessment, ownership, treatment, and review
Workbook Structure
1 | Risk Register | This is the master working sheet. It includes the full risk log, KPI cards, risk scoring logic, heat indicators, and summary charts. Update this sheet during weekly risk review meetings.
2 | Data Entry | Use this sheet for dropdown lists, reference values, and quick risk-intake capture. Edit lookup lists here if owners, departments, or categories change.
3 | Instructions | Use this sheet as the operating guide for the workbook and as a handover note for future project managers.
Recommended Operating Process
• | Log every newly identified risk with a unique Risk ID, date identified, category, owner, and clear description.
• | Score Probability and Impact on a 1–5 scale. The template calculates Score and Priority automatically.
• | Assign a Treatment Strategy and document both mitigation and contingency actions.
• | Use Target Action Date and Next Review to drive weekly follow-up. Overdue actions will flag in the main sheet.
• | Escalate Critical risks and all items marked Escalated to the sponsor or steering committee.
Risk Scoring Guide
Scale | Probability | Impact | Priority Outcome
1 | Rare | Insignificant | Low
2 | Unlikely | Minor | Low / Moderate
3 | Possible | Moderate | Moderate
4 | Likely | Major | High
5 | Almost Certain | Severe | Critical
Good Practice Notes
• Write risks as uncertain events or conditions, not issues that have already happened.
• Separate cause, risk event, and impact in the description where possible.
• Keep owners accountable for actions, not just for awareness.
• Review residual exposure after major mitigation actions are completed.