## Main Template
Stakeholder Analysis
Executive-grade stakeholder register, assessment matrix, communication plan, and action tracker
Project Profile | [7 empty] | Stakeholder Dashboard
Project Name | PhoenixERP Modernization |  | Program Manager | Emma Lawson | Phase | Execution |  | Total Stakeholders |  |  | High Power (4-5) |  |  | Resistant / Opposed |  |  | Critical Priority (≥80) |  |  | Champions
Client / Business Unit | ApexNova Technologies — Global Operations |  | Reporting Date | 2026-03-28 | Steering Forum | Transformation Council |  | 12 |  |  | 8 |  |  | 3 |  |  | 1 |  |  | 2
ID | Stakeholder Name | Organization | Location | Stakeholder Type | Role / Title | Department / Function | Power | Interest | Support | Influence Area | Expectations / Needs | Key Concerns | Communication Method | Frequency | Engagement Strategy | Owner | Current Status | Priority Score | Matrix Quadrant | Recommended Action | Next Review Date | Notes
STK-001 | Olivia Grant | ApexNova Technologies | New York, USA | Internal | Chief Operating Officer | Operations | 5 | 5 | 1 | Operations | Seamless rollout, minimal disruption | Business continuity during cutover | Steering Committee | Weekly | Manage Closely | Emma Lawson | On Track | 84 | High Power / High Interest | Maintain close sponsorship, proactive escalation, and decision-ready updates | 2026-04-03 | Executive sponsor and steering chair
STK-002 | Marcus Reed | ApexNova Technologies | Chicago, USA | Internal | Chief Financial Officer | Finance | 5 | 4 | 0 | Budget | Cost control and governance | Budget creep and delayed benefits | Executive Brief | Biweekly | Keep Satisfied | David Chen | Watchlist | 73 | High Power / High Interest | Maintain close sponsorship, proactive escalation, and decision-ready updates | 2026-04-10 | Budget owner for phase gates
STK-003 | Sophia Martinez | ApexNova Technologies | Austin, USA | Internal | VP, Supply Chain | Operations | 4 | 5 | 2 | Operations | Improved planning visibility | Warehouse disruption risk | 1:1 Meeting | Weekly | Manage Closely | Priya Nair | On Track | 79 | High Power / High Interest | Maintain close sponsorship, proactive escalation, and decision-ready updates | 2026-04-02 | Strong supporter; key change champion
STK-004 | Daniel Brooks | HarborView Consulting | London, UK | External | Engagement Director | Program Delivery | 4 | 4 | 1 | Technology | Timely decisions and scope clarity | Slow approvals from client teams | Status Deck | Weekly | Manage Closely | Emma Lawson | On Track | 68 | High Power / High Interest | Maintain close sponsorship, proactive escalation, and decision-ready updates | 2026-04-05 | Primary delivery partner lead
STK-005 | Aisha Khan | MetroCare Health | Dubai, UAE | External | Compliance Advisor | Compliance | 5 | 3 | -1 | Compliance | Audit-ready process controls | Data privacy and regulatory gaps | Workshop | Monthly | Keep Satisfied | Fatima Al-Hassan | Watchlist | 70 | High Power / Low Interest | Provide concise executive briefings and involve only at key decisions | 2026-04-15 | Regulatory sign-off needed before go-live
STK-006 | Ethan Cole | ApexNova Technologies | Toronto, Canada | Internal | HR Change Lead | People & Change | 3 | 5 | 1 | Change Adoption | Strong adoption and training | Low manager participation | Town Hall | Biweekly | Keep Informed | Michael Torres | On Track | 66 | Low Power / High Interest | Share frequent updates, gather feedback, and involve in testing | 2026-04-12 | Owns training and readiness
STK-007 | Grace Liu | GreenBridge Logistics | Singapore | External | Regional Vendor Manager | Procurement | 3 | 3 | 0 | Procurement | Clear procurement timelines | Late purchase orders | Phone Call | Monthly | Monitor | David Chen | On Track | 48 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-20 | Coordinates hardware and scanners
STK-008 | Noah Bennett | ApexNova Technologies | Chicago, USA | Internal | Plant Director | Manufacturing | 4 | 5 | -2 | Operations | Stable production schedule | Fears downtime and productivity loss | 1:1 Meeting | Weekly | Manage Closely | Priya Nair | Critical | 79 | High Power / High Interest | Maintain close sponsorship, proactive escalation, and decision-ready updates | 2026-04-01 | High-power resistor; needs focused engagement
STK-009 | Hannah Price | Northstar Retail Group | London, UK | External | Customer Advisory Board Chair | Customer Experience | 2 | 4 | 1 | Customer Experience | Better order visibility | Potential service dips during migration | Weekly Email | Monthly | Keep Informed | Emma Lawson | On Track | 50 | Low Power / High Interest | Share frequent updates, gather feedback, and involve in testing | 2026-04-18 | Represents pilot customer voices
STK-010 | Victor Santos | ApexNova Technologies | Austin, USA | Internal | Enterprise Architect | Technology | 4 | 4 | 2 | Technology | Scalable and secure design | Technical debt from legacy integrations | Workshop | Biweekly | Manage Closely | Michael Torres | On Track | 72 | High Power / High Interest | Maintain close sponsorship, proactive escalation, and decision-ready updates | 2026-04-08 | Architecture gatekeeper
STK-011 | Leila Farouk | ApexNova Technologies | Dubai, UAE | Internal | Regional Operations Director | Operations | 4 | 3 | -1 | Operations | Local process fit and training | Template not reflecting regional needs | Status Deck | Monthly | Keep Satisfied | Priya Nair | Watchlist | 61 | High Power / Low Interest | Provide concise executive briefings and involve only at key decisions | 2026-04-14 | Influential regional voice
STK-012 | Jacob Miller | HarborView Consulting | New York, USA | External | PMO Lead | Program Delivery | 3 | 4 | 1 | Budget | Decision log and schedule discipline | Late issue closures | Weekly Email | Weekly | Keep Informed | David Chen | On Track | 59 | Low Power / High Interest | Share frequent updates, gather feedback, and involve in testing | 2026-04-04 | Maintains RAID and governance cadence
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
[18 empty] | 0 | Low Power / Low Interest | Monitor periodically and engage when risks emerge | 2026-04-25
Legend | Editable/input fields |  | Formula-driven fields |  | Positive / champion signal |  | Risk / resistance signal
Note on S10: Priority Score formula: ((Power × 45%) + (Interest × 35%) + (Absolute Support × 20%)) × 20
Note on T10: Quadrant is based on Power and Interest values.

## Data Entry
Validation & Reference Lists
Stakeholder Type | Power Scale | Interest Scale | Support Level | Communication Method | Frequency | Engagement Strategy | Current Status | Project Owners | Locations | Organizations | Influence Area
Internal | 1 - Very Low | 1 - Very Low | -2 - Opposed | Weekly Email | Weekly | Manage Closely | On Track | Emma Lawson | New York, USA | ApexNova Technologies | Budget
External | 2 - Low | 2 - Low | -1 - Resistant | Steering Committee | Biweekly | Keep Satisfied | Watchlist | David Chen | Chicago, USA | HarborView Consulting | Operations
Primary | 3 - Moderate | 3 - Moderate | 0 - Neutral | 1:1 Meeting | Monthly | Keep Informed | Critical | Priya Nair | Austin, USA | GreenBridge Logistics | Compliance
Secondary | 4 - High | 4 - High | 1 - Supportive | Status Deck | Quarterly | Monitor |  | Michael Torres | Toronto, Canada | MetroCare Health | Technology
Direct | 5 - Very High | 5 - Very High | 2 - Champion | Town Hall | At Milestone |  |  | Fatima Al-Hassan | London, UK | Northstar Retail Group | Customer Experience
Indirect |  |  |  | Workshop | Ad Hoc |  |  |  | Dubai, UAE |  | Procurement
|  |  |  | Executive Brief |  |  |  |  | Singapore |  | Change Adoption
Phone Call
Scoring Guide
[8 empty] | Priority Score | Meaning | Quadrant | Action
[8 empty] | 80-100 | Critical stakeholder requiring active management | High Power / High Interest | Manage Closely
[8 empty] | 60-79 | High attention; maintain regular engagement | High Power / Low Interest | Keep Satisfied
[8 empty] | 40-59 | Moderate; monitor and communicate consistently | Low Power / High Interest | Keep Informed
[8 empty] | 0-39 | Low touch; monitor periodically | Low Power / Low Interest | Monitor

## Instructions
Stakeholder Analysis Template — Instructions
Purpose | Use this workbook to identify, assess, prioritize, and manage stakeholders across a project or transformation initiative.
Sheet 1 — Main Template | Primary working sheet. Capture stakeholder details, scores, communication approach, engagement plan, and next review date. Summary KPIs at the top provide a portfolio-level view.
Sheet 2 — Data Entry | Contains approved dropdown lists, scoring guides, and reference data. Update this sheet only if you want to change standard options used by the template.
How scoring works | Priority Score = ((Power × 45%) + (Interest × 35%) + (Absolute Support × 20%)) × 20. Higher values indicate higher management attention.
Power scale | 1 = very low authority, 3 = moderate influence, 5 = decision-maker or budget owner.
Interest scale | 1 = low interest in outcomes, 5 = highly invested in success or failure.
Support scale | -2 = opposed, -1 = resistant, 0 = neutral, 1 = supportive, 2 = champion.
Recommended use | Review all stakeholders weekly during early phases, then refresh monthly once the program stabilizes.
Best practice | Keep the engagement strategy action-oriented: identify concerns, define communication cadence, assign an owner, and schedule a next review date.
Color guide | Blue headers = structure, dark blue = section titles, light blue = editable/input cells, grey = formula/derived cells, green = positive emphasis, orange/red = attention and risk signals.
Executive tip | Focus first on high-power stakeholders with low support; these individuals often drive the biggest delivery risks.
Quadrant Interpretation
High Power / High Interest | Manage Closely | Steering meetings, approvals, issue escalation
High Power / Low Interest | Keep Satisfied | Targeted briefings, decision-ready summaries
Low Power / High Interest | Keep Informed | Frequent updates, workshops, newsletters
Low Power / Low Interest | Monitor | Periodic updates only