## Project Task Manager
Task Manager
Prepared for Meridian Peak Consulting ¦ Portfolio Operations Office | [15 empty] | Traffic-light logic: Attention = delayed, high risk, or overdue
| Total Tasks |  |  |  |  | Completed |  |  |  |  | In Progress |  |  |  |  | Overdue |  |  |  |  | Critical
| 12 |  |  |  |  | 3 |  |  |  |  | 3 |  |  |  |  | 6 |  |  |  |  | 4
Portfolio Summary
Reporting Date | 2026-04-16 |  |  |  | Not Started | 3 |  | Low | 0
Completion Rate | 25% |  |  |  | In Progress | 3 |  | Medium | 3
Tasks At Risk | 4 |  |  |  | On Hold | 1 |  | High | 5
Budget Variance | -53300 |  |  |  | Delayed | 2 |  | Critical | 4
[5 empty] | Completed | 3
Detailed Task View (linked from Data Entry sheet)
Task ID | Project | Workstream | Task Name | Task Description | Phase | Priority | Status | Assigned To | Reviewer | Location | Start Date | Due Date | Actual Finish | Days Remaining | Overdue Days | % Complete | Dependency | Risk Level | Budget ($) | Actual Cost ($) | Variance ($) | Next Action | Last Update | Comments | Flag
TSK-001 | Apollo ERP Rollout | Planning | Approve project charter | Formal sign-off of scope, governance, budget and success metrics | Initiation | Critical | Completed | Ava Brooks | Liam Chen | Chicago, IL | 2026-01-06 | 2026-01-10 | 2026-01-09 | 0 | 0 | 100% | None | Low | 2500 | 2400 | -100 | Archive signed charter | 2026-01-09 | Signed by PMO and sponsor | On Track
TSK-002 | Apollo ERP Rollout | Planning | Finalize integrated timeline | Build baseline plan across finance, supply chain and training workstreams | Planning | High | In Progress | Noah Patel | Emma Sinclair | Chicago, IL | 2026-01-08 | 2026-04-03 |  | 0 | 13 | 72% | TSK-001 | Medium | 12000 | 8300 | -3700 | Confirm cutover milestones | 2026-03-25 | Vendor dependencies under review | Attention
TSK-003 | Apollo ERP Rollout | Data Migration | Cleanse supplier master data | Standardize vendor records before migration rehearsal | Execution | High | On Hold | Sophia Martinez | Olivia Reed | Dallas, TX | 2026-02-02 | 2026-03-14 |  | 0 | 33 | 48% | TSK-002 | High | 8000 | 6100 | -1900 | Resolve duplicate supplier IDs | 2026-03-20 | Waiting for procurement input | Attention
TSK-004 | Apollo ERP Rollout | Testing | Execute UAT cycle 1 | Coordinate scripts, defects and user sign-off for first UAT cycle | Execution | Critical | Delayed | Ethan Walker | Mia Laurent | Phoenix, AZ | 2026-03-01 | 2026-03-22 |  | 0 | 25 | 61% | TSK-003 | High | 18000 | 19250 | 1250 | Escalate defect backlog | 2026-03-26 | Two high-severity defects remain open | Attention
TSK-005 | Apollo ERP Rollout | Training | Launch super-user academy | Prepare change champions and lead classroom practice sessions | Execution | Medium | Not Started | Isabella King | Lucas Bennett | Denver, CO | 2026-04-07 | 2026-04-25 |  | 9 | 0 | 0% | TSK-002 | Medium | 9500 | 0 | -9500 | Approve training roster | 2026-03-24 | Venue reserved at NovaGrid Center | On Track
TSK-006 | Orion HQ Relocation | Facilities | Complete floor plan design | Finalize seating, collaboration zones and executive suite layout | Planning | High | Completed | Grace Foster | Henry Cole | Seattle, WA | 2026-01-12 | 2026-02-06 | 2026-02-03 | 0 | 0 | 100% | None | Low | 6000 | 5750 | -250 | Issue final drawing pack | 2026-02-03 | Approved by leadership team | On Track
TSK-007 | Orion HQ Relocation | Procurement | Order collaboration furniture | Place purchase orders for meeting rooms, pods and lounge areas | Execution | Medium | In Progress | Daniel Cruz | Nora James | Seattle, WA | 2026-02-10 | 2026-04-01 |  | 0 | 15 | 55% | TSK-006 | Medium | 26000 | 14150 | -11850 | Track vendor shipment dates | 2026-03-21 | Lead time risk for imported chairs | Attention
TSK-008 | Orion HQ Relocation | IT & AV | Install conference room AV | Deploy displays, cameras, microphones and room booking panels | Execution | High | Not Started | Harper Sullivan | Mason Price | Seattle, WA | 2026-04-08 | 2026-04-28 |  | 12 | 0 | 0% | TSK-007 | Medium | 22000 | 0 | -22000 | Confirm network drops | 2026-03-22 | Awaiting furniture install sequence | On Track
TSK-009 | Northwind CX Transformation | Process Design | Map current-state support journey | Document customer pain points, handoffs and SLA breakdowns | Discovery | High | Completed | Ella Morgan | Jack Hughes | Boston, MA | 2026-01-05 | 2026-01-30 | 2026-01-28 | 0 | 0 | 100% | None | Low | 7000 | 6900 | -100 | Publish readout to steering committee | 2026-01-28 | Journey map approved | On Track
TSK-010 | Northwind CX Transformation | Automation | Configure chatbot escalation rules | Set routing logic from bot to live agents for high-risk intents | Execution | Critical | In Progress | Benjamin Ross | Chloe Adams | Boston, MA | 2026-02-15 | 2026-03-30 |  | 0 | 17 | 67% | TSK-009 | High | 15000 | 13200 | -1800 | Validate VIP routing logic | 2026-03-27 | Testing with customer success team | Attention
TSK-011 | Northwind CX Transformation | Reporting | Design service dashboard | Create weekly KPI dashboard for CSAT, FCR and backlog | Execution | Medium | Delayed | Zoe Turner | Leo Griffin | New York, NY | 2026-02-20 | 2026-03-18 |  | 0 | 29 | 40% | TSK-009 | Medium | 5000 | 5650 | 650 | Align data source definitions | 2026-03-23 | Metric logic changed twice | Attention
TSK-012 | Northwind CX Transformation | Pilot | Go-live readiness review | Assess people, process and technology readiness before pilot launch | Closure | Critical | Not Started | Caleb Wright | Ruby Ellis | New York, NY | 2026-04-12 | 2026-04-18 |  | 2 | 0 | 0% | TSK-010 | High | 4000 | 0 | -4000 | Schedule readiness workshop | 2026-03-27 | Dependent on automation sign-off | Attention
Template authored for demonstration purposes ¦ Replace hypothetical data with live project records.

## Data Entry
Task Register | [25 empty] | Initiation | Low | Not Started | Low | Apollo ERP Rollout | Planning | Ava Brooks | Chicago, IL
Edit input columns only. Formula columns automatically calculate schedule risk, cost variance, and task flags. | [25 empty] | Discovery | Medium | In Progress | Medium | Orion HQ Relocation | Data Migration | Liam Chen | Dallas, TX
Task ID | Project | Workstream | Task Name | Task Description | Phase | Priority | Status | Assigned To | Reviewer | Location | Start Date | Due Date | Actual Finish | Days Remaining | Overdue Days | % Complete | Dependency | Risk Level | Budget ($) | Actual Cost ($) | Variance ($) | Next Action | Last Update | Comments | Flag | Planning | High | On Hold | High | Northwind CX Transformation | Testing | Emma Sinclair | Phoenix, AZ
TSK-001 | Apollo ERP Rollout | Planning | Approve project charter | Formal sign-off of scope, governance, budget and success metrics | Initiation | Critical | Completed | Ava Brooks | Liam Chen | Chicago, IL | 2026-01-06 | 2026-01-10 | 2026-01-09 | 0 | 0 | 100% | None | Low | 2500 | 2400 | -100 | Archive signed charter | 2026-01-09 | Signed by PMO and sponsor | On Track | Execution | Critical | Delayed |  | Vertex GreenBuild Program | Training | Noah Patel | Denver, CO
TSK-002 | Apollo ERP Rollout | Planning | Finalize integrated timeline | Build baseline plan across finance, supply chain and training workstreams | Planning | High | In Progress | Noah Patel | Emma Sinclair | Chicago, IL | 2026-01-08 | 2026-04-03 |  | 0 | 13 | 72% | TSK-001 | Medium | 12000 | 8300 | -3700 | Confirm cutover milestones | 2026-03-25 | Vendor dependencies under review | Attention | Closure |  | Completed |  | BlueHarbor Cyber Uplift | Facilities | Sophia Martinez | Seattle, WA
TSK-003 | Apollo ERP Rollout | Data Migration | Cleanse supplier master data | Standardize vendor records before migration rehearsal | Execution | High | On Hold | Sophia Martinez | Olivia Reed | Dallas, TX | 2026-02-02 | 2026-03-14 |  | 0 | 33 | 48% | TSK-002 | High | 8000 | 6100 | -1900 | Resolve duplicate supplier IDs | 2026-03-20 | Waiting for procurement input | Attention | [5 empty] | Procurement | Olivia Reed | Boston, MA
TSK-004 | Apollo ERP Rollout | Testing | Execute UAT cycle 1 | Coordinate scripts, defects and user sign-off for first UAT cycle | Execution | Critical | Delayed | Ethan Walker | Mia Laurent | Phoenix, AZ | 2026-03-01 | 2026-03-22 |  | 0 | 25 | 61% | TSK-003 | High | 18000 | 19250 | 1250 | Escalate defect backlog | 2026-03-26 | Two high-severity defects remain open | Attention | [5 empty] | IT & AV | Ethan Walker | New York, NY
TSK-005 | Apollo ERP Rollout | Training | Launch super-user academy | Prepare change champions and lead classroom practice sessions | Execution | Medium | Not Started | Isabella King | Lucas Bennett | Denver, CO | 2026-04-07 | 2026-04-25 |  | 9 | 0 | 0% | TSK-002 | Medium | 9500 | 0 | -9500 | Approve training roster | 2026-03-24 | Venue reserved at NovaGrid Center | On Track | [5 empty] | Process Design | Mia Laurent | Austin, TX
TSK-006 | Orion HQ Relocation | Facilities | Complete floor plan design | Finalize seating, collaboration zones and executive suite layout | Planning | High | Completed | Grace Foster | Henry Cole | Seattle, WA | 2026-01-12 | 2026-02-06 | 2026-02-03 | 0 | 0 | 100% | None | Low | 6000 | 5750 | -250 | Issue final drawing pack | 2026-02-03 | Approved by leadership team | On Track | [5 empty] | Automation | Isabella King | Charlotte, NC
TSK-007 | Orion HQ Relocation | Procurement | Order collaboration furniture | Place purchase orders for meeting rooms, pods and lounge areas | Execution | Medium | In Progress | Daniel Cruz | Nora James | Seattle, WA | 2026-02-10 | 2026-04-01 |  | 0 | 15 | 55% | TSK-006 | Medium | 26000 | 14150 | -11850 | Track vendor shipment dates | 2026-03-21 | Lead time risk for imported chairs | Attention | [5 empty] | Reporting | Lucas Bennett
TSK-008 | Orion HQ Relocation | IT & AV | Install conference room AV | Deploy displays, cameras, microphones and room booking panels | Execution | High | Not Started | Harper Sullivan | Mason Price | Seattle, WA | 2026-04-08 | 2026-04-28 |  | 12 | 0 | 0% | TSK-007 | Medium | 22000 | 0 | -22000 | Confirm network drops | 2026-03-22 | Awaiting furniture install sequence | On Track | [5 empty] | Pilot | Grace Foster
TSK-009 | Northwind CX Transformation | Process Design | Map current-state support journey | Document customer pain points, handoffs and SLA breakdowns | Discovery | High | Completed | Ella Morgan | Jack Hughes | Boston, MA | 2026-01-05 | 2026-01-30 | 2026-01-28 | 0 | 0 | 100% | None | Low | 7000 | 6900 | -100 | Publish readout to steering committee | 2026-01-28 | Journey map approved | On Track | [5 empty] | Finance | Henry Cole
TSK-010 | Northwind CX Transformation | Automation | Configure chatbot escalation rules | Set routing logic from bot to live agents for high-risk intents | Execution | Critical | In Progress | Benjamin Ross | Chloe Adams | Boston, MA | 2026-02-15 | 2026-03-30 |  | 0 | 17 | 67% | TSK-009 | High | 15000 | 13200 | -1800 | Validate VIP routing logic | 2026-03-27 | Testing with customer success team | Attention | [5 empty] | Operations | Daniel Cruz
TSK-011 | Northwind CX Transformation | Reporting | Design service dashboard | Create weekly KPI dashboard for CSAT, FCR and backlog | Execution | Medium | Delayed | Zoe Turner | Leo Griffin | New York, NY | 2026-02-20 | 2026-03-18 |  | 0 | 29 | 40% | TSK-009 | Medium | 5000 | 5650 | 650 | Align data source definitions | 2026-03-23 | Metric logic changed twice | Attention | [5 empty] | Change Management | Nora James
TSK-012 | Northwind CX Transformation | Pilot | Go-live readiness review | Assess people, process and technology readiness before pilot launch | Closure | Critical | Not Started | Caleb Wright | Ruby Ellis | New York, NY | 2026-04-12 | 2026-04-18 |  | 2 | 0 | 0% | TSK-010 | High | 4000 | 0 | -4000 | Schedule readiness workshop | 2026-03-27 | Dependent on automation sign-off | Attention | [6 empty] | Harper Sullivan
Mason Price
Ella Morgan
Jack Hughes
Benjamin Ross
Chloe Adams
Zoe Turner
Leo Griffin
Caleb Wright
Ruby Ellis
Template authored for demonstration purposes ¦ Replace hypothetical data with live project records.
Formulas:
Days Remaining = IF([Task Name]="","",IF([Status]="Completed",0,IF([Due Date]="",0,MAX(0,[Due Date]-TODAY()))))
Overdue Days = IF([Task Name]="","",IF(OR([Status]="Completed",[Due Date]=""),0,MAX(0,TODAY()-[Due Date])))
Note on A3: Unique identifier for each task record.
Note on Q3: Enter % complete as a decimal or percentage (e.g., 0.65 or 65%).
Note on V3: Variance = Actual Cost - Budget. Positive means over budget.

## Instructions
Task Manager Template ¦ User Guide
1) Purpose
This workbook is designed as a senior-project-manager-ready control tower for tracking scope, ownership, schedule, progress, dependencies, budget, risks, and action items.
Use the Data Entry sheet as the only place to add or update task records. The main dashboard sheet refreshes automatically through formulas.
The template uses realistic sample data for Meridian Peak Consulting and hypothetical client programs so you can replace content quickly without redesigning the workbook.
2) Sheet-by-sheet guide
Project Task Manager: executive dashboard, KPI cards, charts, and a polished linked task register for steering meetings and weekly status reviews.
Data Entry: structured task register with dropdown lists, formulas, and conditional formatting. Add new tasks in the blank rows already provided.
Instructions: operating guide, logic definitions, data standards, and a legend so teams use the template consistently.
3) Data rules & dropdowns
Dropdown-controlled fields: Project, Workstream, Phase, Priority, Status, Reviewer, Assigned To, Location, and Risk Level.
Formula-driven fields: Days Remaining, Overdue Days, Variance ($), and Flag. Do not overwrite these formulas.
Required minimum fields for each task: Task ID, Project, Task Name, Priority, Status, Assigned To, Start Date, Due Date, and % Complete.
Best practice: update Last Update and Comments every time a status changes so leadership can see the story behind the numbers.
4) Color & status legend
Dark navy / blue: headings and executive structure. | Status | Completed | Task is fully delivered and signed off.
Green shades: healthy progress, completed work, and positive signals. | Status | In Progress | Task is actively being worked.
Orange / yellow: caution, watch items, and medium priority. | Status | On Hold | Task paused pending decision/input.
Red: delays, critical items, overdue tasks, or high-risk conditions. | Status | Delayed | Task missed plan or needs escalation.
Light blue: active work currently in progress. | Priority | Critical | Immediate management attention.
| Priority | High | Important and time-sensitive.
| Risk | High | Major threat to scope, time, or cost.
| Flag | Attention | Auto-triggered by delay, high risk, or overdue.
5) Recommended PM operating rhythm
Monday: refresh schedule, progress %, blockers, and next actions.
Wednesday: review overdue items, dependencies, and budget variance with workstream leads.
Friday: publish dashboard screenshot or PDF for sponsors and steering committee packs.
Hypothetical entities used in sample data: Meridian Peak Consulting, NovaGrid Center, Orion HQ Relocation, Apollo ERP Rollout, and Northwind CX Transformation.
Template authored for demonstration purposes ¦ Replace hypothetical data with live project records.