## Task Tracker
Task Tracker
Professional project control workbook for the fictional Aurora Commerce Hub Rollout
| Project Name | Aurora Commerce Hub Rollout |  |  | Company | Northwind Meridian Consulting |  |  | Client | BluePeak Retail Group |  |  | Primary Site | Riverton Innovation Park
| Project Manager | Elena Brooks |  |  | Sponsor | Marcus Hale |  |  | Kickoff | 2026-01-06 |  |  | Go-Live Target | 2026-06-30
Total Tasks |  |  | Completed |  |  | In Progress |  |  | Overdue |  |  | % Complete |  |  | Critical Open
20 |  |  | 6 |  |  | 7 |  |  | 14 |  |  | 56.1% |  |  | 6
ID | Workstream | Task / Deliverable | Owner | Department | Priority | Location | Status | Start Date | Due Date | Days Left | % Complete | Dependency | Budget ($) | Health | Next Milestone | Risk / Blocker | Notes
TSK-001 | Initiation | Approve charter and governance | Elena Brooks | PMO | High | Silver Oak Tower | Completed | 2026-01-06 | 2026-01-10 | 0 | 100% |  | 15000 | Complete | Steering committee signed off |  | Project charter filed in PMO library
TSK-002 | Planning | Finalize stakeholder map | Noah Bennett | PMO | Medium | Remote / Hybrid | Completed | 2026-01-08 | 2026-01-15 | 0 | 100% | TSK-001 | 4500 | Complete | Stakeholder map shared |  | Includes executive and site leads
TSK-003 | Infrastructure | Confirm network readiness | Liam Carter | IT | Critical | Harborview Campus | In Progress | 2026-01-20 | 2026-04-05 | -10 | 72% | TSK-001 | 82000 | Off Track | Core network cutover rehearsal | Legacy firewall rule review | Pending final switch configuration
TSK-004 | Procurement | Issue hardware purchase orders | Ava Reynolds | Procurement | High | Silver Oak Tower | Completed | 2026-01-22 | 2026-02-02 | 0 | 100% | TSK-003 | 215000 | Complete | POs released to preferred vendors |  | Supplier: Alpine Tech Supply
TSK-005 | Build | Configure application environments | Priya Shah | IT | Critical | Riverton Innovation Park | In Progress | 2026-02-03 | 2026-04-18 | 3 | 64% | TSK-003 | 126000 | At Risk | SIT environment available | Awaiting two API keys | Dev and test nearly complete
TSK-006 | Finance | Approve revised implementation budget | Ethan Cole | Finance | High | Silver Oak Tower | Completed | 2026-02-05 | 2026-02-14 | 0 | 100% | TSK-001 | 0 | Complete | Budget baseline locked |  | Capex and Opex approved
TSK-007 | Operations | Warehouse process walkthrough | Lucas Green | Operations | Medium | Cedar Creek Warehouse | Completed | 2026-02-10 | 2026-02-21 | 0 | 100% | TSK-002 | 12000 | Complete | Future-state map issued |  | Lean workshop concluded
TSK-008 | Quality | Define test strategy and entry/exit criteria | Sofia Martinez | Quality | High | Riverton Innovation Park | Completed | 2026-02-12 | 2026-02-24 | 0 | 100% | TSK-005 | 18500 | Complete | QA sign-off matrix approved |  | Aligned with PMO governance
TSK-009 | Change | Launch change champion network | Maya Singh | HR | Medium | Remote / Hybrid | In Progress | 2026-02-18 | 2026-04-25 | 10 | 58% | TSK-002 | 24000 | On Track | Town hall briefing | Competing HR initiatives | Regional champions nominated
TSK-010 | Build | Complete integration development | Priya Shah | IT | Critical | Riverton Innovation Park | Delayed | 2026-02-25 | 2026-04-12 | -3 | 49% | TSK-005 | 93000 | Off Track | API regression pack ready | Vendor webhook spec changed | Recovery plan under review
TSK-011 | Procurement | Receive handheld devices on site | Ava Reynolds | Procurement | High | Cedar Creek Warehouse | In Progress | 2026-03-03 | 2026-04-01 | -14 | 81% | TSK-004 | 158000 | Off Track | Goods receipt complete | Freight delay for 20 units | Partial delivery received
TSK-012 | Testing | Run system integration testing | Sofia Martinez | Quality | Critical | Riverton Innovation Park | Not Started | 2026-04-20 | 2026-05-12 | 27 | 0% | TSK-005 | 36000 | At Risk | SIT defect triage kickoff |  | Blocked until environment freeze
TSK-013 | Training | Prepare training materials | Maya Singh | HR | Medium | Remote / Hybrid | In Progress | 2026-03-10 | 2026-04-30 | 15 | 55% | TSK-009 | 21000 | On Track | Pilot training session | Awaiting screen captures | Draft deck 80% complete
TSK-014 | Testing | Coordinate UAT planning | Noah Bennett | PMO | High | Silver Oak Tower | In Progress | 2026-03-15 | 2026-05-08 | 23 | 43% | TSK-012 | 9500 | On Track | UAT calendar approved | Business SMEs have limited availability | Daily coordination in progress
TSK-015 | Deployment | Cutover checklist and command center plan | Elena Brooks | PMO | Critical | Silver Oak Tower | Not Started | 2026-05-18 | 2026-06-10 | 56 | 0% | TSK-014 | 14500 | At Risk | Go-live readiness review |  | Template ready for detailed steps
TSK-016 | Compliance | Security review and sign-off | Liam Carter | IT | High | Harborview Campus | On Hold | 2026-03-12 | 2026-04-22 | 7 | 38% | TSK-003 | 17500 | At Risk | Architecture review board meeting | Waiting for pen-test window | Hold cleared once test dates confirmed
TSK-017 | Communications | Publish launch communications plan | Chloe Kim | Marketing | Medium | Harborview Campus | In Progress | 2026-03-08 | 2026-04-27 | 12 | 62% | TSK-009 | 11000 | On Track | Executive messaging draft |  | Includes customer and internal comms
TSK-018 | Testing | Defect remediation sprint | Priya Shah | IT | High | Riverton Innovation Park | Not Started | 2026-05-13 | 2026-05-27 | 42 | 0% | TSK-012 | 42000 | On Track | Critical defects < 5 |  | Dependent on SIT output
TSK-019 | Deployment | Dress rehearsal / mock cutover | Elena Brooks | PMO | High | Riverton Innovation Park | Not Started | 2026-06-05 | 2026-06-12 | 58 | 0% | TSK-015 | 8500 | On Track | Mock cutover completed |  | Cross-functional participation required
| Go-Live | Hypercare command center | Elena Brooks | PMO | Critical | Riverton Innovation Park | Not Started | 2026-06-30 | 2026-07-14 | 90 | 0% | TSK-019 | 27500 | At Risk | Go-live day 1 |  | Covers two-week hypercare window
Created by Tariq Noor: We Build Technologies for Project Managers
Formulas:
Days Left = IF(OR([Status]="Completed",[Status]="Cancelled"),0,[Overdue]-TODAY())
Note on A11: Use the dropdowns and update task rows only. KPI cards refresh automatically from the table below.
Note on L11: Enter progress as a decimal percentage (e.g., 0.65 = 65%).
Note on O11: Health is calculated automatically from status, priority, due date, and progress.

## Data Entry
Task Tracker Template ¦ Data Entry & Lookup Lists
Project Profile |  | Status List | Priority List | Department List | Location List | Health List
Project Name | Aurora Commerce Hub Rollout | Not Started | Critical | PMO | Riverton Innovation Park | On Track
Company | Northwind Meridian Consulting | In Progress | High | IT | Silver Oak Tower | At Risk
Client | BluePeak Retail Group | On Hold | Medium | Operations | Harborview Campus | Off Track
Project Manager | Elena Brooks | Completed | Low | Procurement | Cedar Creek Warehouse | Complete
Project Sponsor | Marcus Hale | Delayed |  | Finance | Remote / Hybrid
Primary Site | Riverton Innovation Park | Cancelled |  | Marketing
Kickoff Date | 2026-01-06 |  |  | HR
Target Go-Live | 2026-06-30 |  |  | Quality
Team Directory
|  | Assignee | Role | Department | Location | Email
|  | Elena Brooks | Senior Project Manager | PMO | Silver Oak Tower | elena.brooks@nmc.example
|  | Noah Bennett | Business Analyst | PMO | Remote / Hybrid | noah.bennett@nmc.example
|  | Priya Shah | Technical Lead | IT | Riverton Innovation Park | priya.shah@nmc.example
|  | Liam Carter | Infrastructure Manager | IT | Harborview Campus | liam.carter@nmc.example
|  | Ava Reynolds | Procurement Lead | Procurement | Silver Oak Tower | ava.reynolds@nmc.example
|  | Sofia Martinez | QA Manager | Quality | Riverton Innovation Park | sofia.martinez@nmc.example
|  | Ethan Cole | Finance Controller | Finance | Silver Oak Tower | ethan.cole@nmc.example
|  | Maya Singh | Change Manager | HR | Remote / Hybrid | maya.singh@nmc.example
|  | Lucas Green | Operations Lead | Operations | Cedar Creek Warehouse | lucas.green@nmc.example
|  | Chloe Kim | Marketing Manager | Marketing | Harborview Campus | chloe.kim@nmc.example
Created by Tariq Noor: We Build Technologies for Project Managers

## Instructions
Instructions & Operating Guide
How to use the workbook like a senior project manager
Section | Senior PM Guidance | Legend
Purpose | Use this workbook to plan, assign, track, and report project tasks. It combines task control, accountability, schedule tracking, dependency visibility, and risk visibility in one place.
Where to edit | Maintain lookup values and project profile on the Data Entry sheet. Manage live tasks on the Task Tracker sheet from row 12 downward.
Owner field | Choose owners from the dropdown linked to the Team Directory so reporting stays consistent.
Priority guidance | Critical = threatens scope/date/cost immediately. High = strong management attention. Medium = standard delivery priority. Low = nice-to-have or non-critical support work.
Status guidance | Not Started, In Progress, On Hold, Completed, Delayed, Cancelled. Keep status current at least once per week or during every steering review.
% Complete | Enter progress as a decimal value between 0 and 1. Example: 0.25 = 25%, 0.60 = 60%, 1 = 100%.
Days Left | Calculated automatically from Due Date versus today's date. Negative values indicate overdue work.
Health logic | Complete = task status is Completed. Off Track = delayed or overdue. At Risk = critical or approaching due date with weak progress. On Track = everything else.
Budget column | Use estimated or approved task budget. Format is already set for currency and negative variance displays in red parentheses.
Dependencies | Reference predecessor task IDs (for example TSK-005) so sequencing is visible during planning and standups.
Notes & blocker columns | Capture concise action-oriented updates. Good examples: 'Awaiting vendor API key' or 'Security review booked for 15-Apr'.
Leadership rhythm | Recommended cadence: update task statuses twice weekly, review overdue and critical items daily, and use KPI cards in weekly project status meetings.
Professional Notes
Color Theme | Dark blue and navy frame the workbook, green signals healthy progress, orange flags attention points, red flags urgent intervention, and gold highlights important controls.
Suggested workflow | 1) Set project profile in Data Entry 2) Add / update tasks in Task Tracker 3) Use the dashboard to report progress 4) Archive completed rows at phase close if needed.
Created by Tariq Noor: We Build Technologies for Project Managers | All names, companies, and places in this workbook are fictional and provided only to make the template feel like a real project environment.