## Main Template
TO DO LIST
Prepared for NorthStar Civic Solutions Ltd. ¦ Example project: Aurora Renewal Program
Project Name | Aurora Renewal Program |  | Project Sponsor | Daniel Mercer |  | Project Manager | Olivia Grant, PMP |  | Primary Site | Rivergate HQ |  | Total Tasks | 19
Report Date | 2026-03-28 |  | Reporting Period | March 2026 |  | Overall Health | Watch |  | Target Finish | 2026-05-29 |  | Completed | 6
[12 empty] | Open | 13
Action Register - all core fields a senior project manager expects in a live tracker
Task ID | Workstream / Category | Department | Task / Deliverable | Task Description | Start Date | Due Date | Status | Priority | Assigned To | Location | % Complete | Completion Date | Remarks / Next Action
AUR-001 | Planning | PMO | Approve mobilization plan | Finalize site kickoff pack, governance chart and week-1 actions. | 2026-03-03 | 2026-03-06 | Completed | High | Olivia Grant | Rivergate HQ | 100% | 2026-03-06 | Shared with sponsor; use as baseline.
AUR-002 | Stakeholder | Communications | Issue stakeholder notice | Send update to internal leaders and external partners. | 2026-03-04 | 2026-03-08 | Completed | Medium | Sophia Reyes | Rivergate HQ | 100% | 2026-03-08 | Distribution list archived.
AUR-003 | Procurement | Procurement | Release vendor RFQ | Issue request for quotation for HVAC replacement lots. | 2026-03-07 | 2026-03-12 | In Progress | High | Marcus Chen | Harborview Depot | 65% |  | Awaiting final scope note from engineering.
AUR-004 | Design | Operations | Validate draft layout | Review plant room drawings against operational constraints. | 2026-03-10 | 2026-03-14 | Completed | High | Noah Patel | Lakeside Plant | 100% | 2026-03-14 | Approved with minor comments.
AUR-005 | Risk | PMO | Update risk register | Refresh top risks, owners and mitigation actions for March review. | 2026-03-11 | 2026-03-15 | Completed | Medium | Emma Brooks | Rivergate HQ | 100% | 2026-03-15 | Risk workshop completed.
AUR-006 | Training | HR | Book supervisor training | Reserve rooms and trainers for safety induction sessions. | 2026-03-12 | 2026-03-18 | In Progress | Medium | Ava Thompson | Westbridge Campus | 50% |  | Confirm final attendee count by Monday.
AUR-007 | Reporting | Finance | Prepare cost tracker | Build phase-1 forecast and committed cost summary. | 2026-03-14 | 2026-03-19 | At Risk | High | Liam Carter | Rivergate HQ | 45% |  | Two supplier quotes still missing.
AUR-008 | Quality | Operations | Conduct site readiness walk | Complete checklist before equipment delivery. | 2026-03-16 | 2026-03-20 | Completed | High | Noah Patel | Lakeside Plant | 100% | 2026-03-20 | All critical items closed.
AUR-009 | Compliance | IT | Set up document repository | Configure permissions, folders and naming convention. | 2026-03-17 | 2026-03-21 | Completed | Medium | Daniel Price | Rivergate HQ | 100% | 2026-03-21 | Repository live.
AUR-010 | Procurement | Procurement | Evaluate supplier bids | Score RFQ responses and prepare recommendation memo. | 2026-03-18 | 2026-03-24 | Waiting on Client | Critical | Marcus Chen | Harborview Depot | 70% |  | Client requested one-week extension.
AUR-011 | Planning | PMO | Confirm revised schedule | Integrate delivery lead times and site blackout windows. | 2026-03-20 | 2026-03-25 | In Progress | High | Olivia Grant | Rivergate HQ | 60% |  | Draft v3 under review.
AUR-012 | Stakeholder | Communications | Prepare town hall deck | Create executive narrative, schedule and slide pack. | 2026-03-20 | 2026-03-26 | Blocked | High | Sophia Reyes | Summit Park Office | 35% |  | Need sponsor sign-off on headline messages.
AUR-013 | Quality | Operations | Review punch list closure | Verify closure evidence from contractors. | 2026-03-21 | 2026-03-27 | In Progress | Medium | Emma Brooks | Lakeside Plant | 55% |  | Three photos still pending.
AUR-014 | Reporting | Finance | Submit month-end pack | Send budget, progress, risks and decisions log. | 2026-03-22 | 2026-03-28 | In Progress | Critical | Liam Carter | Rivergate HQ | 80% |  | Awaiting final actuals from AP.
AUR-015 | Training | HR | Publish induction roster | Issue final session schedule to supervisors and contractors. | 2026-03-23 | 2026-03-29 | Not Started | Medium | Ava Thompson | Westbridge Campus | 0% |  | Dependent on final attendee approvals.
AUR-016 | Compliance | IT | Archive superseded drawings | Lock obsolete revisions and update transmittal log. | 2026-03-24 | 2026-03-30 | Not Started | Low | Daniel Price | Rivergate HQ | 0% |  | Planned after schedule freeze.
AUR-017 | Design | Operations | Approve equipment submittals | Engineering and operations joint review of vendor package. | 2026-03-25 | 2026-04-01 | In Progress | High | Noah Patel | Lakeside Plant | 40% |  | Meeting scheduled with vendor Tuesday.
AUR-018 | Risk | PMO | Escalate utility outage risk | Prepare executive paper on outage impact and fallback plan. | 2026-03-25 | 2026-03-31 | In Progress | Critical | Olivia Grant | Rivergate HQ | 50% |  | Decision required from sponsor by Wednesday.
Management tip: Keep remarks action-oriented (decision, owner, date). Review red/overdue lines first during weekly governance meetings.
Note on A8: Unique task identifier. Example format: project code + sequence number.
Note on L8: Enter completion as a percentage. The color scale helps a PM quickly spot lagging tasks.
Note on N8: Use for blockers, decisions needed, and next action statements.

## Data Entry
Task Template Support Lists - NorthStar Civic Solutions Ltd.
Priority Levels | Status Options | Departments | Categories | Assigned To | Locations | Projects | Risk Flags
Critical | Not Started | PMO | Planning | Olivia Grant | Rivergate HQ | Aurora Renewal Program | Normal
High | In Progress | Operations | Procurement | Marcus Chen | Lakeside Plant | Maple Transit Upgrade | Watch
Medium | Waiting on Client | Finance | Design | Ava Thompson | Summit Park Office | BluePeak ERP Rollout | Escalate
Low | At Risk | HR | Quality | Noah Patel | Harborview Depot | Cedar Health Expansion
| Blocked | IT | Training | Emma Brooks | Westbridge Campus
| Completed | Procurement | Reporting | Liam Carter
| On Hold | Communications | Stakeholder | Sophia Reyes
|  | Field Services | Risk | Daniel Price
Project Manager | Olivia Grant, PMP |  | Compliance
Sponsor | Daniel Mercer, COO |  | Closure
Default Review Day | Friday

## Instructions
How to Use This To Do List Template
1. Purpose | Use the Main Template sheet as the live action register for a project, department plan, weekly governance meeting, or executive follow-up tracker.
2. What is included | The template captures every core area a professional Excel to-do list should explain: task name, description, category, department, dates, owner, priority, location, status, progress, completion date, and remarks / next action.
3. Data entry rules | Use the drop-down fields in Workstream, Department, Status, Priority, Assigned To, and Location to keep reporting clean and consistent. Expand the support lists on the Data Entry sheet whenever your project needs more options.
4. Recommended PM rhythm | Review this tracker at least once per week. Update % Complete, Status, Completion Date, and Remarks before governance meetings so stakeholders can immediately see decisions and blockers.
5. KPI cards | The KPI cards in columns M:N summarize Total Tasks, Completed, Open, and Overdue items automatically. Overdue tasks are highlighted in soft red when the due date has passed and the task is not completed.
6. Suggested status definitions | Not Started = work has not begun. In Progress = currently being worked. Waiting on Client = external review/approval needed. At Risk = achievable but under pressure. Blocked = cannot move without intervention. Completed = fully closed. On Hold = intentionally paused.
7. Remarks best practice | Write short, decision-ready notes such as: 'Awaiting sponsor sign-off by 31-Mar' or 'Procurement to issue revised RFQ Monday'. Avoid long narrative comments.
8. Customization ideas | Add columns for budget, dependency, risk rating, or meeting cadence if needed. You can also filter by Assigned To, Priority, or Status to create manager-specific action views.
Color logic used | Dark blue headers | Green bands | Orange attention | Red urgency | Gold highlight | Fresh green | Accent blue
Pro Tip | For executive meetings, filter the Main Template to show only Critical/High priority items and all overdue or blocked actions. This turns the file into a sharp decision log rather than just a list.