## WBS Template
Work Breakdown Structure (WBS)
Executive-ready project planning workbook ¦ Sample project: Helios ERP Transformation ¦ Northbridge Manufacturing Group
Project Name | Helios ERP Transformation |  | Company | Northbridge Manufacturing Group |  | Sponsor | Avery Callahan, CFO |  | Senior PM | Elena Brooks |  | Primary Site | Chicago HQ
Portfolio | Digital Operations Modernization |  | Budget Ceiling | $332,000 |  | Baseline Date | 01-Apr-2026 |  | Designed for scope definition, ownership, budgeting, milestone tracking, and status governance.
Total Packages |  |  |  | Total Budget |  |  |  | Avg. Completion |  |  |  | Milestones |  |  |  | At-Risk Items
10 |  |  |  | 332000 |  |  |  | 34.5% |  |  |  | 4 |  |  |  | 1
Comprehensive WBS Register
WBS Code | Level | Phase | Deliverable | Work Package | Description | Owner | Location | Planned Start | Planned Finish | Duration (days) | Budget (USD) | Status | % Complete | Priority | Risk | Dependencies | Milestone | Notes
1.0 | 1 | Initiation | Project Governance | Executive Kickoff | Approve charter, appoint steering committee and confirm sponsor alignment. | Elena Brooks | Chicago HQ | 2026-04-06 | 2026-04-10 | 5 | 18000 | Completed | 100% | Critical | Low | - | Yes | Kickoff complete with board sign-off
1.1 | 2 | Planning | Requirements | Current-State Assessment | Map current workflows across finance, procurement and operations. | Marcus Hale | Austin Hub | 2026-04-13 | 2026-04-24 | 10 | 24000 | Completed | 100% | High | Low | 1.0 | No | Process interviews finished
1.2 | 2 | Planning | Requirements | Future-State Blueprint | Design target operating model for Helios ERP rollout. | Priya Desai | Chicago HQ | 2026-04-27 | 2026-05-08 | 10 | 32000 | In Progress | 70% | Critical | Medium | 1.1 | Yes | Needs CFO validation on purchasing controls
2.0 | 1 | Design | Solution Design | Core Finance Configuration | Define chart of accounts, cost centers and approval workflows. | Daniel Kim | Denver Office | 2026-05-11 | 2026-05-29 | 15 | 56000 | In Progress | 45% | Critical | Medium | 1.2 | No | Awaiting tax logic confirmation
2.1 | 2 | Build | Data Migration | Vendor Master Cleanup | Standardize vendor records from legacy systems. | Sofia Alvarez | Phoenix Plant | 2026-05-18 | 2026-06-05 | 15 | 22000 | At Risk | 30% | High | High | 2.0 | No | Duplicate records above tolerance threshold
2.2 | 2 | Build | Integrations | Warehouse Interface | Connect ERP to OrionTrack WMS and test inventory sync. | Liam Chen | Remote | 2026-05-25 | 2026-06-19 | 20 | 68000 | Not Started | 0% | High | Medium | 2.0 | No | Dependent on API credentials
3.0 | 1 | Testing | Quality Assurance | Conference Room Pilot | Run end-to-end pilot for procure-to-pay and month-end close. | Jonah Reed | Chicago HQ | 2026-06-22 | 2026-07-03 | 10 | 28000 | Not Started | 0% | Critical | Medium | 2.1, 2.2 | Yes | Pilot scripts drafted
3.1 | 2 | Deployment | Training | Super User Training | Train site champions at Northbridge facilities. | Nadia Foster | Austin Hub | 2026-07-06 | 2026-07-17 | 10 | 16000 | Not Started | 0% | Medium | Low | 3.0 | No | Training roster pending
3.2 | 2 | Deployment | Go-Live | Wave 1 Go-Live | Launch finance and procurement modules at Chicago HQ. | Elena Brooks | Chicago HQ | 2026-07-20 | 2026-07-24 | 5 | 42000 | Not Started | 0% | Critical | High | 3.0, 3.1 | Yes | Executive readiness review required
4.0 | 1 | Closure | Transition | Hypercare & Handover | Stabilize system, transition to support and close project. | Marcus Hale | Remote | 2026-07-27 | 2026-08-14 | 15 | 26000 | Not Started | 0% | High | Medium | 3.2 | No | Support model to be approved
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0
Note on B5: Fictional sample project name for demonstration purposes.
Note on A12: Main WBS register: replace linked rows with your own project data or keep the links to the Data Entry sheet.

## Data Entry
WBS Data Entry & Control Lists
Status | Priority | Risk | Owners | Locations | Phases | Milestone? | Units |  | Purpose: maintain the controlled lists and example WBS records used by the main template. You can replace the fictional project data with your own rows while keeping the structure intact. Dropdowns on the main sheet draw from the lists in columns A:H.
Not Started | Critical | High | Elena Brooks | Chicago HQ | Initiation | Yes | days
In Planning | High | Medium | Marcus Hale | Austin Hub | Planning | No | USD
In Progress | Medium | Low | Priya Desai | Denver Office | Design |  | %
At Risk | Low |  | Daniel Kim | Phoenix Plant | Build
On Hold |  |  | Sofia Alvarez | Remote | Testing
Completed |  |  | Jonah Reed |  | Deployment
|  |  | Nadia Foster |  | Training
|  |  | Liam Chen |  | Closure
WBS Code | Level | Phase | Deliverable | Work Package | Description | Owner | Location | Planned Start | Planned Finish | Duration (days) | Budget (USD) | Status | % Complete | Priority | Risk | Dependencies | Milestone | Notes
1.0 | 1 | Initiation | Project Governance | Executive Kickoff | Approve charter, appoint steering committee and confirm sponsor alignment. | Elena Brooks | Chicago HQ | 2026-04-06 | 2026-04-10 | 5 | 18000 | Completed | 100% | Critical | Low | - | Yes | Kickoff complete with board sign-off
1.1 | 2 | Planning | Requirements | Current-State Assessment | Map current workflows across finance, procurement and operations. | Marcus Hale | Austin Hub | 2026-04-13 | 2026-04-24 | 10 | 24000 | Completed | 100% | High | Low | 1.0 | No | Process interviews finished
1.2 | 2 | Planning | Requirements | Future-State Blueprint | Design target operating model for Helios ERP rollout. | Priya Desai | Chicago HQ | 2026-04-27 | 2026-05-08 | 10 | 32000 | In Progress | 70% | Critical | Medium | 1.1 | Yes | Needs CFO validation on purchasing controls
2.0 | 1 | Design | Solution Design | Core Finance Configuration | Define chart of accounts, cost centers and approval workflows. | Daniel Kim | Denver Office | 2026-05-11 | 2026-05-29 | 15 | 56000 | In Progress | 45% | Critical | Medium | 1.2 | No | Awaiting tax logic confirmation
2.1 | 2 | Build | Data Migration | Vendor Master Cleanup | Standardize vendor records from legacy systems. | Sofia Alvarez | Phoenix Plant | 2026-05-18 | 2026-06-05 | 15 | 22000 | At Risk | 30% | High | High | 2.0 | No | Duplicate records above tolerance threshold
2.2 | 2 | Build | Integrations | Warehouse Interface | Connect ERP to OrionTrack WMS and test inventory sync. | Liam Chen | Remote | 2026-05-25 | 2026-06-19 | 20 | 68000 | Not Started | 0% | High | Medium | 2.0 | No | Dependent on API credentials
3.0 | 1 | Testing | Quality Assurance | Conference Room Pilot | Run end-to-end pilot for procure-to-pay and month-end close. | Jonah Reed | Chicago HQ | 2026-06-22 | 2026-07-03 | 10 | 28000 | Not Started | 0% | Critical | Medium | 2.1, 2.2 | Yes | Pilot scripts drafted
3.1 | 2 | Deployment | Training | Super User Training | Train site champions at Northbridge facilities. | Nadia Foster | Austin Hub | 2026-07-06 | 2026-07-17 | 10 | 16000 | Not Started | 0% | Medium | Low | 3.0 | No | Training roster pending
3.2 | 2 | Deployment | Go-Live | Wave 1 Go-Live | Launch finance and procurement modules at Chicago HQ. | Elena Brooks | Chicago HQ | 2026-07-20 | 2026-07-24 | 5 | 42000 | Not Started | 0% | Critical | High | 3.0, 3.1 | Yes | Executive readiness review required
4.0 | 1 | Closure | Transition | Hypercare & Handover | Stabilize system, transition to support and close project. | Marcus Hale | Remote | 2026-07-27 | 2026-08-14 | 15 | 26000 | Not Started | 0% | High | Medium | 3.2 | No | Support model to be approved

## Instructions
Instructions ¦ How to Use This WBS Template
What this template covers
• | Defines the full project scope through phases, deliverables, sub-deliverables and work packages.
• | Captures ownership, location, dependencies, milestones, budget, schedule and completion status.
• | Supports executive reporting via summary KPIs and a presentation-ready WBS register.
• | Uses a realistic fictional project so the workbook feels immediately usable.
Recommended workflow
1. Go to the Data Entry sheet and replace the sample rows with your project phases and work packages.
2. Keep each row at work-package level where duration, owner, budget and status can be managed.
3. Return to the WBS Template sheet to review the polished register and executive KPIs.
4. Use the dropdowns for Phase, Owner, Location, Status, Priority, Risk and Milestone to keep data consistent.
5. Update % Complete and Status weekly for governance reviews.
Color legend
| #1F3A5F | Title banners / executive branding
| #2F5597 | Section headers and main labels
| #548235 | Core WBS sections and budget card
| #92D050 | Positive progress emphasis
| #ED7D31 | Attention / schedule monitoring
| #C00000 | Risk / issue emphasis
| #FFC000 | Milestones / highlights
| #70AD47 | Supportive success accents
| #4472C4 | Project metadata / KPI framing