## Main Template
Work Schedule Template
Professional weekly workforce planner with approvals, workload visibility, and conflict controls
Company | Apex Meridian Consulting |  | Project / Function | North Harbor Redevelopment |  | Site / Location | Riverside Operations Hub |  | Schedule Start | 2026-04-06 |  | Schedule End | 2026-04-12 |  | Prepared By | Olivia Hart, PMO Lead
Reviewed By | Marcus Bennett, Senior Project Manager |  | Approved By | Sophia Chen, Program Director |  | Coverage Model | 5x8 + selective weekend support |  | Default Hours / Day | 8 |  | Escalation Contact | resource.office@apexmeridian.example |  | Version | v1.0
Scheduled Staff |  |  | Planned Hours |  |  | Overtime Hours |  |  | Leave Count |  |  | Coverage Gaps |  |  | Conflict Flags
16 |  |  | 143 |  |  | 2 |  |  | 1 |  |  | 0 |  |  | 0
Integrated Weekly Schedule View (live from Data Entry)
Date | Day | Emp ID | Employee Name | Job Title | Department | Supervisor | Location | Shift | Start | End | Break (hrs) | Work Hrs | OT Hrs | Status | Task / Activity | Priority | Comments / Notes | Flag
2026-04-06 | Mon | EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Foundation QA walkdown | High | Coordinate with QA Inspector | OK
2026-04-06 | Mon | EMP-102 | Liam Patel | Project Coordinator | PMO | Olivia Hart | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Daily controls & reporting | High | Issue 5 PM dashboard | OK
2026-04-06 | Mon | EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | D1 | 7:00 | 16:00 | 1 | 8 | 0 | Scheduled | Permit-to-work audit | Critical | Toolbox talk at 07:15 | OK
2026-04-06 | Mon | EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | E1 | 13:00 | 22:00 | 1 | 8 | 0 | Scheduled | Gate logistics supervision | Medium | Backfill evening gate | OK
2026-04-07 | Tue | EMP-105 | Mason Reed | Procurement Analyst | Supply Chain | Olivia Hart | Central Procurement Desk | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Remote | Vendor expediting & PO closeout | High | Remote supplier calls | OK
2026-04-07 | Tue | EMP-106 | Sophia Turner | Document Controller | PMO | Olivia Hart | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Drawing transmittal control | Medium | Rev 4 package due | OK
2026-04-07 | Tue | EMP-107 | Ethan Flores | Cost Engineer | Commercial | Sophia Chen | Finance Pod | D1 | 8:00 | 18:00 | 1 | 9 | 1 | Scheduled | Forecast reconciliation | High | Includes cost review | OK
2026-04-08 | Wed | EMP-108 | Isabella Ward | QA Inspector | Quality | Marcus Bennett | East Yard | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Concrete cube test witness | Critical | Hold point at 10 AM | OK
2026-04-08 | Wed | EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | East Yard | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Field inspection support | High | With QA and HSE | OK
2026-04-08 | Wed | EMP-102 | Liam Patel | Project Coordinator | PMO | Olivia Hart | Remote / Home Office | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Training | Primavera schedule update training | Medium | Half-day learning | OK
2026-04-09 | Thu | EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Scaffold inspection | Critical | Joint review with contractor | OK
2026-04-09 | Thu | EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | N1 | 22:00 | 6:00 | 0.5 | 7.5 | 0 | Scheduled | Night shutdown coordination | Critical | Requires permit sign-off | OK
2026-04-09 | Thu | EMP-106 | Sophia Turner | Document Controller | PMO | Olivia Hart | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | 0 | 0 | Leave | Annual leave | Low | Approved leave | OK
2026-04-10 | Fri | EMP-105 | Mason Reed | Procurement Analyst | Supply Chain | Olivia Hart | Central Procurement Desk | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Expediting report issue | High | Release Friday report | OK
2026-04-10 | Fri | EMP-107 | Ethan Flores | Cost Engineer | Commercial | Sophia Chen | Finance Pod | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Weekly earned value update | High | Send by 3 PM | OK
2026-04-10 | Fri | EMP-108 | Isabella Ward | QA Inspector | Quality | Marcus Bennett | East Yard | D1 | 8:00 | 17:00 | 1 | 8 | 1.7764e-15 | Scheduled | Punch list verification | High | Close top 10 items | OK
2026-04-11 | Sat | EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | Riverside Operations Hub | SPL | 7:00 | 18:00 | 2 | 9 | 1 | Scheduled | Weekend critical path coverage | Critical | Client walkdown at noon | OK
2026-04-11 | Sat | EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | D1 | 8:00 | 15:00 | 0.5 | 6.5 | 0 | Scheduled | Weekend receiving supervision | Medium | Short support shift | OK
2026-04-12 | Sun | EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | D1 | 8:00 | 12:00 | 0.5 | 3.5 | 0 | Scheduled | Sunday safety readiness check | Medium | Pre-mobilization review | OK
2026-04-12 | Sun | EMP-106 | Sophia Turner | Document Controller | supply Chain | Olivia Hart | Remote / Home Office | D1 | 8:00 | 12:00 | 0.5 | 3.5 | 0 | Remote | Weekend transmittal backlog clearance | Low | Optional support | OK
Shift & Status Legend
Code / Status | Meaning | Color cue |  | Daily Planned Hours
D1 | Day Shift ¦ 08:00-17:00 ¦ 1h break | Blue |  | Mon | 32
E1 | Evening Shift ¦ 13:00-22:00 ¦ 1h break | Green |  | Tue | 25
N1 | Night Shift ¦ 22:00-06:00 ¦ 0.5h break | Orange |  | Wed | 24
SPL | Split / Field Coverage | Gold |  | Thu | 15.5
Scheduled | Confirmed work assignment | Green |  | Fri | 24
Remote | Remote delivery day | Blue |  | Sat | 15.5
Leave | Approved leave | Red |  | Sun | 7
Training | Planned development session | Orange
Formulas:
Company = IF(COUNTA('Data Entry'!A14:[Prepared By, row below])=0,"",'Data Entry'!A14)

## Data Entry
Data Entry ¦ Workforce Scheduling Inputs
Edit only the light cells. The Main Template sheet refreshes automatically.
Employee Directory | [7 empty] | Shift Library | [6 empty] | Control Lists
Emp ID | Employee Name | Job Title | Department | Supervisor | Default Location | Home Base |  | Shift | Start | End | Break (hrs) | Typical Use | Hours |  | Status | Priority | Locations | Day Map
EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | Riverside Operations Hub | Chicago |  | D1 | 8:00 | 17:00 | 1 | Standard day coverage | 8 |  | Scheduled | Critical | Riverside Operations Hub | Mon
EMP-102 | Liam Patel | Project Coordinator | PMO | Olivia Hart | Riverside Operations Hub | Chicago |  | E1 | 13:00 | 22:00 | 1 | Evening coordination | 8 |  | Remote | High | East Yard | Tue
EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | Milwaukee |  | N1 | 22:00 | 6:00 | 0.5 | Night works / shutdown | 7.5 |  | Leave | Medium | North Harbor Gatehouse | Wed
EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | Chicago |  | SPL | 7:00 | 18:00 | 2 | Split / field movement | 9 |  | Sick Leave | Low | Finance Pod | Thu
EMP-105 | Mason Reed | Procurement Analyst | Supply Chain | Olivia Hart | Central Procurement Desk | Chicago | [8 empty] | Training |  | Central Procurement Desk | Fri
Schedule Input Grid (edit light cells) | [16 empty] | Remote / Home Office | Sat
Date | Day | Emp ID | Employee Name | Job Title | Department | Supervisor | Location | Shift | Start | End | Break (hrs) | Status | Task / Activity | Priority | Comments / Notes |  |  | Sun
2026-04-06 | Mon | EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | Scheduled | Foundation QA walkdown | High | Coordinate with QA Inspector
2026-04-06 | Mon | EMP-102 | Liam Patel | Project Coordinator | PMO | Olivia Hart | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | Scheduled | Daily controls & reporting | High | Issue 5 PM dashboard
2026-04-06 | Mon | EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | D1 | 7:00 | 16:00 | 1 | Scheduled | Permit-to-work audit | Critical | Toolbox talk at 07:15
2026-04-06 | Mon | EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | E1 | 13:00 | 22:00 | 1 | Scheduled | Gate logistics supervision | Medium | Backfill evening gate
2026-04-07 | Tue | EMP-105 | Mason Reed | Procurement Analyst | Supply Chain | Olivia Hart | Central Procurement Desk | D1 | 8:00 | 17:00 | 1 | Remote | Vendor expediting & PO closeout | High | Remote supplier calls
2026-04-07 | Tue | EMP-106 | Sophia Turner | Document Controller | PMO | Olivia Hart | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | Scheduled | Drawing transmittal control | Medium | Rev 4 package due
2026-04-07 | Tue | EMP-107 | Ethan Flores | Cost Engineer | Commercial | Sophia Chen | Finance Pod | D1 | 8:00 | 18:00 | 1 | Scheduled | Forecast reconciliation | High | Includes cost review
2026-04-08 | Wed | EMP-108 | Isabella Ward | QA Inspector | Quality | Marcus Bennett | East Yard | D1 | 8:00 | 17:00 | 1 | Scheduled | Concrete cube test witness | Critical | Hold point at 10 AM
2026-04-08 | Wed | EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | East Yard | D1 | 8:00 | 17:00 | 1 | Scheduled | Field inspection support | High | With QA and HSE
2026-04-08 | Wed | EMP-102 | Liam Patel | Project Coordinator | PMO | Olivia Hart | Remote / Home Office | D1 | 8:00 | 17:00 | 1 | Training | Primavera schedule update training | Medium | Half-day learning
2026-04-09 | Thu | EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | D1 | 8:00 | 17:00 | 1 | Scheduled | Scaffold inspection | Critical | Joint review with contractor
2026-04-09 | Thu | EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | N1 | 22:00 | 6:00 | 0.5 | Scheduled | Night shutdown coordination | Critical | Requires permit sign-off
2026-04-09 | Thu | EMP-106 | Sophia Turner | Document Controller | PMO | Olivia Hart | Riverside Operations Hub | D1 | 8:00 | 17:00 | 1 | Leave | Annual leave | Low | Approved leave
2026-04-10 | Fri | EMP-105 | Mason Reed | Procurement Analyst | Supply Chain | Olivia Hart | Central Procurement Desk | D1 | 8:00 | 17:00 | 1 | Scheduled | Expediting report issue | High | Release Friday report
2026-04-10 | Fri | EMP-107 | Ethan Flores | Cost Engineer | Commercial | Sophia Chen | Finance Pod | D1 | 8:00 | 17:00 | 1 | Scheduled | Weekly earned value update | High | Send by 3 PM
2026-04-10 | Fri | EMP-108 | Isabella Ward | QA Inspector | Quality | Marcus Bennett | East Yard | D1 | 8:00 | 17:00 | 1 | Scheduled | Punch list verification | High | Close top 10 items
2026-04-11 | Sat | EMP-101 | Ava Thompson | Site Engineer | Engineering | Marcus Bennett | Riverside Operations Hub | SPL | 7:00 | 18:00 | 2 | Scheduled | Weekend critical path coverage | Critical | Client walkdown at noon
2026-04-11 | Sat | EMP-104 | Emma Brooks | Field Supervisor | Operations | Marcus Bennett | North Harbor Gatehouse | D1 | 8:00 | 15:00 | 0.5 | Scheduled | Weekend receiving supervision | Medium | Short support shift
2026-04-12 | Sun | EMP-103 | Noah Rivera | Safety Lead | HSE | Sophia Chen | East Yard | D1 | 8:00 | 12:00 | 0.5 | Scheduled | Sunday safety readiness check | Medium | Pre-mobilization review
2026-04-12 | Sun | EMP-106 | Sophia Turner | Document Controller | PMO | Olivia Hart | Remote / Home Office | D1 | 8:00 | 12:00 | 0.5 | Remote | Weekend transmittal backlog clearance | Low | Optional support

## Instructions
Instructions ¦ How to Use This Work Schedule Template
Purpose
Use this workbook to plan, communicate, and control weekly workforce deployment for projects, operations, or departmental teams. The design supports employee allocation, shift timing, overtime visibility, leave planning, task assignments, location control, conflict identification, and management sign-off.
How the 3 sheets work together
1 | Data Entry | Enter or update schedule rows in the blue input area. Use the employee directory and shift library as a guide. | Input
2 | Main Template | Share this sheet with leadership and teams. It presents the schedule in a polished management view with KPIs and flags. | Output
3 | Instructions | Use this sheet for handover, onboarding, or governance reviews. | Reference
What this template covers
• Employee and supervisor information
• Schedule period and daily date mapping
• Shift start, end, break, total hours, and overtime
• Task / activity assignment and priority
• Location / site allocation and remote work visibility
• Attendance status: Scheduled, Remote, Leave, Sick Leave, Training, Holiday
• Conflict and gap flags for missing or risky assignments
• Prepared by, reviewed by, and approved by controls
Best-practice operating notes from a senior project manager
• Plan capacity first, then assign tasks. Avoid building schedules one task at a time without checking workload balance.
• Use Status and Priority consistently so leadership can interpret the schedule quickly.
• Review rows flagged as Review or Gap before distributing the schedule.
• For night or weekend work, confirm supervisor coverage, safety readiness, and permit approvals.
• Treat the Main Template as the presentation layer and the Data Entry tab as the controlled input layer.
Color guide used in this workbook
| #2F5597 / #1F3A5F | Primary headers and executive bands
| #548235 / #70AD47 / #92D050 | Operational sections and positive status cues
| #ED7D31 / #FFC000 | Attention areas, weekend work, and warnings
| #C00000 | Leave / high-risk exceptions
| #4472C4 | Complementary dashboard highlights