## Task list
| Project Name | [Project Name] |  |  |  |  | No. of Projects - 11
| Project Manager | [Name] |  |  |  |  | Not Started | 4
| Start Date | 2020-02-03 |  |  |  |  | In Progress | 2
| End Date | 2021-02-11 |  |  |  |  | Complete | 4
| Duration | 374 Day(s) |  |  |  |  | Overdue | 1
Budget
[7 empty] | Planned Cost | 2063
[7 empty] | Actual Cost | 1012
[7 empty] | Variance + / (-) | 1051
Tasks | Assigned To | Start | End | Days | Status | Planned Cost | Actual Cost | Notes
Choose Event Time | Lila Patel | 2021-02-01 | 2021-02-03 | 2 | Complete | 25 | 30
Create Guest List | Ethan Carter | 2021-02-02 | 2021-02-03 | 1 | Complete | 50 | 30
Create Invitations | Marcus Zhao | 2021-02-03 | 2021-02-07 | 4 | Overdue | 10 | 12
Purchase Invitation Gift | Sophia Rivera | 2020-02-04 | 2020-02-10 | 6 | In Progress | 400 | 300
Send Invitations | Oscar Bennett | 2021-02-11 | 2021-02-14 | 3 | Not Started | 100
Hire Event Coordinator | Yara Santos | 2020-02-03 | 2020-02-14 | 11 | Complete | 250 | 300
Plan Event Details | Luca Moretti | 2020-02-03 | 2020-02-21 | 18 | In Progress | 40 | 30
Purchase Required Items | Daniel Kovac | 2020-02-21 | 2020-02-28 | 7 | Not started | 258
Lock in Guest List | Zara Al-Mansoori | 2020-03-01 | 2020-03-04 | 3 | Not started | 400
Finalize other Hires | Marcus Zhao | 2020-02-03 | 2020-02-28 | 25 | Complete | 300 | 310
Send Reminders | Yara Santos | 2020-03-07 | 2020-03-10 | 3 | Not started | 230
Above is an Excel Table, Just start typing below last task. Table will be extended automatically with all formating intact.
Note on D12: Update Assigned To table in Settings sheet

## Dashboard
[Project Name]

## Settings
Total Tasks | 11
Assigned To | Workload | Complete | Overdue | In Progress | Not Started | Status | Count | %
Ethan Carter | 1 | 1 | 0 | 0 | 0 | Complete | 4 | 36.36%
Lila Patel | 1 | 1 | 0 | 0 | 0 | Overdue | 1 | 9.091%
Marcus Zhao | 2 | 1 | 1 | 0 | 0 | In Progress | 2 | 18.18%
Sophia Rivera | 1 | 0 | 0 | 1 | 0 | Not Started | 4 | 36.36%
Oscar Bennett | 1 | 0 | 0 | 0 | 1
Zara Al-Mansoori | 1 | 0 | 0 | 0 | 1
Daniel Kovac | 1 | 0 | 0 | 0 | 1
Amara Okeke | 0 | 0 | 0 | 0 | 0
Luca Moretti | 1 | 0 | 0 | 1 | 0
Yara Santos | 2 | 1 | 0 | 0 | 1

## Reports (hidden)
|  | Workload | Column Labels | [5 empty] | Days | (All)
|  | Row Labels | Complete | In Progress | Not Started | Overdue | (blank) | Grand Total
|  | Jenny Smith |  | 1 | 1 |  |  | 2 |  | Column Labels
|  | Stacy Williams | 1 |  | 3 | 1 |  | 5 |  | Create Guest List | Create Invitations | Finalize other Hires | Hire Event Coordinator | Plan Event Details | Purchase Invitation Gift | Purchase Required Items | Send Invitations | Send Reminders | Grand Total
|  | Bozo the Clown | 3 | 1 |  |  |  | 4 | Sum of Days | 1 | 4 | 25 | 11 | 18 | 6 | 7 | 3 | 3 | 78
|  | Grand Total | 4 | 2 | 4 | 1 |  | 11
Row Labels | Count of Tasks
Complete | 4
In Progress | 2
Not Started | 4
Overdue | 1
Grand Total | 11
Row Labels
Choose Event Time
Create Guest List
Create Invitations
Finalize other Hires
Hire Event Coordinator
Lock in Guest List
Plan Event Details
Purchase Invitation Gift
Purchase Required Items
Send Invitations
Send Reminders
(blank)
Grand Total
Status List
[19 empty] | Not Started | 4
[19 empty] | In Progress | 2
[19 empty] | Complete | 4
[19 empty] | Overdue | 1