## Project Dashboard
PROJECT DASHBOARD
Olympic International Project Planning Tool |  | Status | Count | Owner | Complete | In Progress | Not Started | Overdue | Category | Actual Cost
Project Name | Olympic 2026 | Complete | 11 | Person 1 | 1 | 1 | 1 | 0 | Create Guest List | 50
Project Lead | Template22 | In Progress | 5 | Person 2 | 1 | 1 | 2 | 0 | Create Invitations | 80
Start Date | 2024-08-05 | Not Started | 7 | Person 3 | 1 | 1 | 0 | 1 | Finalize Other Hires | 310
End Date | 2026-09-10 | Overdue | 2 | Person 4 | 2 | 1 | 0 | 0 | Hire Event | 200
On Track | 37 items are on track. |  |  | Person 5 | 1 | 0 | 0 | 0 | Lock In Guest List | 0
Budget | 5500 |  |  | Person 6 | 1 | 0 | 0 | 0 | Party! | 2342
Actual Cost | 5300 |  |  | Person 7 | 0 | 0 | 1 | 0 | Plan Event Details | 290
Variance | 200 |  |  | Person 8 | 2 | 1 | 1 | 0 | Purchase Invitation | 280
|  |  |  | Person 9 | 1 | 1 | 1 | 0 | Purchase Required | 280
|  |  |  | Person 10 | 1 | 0 | 1 | 0 | Send Invitations | 8
[9 empty] | Send Reminders | 0
[9 empty] | Planning | 860
|  | Task | Days
|  | Meet Client | 4
|  | Requirements | 2
|  | Inputs | 1
|  | Design | 7
|  | Project Testing | 1
|  | Process | 3
|  | Data model | 10
|  | Project Deliver | 1
|  | Define server | 6
|  | Configure server | 3
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Data
PROJECT MASTER DATA SHEET (Edit this sheet only — all templates update automatically)
Project Name | Olympic 2026
Project Lead | Template22
Sponsor | Olympic International
Start Date | 2024-08-05
End Date | 2026-09-10
Reporting Date | 2024-12-15
Location | Los Angeles, Case
Department | Event Operations area
Budget ($) | 5500
ID | Task | Category | Owner | Status | Start | Due | Days | Est Hours | Planned Cost ($) | Actual Cost ($) | Notes | WBS Code | Phase | Milestone | Predecessor ID | Dependency | Priority | % Complete | Actual End | RAG | Opt Days | Most Likely | Pes Days
1 | Meet Client | Initiation | Person 1 | Complete | 2024-08-01 | 2024-08-04 | 4 | 2 | 150 | 150 | Kickoff approved | 1.0 | Initiation | No |  | FS | Low | 100 | 2024-08-04 | Green | 3 | 4 | 5
2 | Requirements | Planning | Person 2 | Complete | 2024-08-01 | 2024-08-02 | 2 | 2 | 140 | 140 | Requirements draft | 2.0 | Planning | No | 1 | FS | Low | 100 | 2024-08-02 | Green | 1 | 2 | 3
3 | Inputs | Planning | Person 3 | Overdue | 2024-08-05 | 2024-08-05 | 1 | 1 | 200 | 200 | Missing vendor input | 3.0 | Planning | Yes | 2 | FS | High | 0 |  | Red | 1 | 1 | 2
4 | Design | Planning | Person 4 | Complete | 2024-08-06 | 2024-08-12 | 7 | 5 | 180 | 180 | Design reviewed | 4.0 | Planning | No | 3 | FS | Low | 100 | 2024-08-12 | Green | 6 | 7 | 8
5 | Project Testing | Execution | Person 1 | In Progress | 2024-08-12 | 2024-08-12 | 1 | 2 | 670 | 430 | Testing ongoing | 5.0 | Execution | Yes | 4 | FS | Medium | 50 |  | Amber | 1 | 1 | 2
6 | Process | Execution | Person 2 | In Progress | 2024-08-13 | 2024-08-15 | 3 | 3 | 300 | 120 | Workflow updates | 6.0 | Execution | No | 5 | FS | Medium | 50 |  | Amber | 2 | 3 | 4
7 | Data model | Execution | Person 3 | In Progress | 2024-08-06 | 2024-08-15 | 10 | 8 | 200 | 90 | Data mapping | 7.0 | Execution | No | 6 | FS | Medium | 50 |  | Amber | 9 | 10 | 11
8 | Project Deliver | Execution | Person 7 | Not Started | 2024-08-15 | 2024-08-15 | 1 | 6 | 690 | 0 | Delivery pending | 8.0 | Execution | Yes | 7 | FS | Low | 0 |  | Green | 1 | 1 | 2
9 | Define server | Execution | Person 10 | Not Started | 2024-08-16 | 2024-08-21 | 6 | 4 | 340 | 0 | Infra pending | 9.0 | Execution | No | 8 | FS | Low | 0 |  | Green | 5 | 6 | 7
10 | Configure server | Execution | Person 8 | Not Started | 2024-08-22 | 2024-08-24 | 3 | 1 | 200 | 0 |  | 10.0 | Execution | No | 9 | FS | Low | 0 |  | Green | 2 | 3 | 4
11 | Task 7 | Control | Person 2 | Not Started | 2024-08-22 | 2024-08-26 | 5 | 3 | 230 | 0 |  | 11.0 | Control | No | 10 | FS | Low | 0 |  | Green | 4 | 5 | 6
12 | Project Completion | Close | Person 1 | Not Started | 2024-08-26 | 2024-08-26 | 1 | 6 | 770 | 0 | Go-live signoff | 12.0 | Close | Yes | 11 | FS | Low | 0 |  | Green | 1 | 1 | 2
13 | Prepare PROD | Close | Person 8 | In Progress | 2024-08-27 | 2024-09-01 | 6 | 4 | 200 | 150 | Deployment prep | 13.0 | Close | No | 12 | FS | Medium | 50 |  | Amber | 5 | 6 | 7
14 | Create Guest List | Planning | Person 3 | Complete | 2024-08-03 | 2024-08-06 | 4 | 2 | 50 | 50 | Event planning carryover | 14.0 | Planning | No | 13 | FS | Low | 100 | 2024-08-06 | Green | 3 | 4 | 5
15 | Create Invitations | Communications | Person 4 | In Progress | 2024-08-07 | 2024-08-18 | 12 | 6 | 250 | 80 | Draft ready | 15.0 | Planning | No | 14 | FS | Medium | 50 |  | Amber | 11 | 12 | 13
16 | Finalize Other Hires | Procurement | Person 5 | Complete | 2024-08-08 | 2024-08-09 | 2 | 3 | 310 | 310 | A/V vendor | 16.0 | Execution | No | 15 | FS | Low | 100 | 2024-08-09 | Green | 1 | 2 | 3
17 | Hire Event | Procurement | Person 6 | Complete | 2024-08-10 | 2024-08-10 | 1 | 2 | 200 | 200 | Coordinator hired | 17.0 | Execution | Yes | 16 | FS | Low | 100 | 2024-08-10 | Green | 1 | 1 | 2
18 | Lock In Guest List | Planning | Person 2 | Not Started | 2024-08-11 | 2024-08-20 | 10 | 3 | 0 | 0 |  | 18.0 | Planning | No | 17 | FS | Low | 0 |  | Green | 9 | 10 | 11
19 | Party! | Execution | Person 9 | Not Started | 2024-08-28 | 2024-08-28 | 1 | 1 | 0 | 0 | Event day | 19.0 | Execution | Yes | 18 | FS | Low | 0 |  | Green | 1 | 1 | 2
20 | Plan Event Details | Planning | Person 4 | Complete | 2024-08-04 | 2024-08-14 | 11 | 7 | 290 | 290 | Run sheet | 20.0 | Planning | No | 19 | FS | Low | 100 | 2024-08-14 | Green | 10 | 11 | 12
21 | Purchase Invitation | Procurement | Person 8 | Complete | 2024-08-18 | 2024-08-19 | 2 | 2 | 280 | 280 | Printing | 21.0 | Execution | No | 20 | FS | Low | 100 | 2024-08-19 | Green | 1 | 2 | 3
22 | Purchase Required | Procurement | Person 8 | Complete | 2024-08-20 | 2024-08-22 | 3 | 3 | 280 | 280 | Supplies | 22.0 | Execution | No | 21 | FS | Low | 100 | 2024-08-22 | Green | 2 | 3 | 4
23 | Send Invitations | Communications | Person 9 | Complete | 2024-08-23 | 2024-08-23 | 1 | 1 | 8 | 8 | Email blast | 23.0 | Planning | Yes | 22 | FS | Low | 100 | 2024-08-23 | Green | 1 | 1 | 2
24 | Send Reminders | Communications | Person 10 | Complete | 2024-08-25 | 2024-08-25 | 1 | 1 | 0 | 0 | SMS reminders | 24.0 | Planning | Yes | 23 | FS | Low | 100 | 2024-08-25 | Green | 1 | 1 | 2
25 | Party! | Communications | person 11 | Overdue | 2025-08-05 | 2026-08-10 | 371 | 5 | 34234 | 2342 | Email blast | 25.0 | Execution | No | 31 | FS | High | 0 | 12-agu-25 | Red | 370 | 371 | 372
FS
FS
FS
FS
FS
FS
FS
FS
FS
TEAM MASTER | [6 empty] | STAKEHOLDERS MASTER | [6 empty] | No |  | FS | Low | 0 |  |  |  | STAKEHOLDERS MASTER
Name | Role | Rate ($/hr) | Department | Email | Location |  | Name | Role | Influence | Interest | Email | Status |  | No |  | FS | Low | 0 |  | Green |  | Name
Person 1 | Project Manager | 95 | PMO | person1@olympicintl.com | Los Angeles |  | Laura Chen | Sponsor | High | High | laura@olympicintl.com | Active |  | No |  | FS | Low | 0 |  | Green |  | Laura Chen
Person 2 | Business Analyst | 70 | PMO | person2@olympicintl.com | Los Angeles |  | Jonathan Lee | Finance Lead | High | High | jonathan@olympicintl.com | Active |  | No |  | FS | Low | 0 |  | Green |  | Jonathan Lee
Person 3 | Data Analyst | 65 | Data | person3@olympicintl.com | San Diego |  | Sandra Cortes | City Inspector | Medium | Low | sandra@city.gov | Pending |  | No |  | FS | Low | 0 |  | Green |  | Sandra Cortes
Person 4 | Designer | 60 | Design | person4@olympicintl.com | Austin |  | Dan Coleman | Venue Operator | High | Medium | dan@venue.com | Active |  | No |  | FS | Low | 0 |  | Green |  | Dan Coleman
Person 5 | Vendor Manager | 75 | Supply | person5@olympicintl.com | Chicago |  | Mark Wood | Procurement Lead | Medium | High | mark@olympicintl.com | Active |  | No |  | FS | Low | 0 |  | Green |  | Mark Wood
Person 6 | Coordinator | 55 | Ops | person6@olympicintl.com | Miami | [6 empty] | Person 6 |  | No |  | FS | Low | 0 |  | Green
Person 7 | QA Lead | 72 | QA | person7@olympicintl.com | Seattle | [6 empty] | Person 7 |  | No |  | FS | Low | 0 |  | Green
Person 8 | Engineer | 80 | IT | person8@olympicintl.com | New York | [6 empty] | Person 8 |  | No |  | FS | Low | 0 |  | Green
Person 9 | Comms Lead | 62 | Comms | person9@olympicintl.com | Boston | [6 empty] | Person 9 |  | No |  | FS | Low | 0 |  | Green
Person 10 | Sys Admin | 78 | IT | person10@olympicintl.com | Dallas | [6 empty] | Person 10 |  | No |  | FS | Low | 0 |  | Green
FS
FS
FS
FS
WBS MASTER | [11 empty] | WBS MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
WBS Code | Level 1 | Level 2 | Level 3 | Owner | Start | Finish | Budget ($) |  |  |  |  | WBS Code |  | No |  | FS | Low | 0 |  | Green |  | Budget ($)
1.0 | Initiation | Hardware | Install | Person 1 | 2024-08-01 | 2024-08-04 | 150 |  |  |  |  | 1.0 |  | No |  | FS | Low | 0 |  | Green | 149 | 150 | 151
2.0 | Planning | Task | Subtask | Person 2 | 2024-08-01 | 2024-08-12 | 670 |  |  |  |  | 2.0 |  | No |  | FS | Low | 0 |  | Green | 669 | 670 | 671
3.0 | Execution | Task | Subtask | Person 4 | 2024-08-13 | 2024-08-24 | 690 |  |  |  |  | 3.0 |  | No |  | FS | Low | 0 |  | Green | 689 | 690 | 691
4.0 | Control | Task | Subtask | Person 7 | 2024-08-13 | 2024-08-26 | 300 |  |  |  |  | 4.0 |  | No |  | FS | Low | 0 |  | Green | 299 | 300 | 301
5.0 | Close | Task | Subtask | Person 8 | 2024-08-27 | 2024-09-01 | 970 |  |  |  |  | 5.0 |  | No |  | FS | Low | 0 |  | Green | 969 | 970 | 971
FS
FS
FS
FS
FS
FS
FS
RISK MASTER | [11 empty] | RISK MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
Risk ID | Description | Impact | Response | Risk Level | Owner | Status | Date Opened | Target Date | Notes |  |  | Risk ID |  | No |  | FS | Low | 0 |  | Green |  | Date Opened
1 | Supplier delay | Timeline slip | Expedite alternate vendor | High | Person 5 | Open | 2024-08-05 | 2024-08-12 | Monitor daily |  |  | 1.0 |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-05
2 | Budget overrun | Cost increase | Cost freeze and review | Medium | Person 1 | Open | 2024-08-08 | 2024-08-20 | Weekly review |  |  | 2.0 |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-08
3 | Server issue | System downtime | Add backup environment | High | Person 10 | Open | 2024-08-10 | 2024-08-18 | Infra team |  |  | 3.0 |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-10
4 | Low attendance | Event impact | Marketing push | Low | Person 9 | Mitigated | 2024-08-11 | 2024-08-25 | Comms plan |  |  | 4.0 |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-11
FS
FS
FS
FS
ISSUE MASTER | [11 empty] | ISSUE MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
Issue ID | Description | Potential Impact | Priority | Date Opened | Date Closed | Owner | Department | Status | Notes |  |  | Issue ID |  | No |  | FS | Low | 0 |  | Green |  | Department
1 | Website loading slow | Lag in registration | High | 2024-08-03 |  | Person 10 | IT | Open | Investigating |  |  | 1.0 |  | No |  | FS | Low | 0 |  | Green |  | IT
2 | Guest list mismatch | Duplicate invites | Medium | 2024-08-04 |  | Person 3 | Data | Open | Clean file |  |  | 2.0 |  | No |  | FS | Low | 0 |  | Green |  | Data
3 | Vendor quote pending | Procurement delay | Low | 2024-08-06 | 2024-08-07 | Person 5 | Supply | Closed | Resolved |  |  | 3.0 |  | No |  | FS | Low | 0 |  | Green |  | Supply
FS
FS
FS
FS
FS
CHANGE LOG MASTER | [11 empty] | CHANGE LOG MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
Change # | Type | Description | Date Initiated | Status | Priority | Assigned | Expected Resolution | Action | Impact | Date Resolved |  | Change # |  | No |  | FS | Low | 0 |  | Green |  | Expected Resolution
1 | Product | Revise invite design | 2024-08-07 | Open | Medium | Person 4 | 3 days | Update artwork | Scope |  |  | 1.0 |  | No |  | FS | Low | 0 |  | Green |  | 3 days
2 | Schedule | Move rehearsal date | 2024-08-08 | Closed | High | Person 6 | 1 day | Rebook venue | Schedule | 2024-08-09 |  | 2.0 |  | No |  | FS | Low | 0 |  | Green |  | 1 day
FS
FS
FS
FS
FS
FS
DOC MASTER | [11 empty] | DOC MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
Phase | Document Name | Description | Owner | Status | Date Created | Last Updated | Location |  |  |  |  | Phase |  | No |  | FS | Low | 0 |  | Green |  | Location
Initiation | Business Case | Need and value statement | Person 1 | Approved | 2024-07-25 | 2024-07-28 | SharePoint/Initiation/Business_Case.docx |  |  |  |  | Initiation |  | No |  | FS | Low | 0 |  | Green |  | SharePoint/Initiation/Business_Case.docx
Initiation | Project Charter | Authorizes project | Person 1 | Approved | 2024-08-01 | 2024-08-01 | SharePoint/Initiation/Project_Charter.docx |  |  |  |  | Initiation |  | No |  | FS | Low | 0 |  | Green |  | SharePoint/Initiation/Project_Charter.docx
Planning | Schedule Management Plan | Planning baseline | Person 2 | Approved | 2024-08-02 | 2024-08-03 | SharePoint/Planning/Schedule_Plan.docx |  |  |  |  | Planning |  | No |  | FS | Low | 0 |  | Green |  | SharePoint/Planning/Schedule_Plan.docx
Execution | Status Reports | Weekly updates | Person 9 | In Progress | 2024-08-10 | 2024-08-15 | SharePoint/Execution/Status_Report.xlsx |  |  |  |  | Execution |  | No |  | FS | Medium | 50 |  | Amber |  | SharePoint/Execution/Status_Report.xlsx
FS
FS
FS
FS
RESOURCE PLAN MASTER | [11 empty] | RESOURCE PLAN MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
Resource | Team | Task | Hours | Rate | Date | Project | [5 empty] | Resource |  |  |  | FS | Low | 0 |  | Green
Person 1 | PMO | Kickoff | 6 | 95 | 2024-08-01 | Olympic 2024 | [5 empty] | Person 1 |  |  |  | FS | Low | 0 |  | Green
Person 3 | Data | Guest List | 8 | 65 | 2024-08-05 | Olympic 2024 | [5 empty] | Person 3 |  |  |  | FS | Low | 0 |  | Green
Person 4 | Design | Invitation Design | 10 | 60 | 2024-08-06 | Olympic 2024 | [5 empty] | Person 4 |  |  |  | FS | Low | 0 |  | Green
Person 9 | Comms | Reminders | 4 | 62 | 2024-08-20 | Olympic 2024 | [5 empty] | Person 9 |  |  |  | FS | Low | 0 |  | Green
FS
FS
FS
FS
CHANGE REQUEST MASTER | [11 empty] | CHANGE REQUEST MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
CR # | Project Name | Change Name | Requested By | Contact | Date | Description | Reason | Priority | Impact | Date Needed | Approval | CR # |  | No |  | FS | Low | 0 |  | Green |  | Reason
1 | Olympic 2024 | Add VIP seating | Person 1 | person1@olympicintl.com | 2024-08-09 | Add VIP rows near stage | Sponsor request | High | Layout + budget | 2024-08-20 | Pending | 1.0 |  | No |  | FS | Low | 0 |  | Green |  | Sponsor request
FS
FS
FS
FS
FS
FS
FS
MILESTONE MASTER | [11 empty] | MILESTONE MASTER |  | No |  | FS | Low | 0 |  |  |  | 0
Milestone | Description | Delivery Date | Status | Owner | [7 empty] | Milestone |  | No |  | FS | Low | 0 |  | Green
Business Case Approved | Approved by sponsor | 2024-07-28 | Done | Person 1 | [7 empty] | Business Case Approved |  | No |  | FS | Low | 0 |  | Green
Project Charter Approved | Signed charter | 2024-08-01 | Done | Person 1 | [7 empty] | Project Charter Approved |  | No |  | FS | Low | 0 |  | Green
Team Appointed | Core team assigned | 2024-08-02 | Done | Person 1 | [7 empty] | Team Appointed |  | No |  | FS | Low | 0 |  | Green
Project Office Established | Workspace/tools ready | 2024-08-03 | Done | Person 6 | [7 empty] | Project Office Established |  | No |  | FS | Low | 0 |  | Green
FS
FS
FS
FS
PRIORITIZATION MASTER | [11 empty] | PRIORITIZATION MASTER |  | No |  | FS | Low | 0
Task | Urgency | Importance | Quadrant | Action | Owner | Due Date | Notes |  |  |  |  | Task |  | No |  | FS | Low | 0 |  | Green |  | Notes
Fix athlete check-in system | High | High | DO NOW | Execute immediately | Person 8 | 2024-08-18 | Critical operations |  |  |  |  | Fix athlete check-in system |  | No |  | FS | Low | 0 |  | Green |  | Critical operations
Finalize sponsor deck | Low | High | DO LATER | Schedule next week | Person 4 | 2024-08-22 | Needs review |  |  |  |  | Finalize sponsor deck |  | No |  | FS | Low | 0 |  | Green |  | Needs review
Archive old media files | Low | Low | Delete or move | Remove/Archive | Person 3 | 2024-08-30 | Low value |  |  |  |  | Archive old media files |  | No |  | FS | Low | 0 |  | Green |  | Low value
Delegate badge printing QA | High | Low | Delegate | Assign to coordinator | Person 6 | 2024-08-20 | Track status |  |  |  |  | Delegate badge printing QA |  | No |  | FS | Low | 0 |  | Green |  | Track status
FS
FS
FS
FS
GAP ANALYSIS MASTER | [11 empty] | GAP ANALYSIS MASTER |  | No |  | FS | Low | 0
Focus | Current State | Future State | Gap % | Action | Priority | Start | End | Owner | Status |  |  | Focus |  | No |  | FS | Low | 0 |  | Green |  | End
Volunteer Capacity | 10 volunteers | 20 volunteers | 50 | Recruiting | Medium | 2024-08-01 | 2024-08-21 | Person 6 | In Progress |  |  | Volunteer Capacity |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-21
Registration Tablets | 6 tablets | 12 tablets | 50 | Purchase | High | 2024-08-05 | 2024-08-12 | Person 5 | Done |  |  | Registration Tablets |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-12
Parking Signage | 20 signs | 35 signs | 43 | Print signs | Low | 2024-08-10 | 2024-08-24 | Person 4 | Not Started |  |  | Parking Signage |  | No |  | FS | Low | 0 |  | Green |  | 2024-08-24
FS
FS
FS
FS
FS
STAKEHOLDER MASTER | [11 empty] | STAKEHOLDER MASTER |  | No |  | FS | Low | 0
Name | Title | Email | Influence | Interest | Priority | SME? | Decision Maker | Comm Freq | Comm Method | Current | Required | Phase | Contact | No |  | FS | Low | 0 |  | Green |  | Decision Maker
David Johnson | Sponsor | david@olympicintl.com | High | High | High | Yes | Yes | Weekly | In Person | Neutral | Supporter | Planning | 555-0101 | No |  | FS | Low | 0 |  | Green |  | Yes
Sally Feldman | Finance Lead | sally@olympicintl.com | Medium | High | Medium | Yes | No | Biweekly | Email | Passive | Neutral | Execution | 555-0102 | No |  | FS | Low | 0 |  | Green |  | No
Mike McPadden | Operations Head | mike@olympicintl.com | High | Medium | High | Yes | Yes | Weekly | Phone | Supporter | Supporter | Execution | 555-0103 | No |  | FS | Low | 0 |  | Green |  | Yes
Joyce Van Patten | City Liaison | joyce@lacity.gov | Low | High | Medium | No | No | Monthly | Meeting | Neutral | Supporter | Control | 555-0104 | No |  | FS | Low | 0 |  | Green |  | No
FS
FS
FS
FS
FS
COST BENEFIT MASTER | [11 empty] | COST BENEFIT MASTER |  | No |  | FS | Low | 0
Category | Type | Year1 | Year2 | Year3 | Year4 | Year5 | Year6 | Notes |  |  |  | Category |  | No |  | FS | Low | 0 |  | Green |  | Year6
Rent | Indirect Cost | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | Venue operations |  |  |  | Rent |  | No |  | FS | Low | 0 |  | Green | 1499 | 1500 | 1501
Utilities | Indirect Cost | 200 | 220 | 240 | 260 | 280 | 300 | Electricity/IT |  |  |  | Utilities |  | No |  | FS | Low | 0 |  | Green | 299 | 300 | 301
Production levels | Intangible Cost | 500 | 400 | 600 | 800 | 500 | 300 | Learning curve |  |  |  | Production levels |  | No |  | FS | Low | 0 |  | Green | 299 | 300 | 301
Ticket Revenue | Benefit | 3500 | 4200 | 4600 | 5100 | 5300 | 5600 | Projected inflow |  |  |  | Ticket Revenue |  | No |  | FS | Low | 0 |  | Green | 5599 | 5600 | 5601
Sponsor Revenue | Benefit | 2000 | 2400 | 2600 | 2800 | 3000 | 3200 | Partnership growth |  |  |  | Sponsor Revenue |  | No |  | FS | Low | 0 |  | Green | 3199 | 3200 | 3201
FS
FS
FS
FS
FS
RAID MASTER | [11 empty] | RAID MASTER |  | No |  | FS | Low | 0
ID | Category | Description | Impact | Response | Priority | Owner | Status | Notes |  |  |  | ID |  | No |  | FS | Low | 0 |  | Green |  | Status
1 | Risk | Machinery breakdown | Delay schedule | Backup supplier | High | Joyce | Open | SAMPLE |  |  |  | 1.0 |  | No |  | FS | Low | 0 |  | Green |  | Open
2 | Assumption | Machine uptime 95% | Cost variance | Monitor weekly | High | Dan | Open | SAMPLE |  |  |  | 2.0 |  | No |  | FS | Low | 0 |  | Green |  | Open
3 | Issue | Late permit review | Schedule slip | Escalate city office | Low | Helen | In Progress | SAMPLE |  |  |  | 3.0 |  | No |  | FS | Low | 0 |  | Green |  | In Progress
4 | Dependency | Venue access approval | Blocked setup | Confirm date | Medium | Hank | Open | SAMPLE |  |  |  | 4.0 |  | No |  | FS | Low | 0 |  | Green |  | Open
FS
FS
LESSONS LEARNED MASTER
Type | Description | Impact | Future Change | Action Items | Owner
WIN | Daily standups improved coordination | Saved 20 hours | Standardize for all events | Publish playbook | Person 1
ISSUE | Late vendor onboarding | Two-day delay | Prequalify vendors earlier | Create vendor checklist | Person 5
WIN | Shared dashboard improved visibility | Fewer status meetings | Use common dashboard | Train all leads | Person 2
DECISION MATRIX MASTER
Criteria | Weight | Option A | Option B | Option C | A Score | B Score | C Score
Quality | 2 | 3 | 2 | 2 | 6 | 4 | 4
Cost | 5 | 3 | 3 | 5 | 15 | 15 | 25
Value to Customer | 3 | 4 | 3 | 5 | 12 | 9 | 15
Safety/Environment | 1 | 3 | 3 | 5 | 3 | 3 | 5
Support to Solution | 3 | 4 | 4 | 5 | 12 | 12 | 15
Training Factors | 2 | 3 | 2 | 4 | 6 | 4 | 8
COMMUNICATION PLAN MASTER
Communication Activity | Objective | Audience | Frequency | Owner | Channel | Key Message
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Status Update Emails | Provide progress updates | All Team Members | Weekly | Project Coordinator | Email | Current status and next steps
Monthly Steering Committee | Review project milestones | Steering Committee | Monthly | Project Sponsor | Virtual Meeting | Milestone review and decisions
Team Meetings | Discuss work progress | Project Team | Bi-Weekly | Team Lead | Conference Call | Task updates and issue resolution
Client Reports | Share progress and budget status | Client / Sponsor | Monthly | Account Manager | Email | Progress, risks, and financial summary
Project Newsletter | Share highlights | All Employees | Monthly | Communications Lead | Newsletter | Success stories and upcoming milestones
COMMUNICATION MATRIX MASTER
Role | Kickoff Meeting | Status Update Emails | Steering Committee | Team Meetings | Client Reports | Project Newsletter
Project Manager | R | R | R | R | C | R
Project Coordinator | R | R | R | C | C | R
Project Sponsor | R | C | A | C | A | C
Team Lead | C | R | C | R | I | I
Account Manager | I | C | C | C | R | R
Communications Lead | A | A | C | A | C | A
Project Team | I | A | I | A | I | I
All Employees | I | I | I | I | I | A
COST ESTIMATION MASTER
Task/Item | Description | Hours/Qty | Unit Cost | Dependencies | Notes
Research & Planning | Initial project research | 20 | 50 | Client approval | Review materials
Design & Development | UI/UX design | 50 | 75 | Design specs | Prototype creation
Testing & QA | Functionality testing | 30 | 40 | Bug fixes | Testing reports
QUALITY MANAGEMENT MASTER
Field | Value
Quality Objective 1 | Improve user experience
Quality Objective 2 | Ensure 100% functionality
Quality Objective 3 | Deliver project on schedule
Standard 1 | Responsive Design
Standard 2 | Load Time <3 Seconds
Standard 3 | No Critical Defects
QA Activity 1 | Design Reviews
QA Activity 2 | Code Inspections
QA Activity 3 | Documentation Audits
QA Activity 4 | Team Training Sessions
Prepared By | John Smith
Reviewed By | Jane Doe
Approval Date | 2024-01-20
Next Review Date | 2024-05-15
PROCUREMENT MANAGEMENT MASTER
Item/Service | Description | Procurement Method | Supplier | Est. Cost | Timeline
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
IT Equipment | Computers, servers | RFP | Tech Solutions Inc. | 75000 | Q1 2024
Construction Services | Interior build-out work | Direct Contract | BuildRight Contractors | 120000 | Q2 2024
Office Supplies | Stationery and supplies | Purchase Order | SupplyMart | 10000 | Ongoing
PROCUREMENT RISK MASTER
Risk | Mitigation Strategy
Delays in Delivery | Set clear timelines and penalties for late delivery
Budget Overruns | Regular cost reviews and contingency fund
PROJECT BUDGET TRACKER MASTER
Date | Category | Description | Vendor | Cost | Status
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-22 | Marketing | Online Ads | Google | 8500 | Approved
2024-02-05 | Travel | Client Meeting | Delta Airlines | 2300 | Pending
2024-02-16 | Materials | Office Supplies | Staples | 1200 | Approved
2024-03-02 | Consultants | Design Services | Creative Co. | 5500 | Approved
2024-03-15 | Software | Project Software | SoftTech Inc. | 7950 | Approved
PROJECT INITIATION CHECKLIST MASTER
Task | Description | Owner | Due Date | Status | Progress
Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
Identify Stakeholders | List key stakeholders and their roles. | Bob | 2024-01-17 | Complete | 100
Develop Business Case | Create a business case document. | Sarah | 2024-01-20 | In Progress | 60
Establish Project Team | Assign project team members. | John | 2024-01-22 | Not Started | 0
Create Project Charter | Draft the project charter document. | Emma | 2024-01-25 | Not Started | 0
Conduct Feasibility Study | Analyze project feasibility and risks. | Mike | 2024-01-28 | Not Started | 0
PROJECT KICKOFF AGENDA MASTER
Time | Agenda Item | Presenter | Details
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:15 AM - 10:35 AM | Project Overview | Jane Smith | Project goals, scope, and timeline
10:35 AM - 11:00 AM | Roles & Responsibilities | Michael Brown | Team roles and key responsibilities
11:00 AM - 11:20 AM | Project Plan & Milestones | Lisa Turner | Key deliverables and timeline overview
11:20 AM - 11:40 AM | Communication Plan | David Lee | Communication tools and protocols
11:40 AM - 11:50 AM | Q&A Session | All Participants | Open floor for questions
11:50 AM - 12:00 PM | Next Steps & Closing Remarks | Project Manager | Summary of action items and next steps
CHANGE MANAGEMENT MASTER
ID | Change Description | Area Affected | Impact Level | Comments | Task | Owner | Status | Audience | Method
C-001 | Upgrade Software Platform | IT Department | High | System downtime | Software Installation | Michael | In Progress | All Employees | Email Updates
C-002 | Process Workflow Adjustment | Customer Service | Medium | Training needed | Staff Training | Sarah | Not Started | Team Leaders | Meetings
C-003 | Policy Update | Finance Dept. | Low | Minor impact | Policy Revision | David | Completed | Stakeholders | Status Reports
MEETING MINUTES MASTER
Meeting Date | Meeting Time | Location | Meeting Leader | Attendee | Agenda Item | Presenter | Discussion Notes | Action Item | Responsible | Due Date | Action Status
2024-02-15 | 10:00 AM | Los Angeles HQ | John Smith | John Smith | Project Timeline | John Smith | Reviewed updated project schedule. | Finalize timeline and share with team | John Smith | 2024-02-18 | Open
2024-02-15 | 10:00 AM | Los Angeles HQ | John Smith | Sarah Lee | Budget Update | Sarah Lee | Discussed budget adjustments needed. | Prepare revised budget report | Sarah Lee | 2024-02-17 | Open
2024-02-15 | 10:00 AM | Los Angeles HQ | John Smith | Michael Brown | Design Review | Michael Brown | Reviewed design concepts and feedback. | Update design based on feedback | Michael Brown | 2024-02-20 | Open
TASK ASSIGNMENT MASTER
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Progress
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T002 | Design Website Mockup | Emma Davis | Medium | 2024-05-12 | Not Started | 0
T003 | Write Marketing Report | Michael Brown | High | 2024-05-08 | Completed | 100
T004 | Client Meeting | Sara Lee | High | 2024-05-07 | Scheduled | 0
T005 | Code Review | David Wilson | Low | 2024-05-09 | Completed | 100
T006 | Prepare Presentation | Laura Clark | Medium | 2024-05-11 | In Progress | 60
T007 | Data Analysis | James Miller | High | 2024-05-13 | Not Started | 0
T008 | Test Software | Linda Harris | Medium | 2024-05-10 | In Testing | 75
T009 | Create User Manual | Kevin Anderson | Low | 2024-05-14 | In Review | 30
T010 | Finalize Budget Report | Rachel Green | High | 2024-05-10 | Pending | 0
COMMUNICATION LOG MASTER
Date | Time | Contact Person | Method | Subject / Topic | Discussion Summary | Action Items | Next Steps / Follow-Up
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-16 | 02:00 PM | Sarah Lee | Phone Call | Budget Update | Discussed budget adjustments needed. | Prepare revised budget report. | Send report by 2024-02-17
2024-02-17 | 09:30 AM | Michael Brown | Meeting | Design Review | Reviewed design concepts and feedback. | Update design based on feedback. | Share new designs by 2024-02-20
2024-02-18 | 01:00 PM | Lisa Clark | Video Conference | Client Presentation | Planned upcoming client presentation. | Create presentation slides. | Rehearse on 2024-02-21
PROJECT CLOSURE MASTER
Field | Value
Project ID | PL2021-005
Closure Date | 2024-12-15
Project Objective | Successful launch of event to market
Performance Scope | Met
Performance Schedule | Delayed
Performance Budget | On Budget
Performance Quality | High Quality
What Went Well | Effective teamwork and clear communication
What Could Improve | Better risk management and contingency planning
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Instructions
Instructions
How to enter data once and have every template update automatically
1) Start here: Fill the Data sheet
• Open the sheet named Data. This is the main sheet you type into.
• Update Project Info (Project Name, Manager/Lead, Sponsor, Dates, Budget).
• Enter / update Tasks, Milestones, Costs, Risks, Stakeholders, and logs in the Data tables.
2) Dashboard & templates update automatically
• All other sheets pull from Data using formulas. When you change Data, everything updates.
• If charts don’t update immediately: Formulas → Calculate Now (or reopen the file).
3) Recommended workflow
• Step A: Update Data → Project Info + Tasks + Costs + Risks.
• Step B: Review Project Dashboard for overall status.
• Step C: Use supporting templates (Communication Plan, Budget Tracker, Change Plan, Meeting Minutes).
4) Tips to avoid errors
• Do not rename or delete sheets (formulas reference them).
• Do not delete columns in Data tables—append new rows at the bottom instead.
• Use consistent date format (YYYY-MM-DD recommended).
• If you insert rows, insert inside the table area (not above headers).
5) Color palette used in this workbook
Hex | Usage | Sample
#2F5597 | Workbook theme color
#1F3A5F | Workbook theme color
#548235 | Workbook theme color
#92D050 | Workbook theme color
#ED7D31 | Workbook theme color
#C00000 | Workbook theme color
#FFC000 | Workbook theme color
#70AD47 | Workbook theme color
#4472C4 | Workbook theme color
Tip: To extend the system, add rows to Data tables (do not overwrite formula areas on other sheets).
Desclimer
There are a few glitches in this template due to Excel limitations. Specifically, we cannot apply two formulas in the same cell at the same time.
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Benefits
BENEFITS OF USING THIS TEMPLATE
Edit the Data sheet once — dashboards, trackers, and planning templates update automatically
Centralized Data Entry | Enter project information, tasks, costs, risks, issues, and changes in one place for faster updates and fewer mistakes.
Automatic Template Updates | Linked formulas and references help multiple sheets refresh from the Data sheet without retyping the same information.
Consistent Reporting | Status reports, trackers, and dashboards stay aligned because they are driven by the same source data.
Time Saving Workflow | Reduces manual copy-paste work and helps teams spend more time on decisions instead of formatting files.
Better Accuracy | Structured tables and synchronized calculations improve reliability and reduce broken links across sheets.
Executive Visibility | Dashboards and summary sheets provide quick insight into progress, cost, risks, and workload.
Scalable for Many Projects | Use for a single initiative or multiple projects while keeping records organized and easy to maintain.
Ready for Collaboration | Clear sheet structure makes handover, review, and team updates easier for managers, coordinators, and stakeholders.
Tip: Update the Data sheet first. Avoid typing the same information on linked templates unless the sheet is intentionally a standalone form.
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Template22
TEMPLATE22 ¦ HISTORY, LEGACY, WORKING MODEL & IMPACT
About TEMPLATE22 and Tariq Noor
Template22 grew from real project delivery needs and a simple idea: make professional planning tools practical, clear, and fast to use. Over time, its templates built a legacy of dependable structure, better reporting, and stronger team coordination. TEMPLATE22 works by combining organized data sheets, linked formulas, and ready-to-use formats that reduce manual effort and support daily organizational work. Many users save time, avoid mistakes, and make better decisions through these systems. Tariq Noor deserves special appreciation for creating useful, user-focused solutions with consistency, generosity, and high standards, helping professionals work smarter, present better, and improve project outcomes with confidence globally.
Legacy | Dependable templates and structured systems
Working | Linked data + formulas + ready formats
Impact | Saves time, reduces errors, improves decisions
Creator | Tariq Noor: practical, generous, quality-focused
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Plan
PROJECT PLAN TEMPLATE
Project Goals and Objectives
Deliver Functional and Market-Ready Outcome |  |  | Coordinate with teams and stakeholders to ensure scoped deliverables are complete.
Ensure High-Quality Standards |  |  | Apply inspections and acceptance checks before handover.
Maintain Safe and Compliant Conditions |  |  | Track issues, risks, and compliance actions across execution.
Project Success Criteria
Category | Success Metrics | Measurement Method | Target | Assigned to
Scope | Tasks entered in Data | Task Count | 39 | Project Lead
Schedule | Completion ratio | Complete / Total | 28.21% | Scheduler
Budget | Variance | Budget - Actual | 200 | Finance
Risk | Overdue tasks | Overdue Count | 2 | Risk Manager
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Execution Plan
PROJECT EXECUTION PLAN TEMPLATE
Project |  |  | Project Manager |  |  | Project Sponsor |  |  | Date Revised
Olympic 2026 |  |  | Template22 |  |  | Olympic International |  |  | 45641
Key Project Team Members | [5 empty] | Stakeholders
Name |  |  | Role |  |  | Name |  |  | Role
Person 1 |  |  | Project Manager |  |  | Laura Chen |  |  | Sponsor
Person 2 |  |  | Business Analyst |  |  | Jonathan Lee |  |  | Finance Lead
Person 3 |  |  | Data Analyst |  |  | Sandra Cortes |  |  | City Inspector
Person 4 |  |  | Designer |  |  | Dan Coleman |  |  | Venue Operator
Person 5 |  |  | Vendor Manager |  |  | Mark Wood |  |  | Procurement Lead
Project Scope and Timeline
Project Tasks | Deliverables | Priority | Assigned To | Estimated Duration | Planned Start | Actual Start | Planned Finish | Actual Finish | Status | Percentage Completion
Meet Client | Initiation | Low | Person 1 | 4 | 2024-08-01 | 2024-08-01 | 2024-08-04 | 2024-08-04 | Complete | 100
Requirements | Planning | Low | Person 2 | 2 | 2024-08-01 | 2024-08-01 | 2024-08-02 | 2024-08-02 | Complete | 100
Inputs | Planning | High | Person 3 | 1 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 0 | Overdue | 0
Design | Planning | Low | Person 4 | 7 | 2024-08-06 | 2024-08-06 | 2024-08-12 | 2024-08-12 | Complete | 100
Project Testing | Execution | Medium | Person 1 | 1 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 0 | In Progress | 50
Process | Execution | Medium | Person 2 | 3 | 2024-08-13 | 2024-08-13 | 2024-08-15 | 0 | In Progress | 50
Data model | Execution | Medium | Person 3 | 10 | 2024-08-06 | 2024-08-06 | 2024-08-15 | 0 | In Progress | 50
Project Deliver | Execution | Low | Person 7 | 1 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 0 | Not Started | 0
Define server | Execution | Low | Person 10 | 6 | 2024-08-16 | 2024-08-16 | 2024-08-21 | 0 | Not Started | 0
Configure server | Execution | Low | Person 8 | 3 | 2024-08-22 | 2024-08-22 | 2024-08-24 | 0 | Not Started | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Charter
PROJECT CHARTER TEMPLATE FOR EXCEL
Project Title | Olympic 2026
Project Sponsor Name | Olympic International
Project Manager Name | Template22
Project Start Date | 45509
Project Completion Date | 46275
Project Budget | 5500
Project Purpose / Justification | Single source of truth for planning, tracking, reporting, budgeting, and scheduling.
Project Goals and Objectives
Deliver Functional and Market-Ready Outcome |  |  | Coordinate with teams and stakeholders to ensure scoped deliverables are complete.
Ensure High-Quality Standards |  |  | Apply inspections and acceptance checks before handover.
Maintain Safe and Compliant Conditions |  |  | Track issues, risks, and compliance actions across execution.
High-Level Requirements & Project Success Criteria
Category | Success Metrics | Measurement Method | Target | Assigned to
Scope | Tasks entered in Data | Task Count | 39 | Project Lead
Schedule | Completion ratio | Complete / Total | 0.28205 | Scheduler
Budget | Variance | Budget - Actual | 200 | Finance
Risk | Overdue tasks | Overdue Count | 2 | Risk Manager
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Task Tracking
TASK TRACKING TEMPLATE
Task Name/Description | Dependent Tasks | Assigned To | Priority | Start Date | Planned End Date | Actual End Date | Status | Notes | RAG | % Complete | Cost ($)
Meet Client | 0 | Person 1 | Low | 2024-08-01 | 2024-08-04 | 2024-08-04 | Complete | Kickoff approved | Green | 100 | 150
Requirements | 1 | Person 2 | Low | 2024-08-01 | 2024-08-02 | 2024-08-02 | Complete | Requirements draft | Green | 100 | 140
Inputs | 2 | Person 3 | High | 2024-08-05 | 2024-08-05 | 0 | Overdue | Missing vendor input | Red | 0 | 200
Design | 3 | Person 4 | Low | 2024-08-06 | 2024-08-12 | 2024-08-12 | Complete | Design reviewed | Green | 100 | 180
Project Testing | 4 | Person 1 | Medium | 2024-08-12 | 2024-08-12 | 0 | In Progress | Testing ongoing | Amber | 50 | 430
Process | 5 | Person 2 | Medium | 2024-08-13 | 2024-08-15 | 0 | In Progress | Workflow updates | Amber | 50 | 120
Data model | 6 | Person 3 | Medium | 2024-08-06 | 2024-08-15 | 0 | In Progress | Data mapping | Amber | 50 | 90
Project Deliver | 7 | Person 7 | Low | 2024-08-15 | 2024-08-15 | 0 | Not Started | Delivery pending | Green | 0 | 0
Define server | 8 | Person 10 | Low | 2024-08-16 | 2024-08-21 | 0 | Not Started | Infra pending | Green | 0 | 0
Configure server | 9 | Person 8 | Low | 2024-08-22 | 2024-08-24 | 0 | Not Started | 0 | Green | 0 | 0
Task 7 | 10 | Person 2 | Low | 2024-08-22 | 2024-08-26 | 0 | Not Started | 0 | Green | 0 | 0
Project Completion | 11 | Person 1 | Low | 2024-08-26 | 2024-08-26 | 0 | Not Started | Go-live signoff | Green | 0 | 0
Prepare PROD | 12 | Person 8 | Medium | 2024-08-27 | 2024-09-01 | 0 | In Progress | Deployment prep | Amber | 50 | 150
Create Guest List | 13 | Person 3 | Low | 2024-08-03 | 2024-08-06 | 2024-08-06 | Complete | Event planning carryover | Green | 100 | 50
Create Invitations | 14 | Person 4 | Medium | 2024-08-07 | 2024-08-18 | 0 | In Progress | Draft ready | Amber | 50 | 80
Finalize Other Hires | 15 | Person 5 | Low | 2024-08-08 | 2024-08-09 | 2024-08-09 | Complete | A/V vendor | Green | 100 | 310
Hire Event | 16 | Person 6 | Low | 2024-08-10 | 2024-08-10 | 2024-08-10 | Complete | Coordinator hired | Green | 100 | 200
Lock In Guest List | 17 | Person 2 | Low | 2024-08-11 | 2024-08-20 | 0 | Not Started | 0 | Green | 0 | 0
Party! | 18 | Person 9 | Low | 2024-08-28 | 2024-08-28 | 0 | Not Started | Event day | Green | 0 | 0
Plan Event Details | 19 | Person 4 | Low | 2024-08-04 | 2024-08-14 | 2024-08-14 | Complete | Run sheet | Green | 100 | 290
Purchase Invitation | 20 | Person 8 | Low | 2024-08-18 | 2024-08-19 | 2024-08-19 | Complete | Printing | Green | 100 | 280
Purchase Required | 21 | Person 8 | Low | 2024-08-20 | 2024-08-22 | 2024-08-22 | Complete | Supplies | Green | 100 | 280
Send Invitations | 22 | Person 9 | Low | 2024-08-23 | 2024-08-23 | 2024-08-23 | Complete | Email blast | Green | 100 | 8
Send Reminders | 23 | Person 10 | Low | 2024-08-25 | 2024-08-25 | 2024-08-25 | Complete | SMS reminders | Green | 100 | 0
Party! | 31 | person 11 | High | 2025-08-05 | 2026-08-10 | 12-agu-25 | Overdue | Email blast | Red | 0 | 2342
0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Network Diagram
PROJECT NETWORK DIAGRAM TEMPLATE
Task | Task Name | Predecessor | Dependency | Duration | Start | Finish | Node From | Node To | Critical
1 | Meet Client | 0 | FS | 4 | 2024-08-01 | 2024-08-04 | Node 0 | Node 1 | No
2 | Requirements | 1 | FS | 2 | 2024-08-01 | 2024-08-02 | Node 1 | Node 2 | No
3 | Inputs | 2 | FS | 1 | 2024-08-05 | 2024-08-05 | Node 2 | Node 3 | Yes
4 | Design | 3 | FS | 7 | 2024-08-06 | 2024-08-12 | Node 3 | Node 4 | No
5 | Project Testing | 4 | FS | 1 | 2024-08-12 | 2024-08-12 | Node 4 | Node 5 | No
6 | Process | 5 | FS | 3 | 2024-08-13 | 2024-08-15 | Node 5 | Node 6 | No
7 | Data model | 6 | FS | 10 | 2024-08-06 | 2024-08-15 | Node 6 | Node 7 | No
8 | Project Deliver | 7 | FS | 1 | 2024-08-15 | 2024-08-15 | Node 7 | Node 8 | No
9 | Define server | 8 | FS | 6 | 2024-08-16 | 2024-08-21 | Node 8 | Node 9 | No
10 | Configure server | 9 | FS | 3 | 2024-08-22 | 2024-08-24 | Node 9 | Node 10 | No
11 | Task 7 | 10 | FS | 5 | 2024-08-22 | 2024-08-26 | Node 10 | Node 11 | No
12 | Project Completion | 11 | FS | 1 | 2024-08-26 | 2024-08-26 | Node 11 | Node 12 | No
13 | Prepare PROD | 12 | FS | 6 | 2024-08-27 | 2024-09-01 | Node 12 | Node 13 | No
14 | Create Guest List | 13 | FS | 4 | 2024-08-03 | 2024-08-06 | Node 13 | Node 14 | No
15 | Create Invitations | 14 | FS | 12 | 2024-08-07 | 2024-08-18 | Node 14 | Node 15 | No
16 | Finalize Other Hires | 15 | FS | 2 | 2024-08-08 | 2024-08-09 | Node 15 | Node 16 | No
17 | Hire Event | 16 | FS | 1 | 2024-08-10 | 2024-08-10 | Node 16 | Node 17 | No
18 | Lock In Guest List | 17 | FS | 10 | 2024-08-11 | 2024-08-20 | Node 17 | Node 18 | No
19 | Party! | 18 | FS | 1 | 2024-08-28 | 2024-08-28 | Node 18 | Node 19 | No
20 | Plan Event Details | 19 | FS | 11 | 2024-08-04 | 2024-08-14 | Node 19 | Node 20 | No
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Status Report
STATUS REPORT TEMPLATE
Project Information
Project Name | Olympic 2026
Reporting Period | 5-Aug-24 to 10-Sep-26
Report Date | 45641
Project Manager | Template22
Project Sponsor | Olympic International
Project Status Summary
Total Tasks: 39, Complete: 11, In Progress: 6, Overdue: 2, Cost Used: $5,300.
Completed Work
Action Item | Date | RAG | Owner | Comments
Meet Client | 2024-08-04 | Green | Person 1 | Kickoff approved
Requirements | 2024-08-02 | Green | Person 2 | Requirements draft
Inputs | 2024-08-05 | Red | Person 3 | Missing vendor input
Design | 2024-08-12 | Green | Person 4 | Design reviewed
Project Testing | 2024-08-12 | Amber | Person 1 | Testing ongoing
Upcoming Work
Action Item | Date | RAG | Owner | Comments
Data model | 2024-08-15 | Amber | Person 3 | Data mapping
Project Deliver | 2024-08-15 | Green | Person 7 | Delivery pending
Define server | 2024-08-21 | Green | Person 10 | Infra pending
Configure server | 2024-08-24 | Green | Person 8 | 0
Task 7 | 2024-08-26 | Green | Person 2 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Budget
PROJECT BUDGET TEMPLATE
Project Name | Olympic 2026
Department | Event Operations area
Supervisor Name | Template22
Budget Tracking
WBS | Project Tasks | Assigned To | Planned | Actual Hours | Rate | Labor | Materials | Travel | Equipment | BUDGETED | ACTUAL | BALANCE
1.0 | Meet Client | Person 1 | 2 | 2 | 95 | 190 | 0 | 150 | 0 | 150 | 340 | -190
2.0 | Requirements | Person 2 | 2 | 2 | 70 | 140 | 0 | 0 | 0 | 140 | 280 | -140
3.0 | Inputs | Person 3 | 1 | 0 | 65 | 0 | 0 | 0 | 0 | 200 | 200 | 0
4.0 | Design | Person 4 | 5 | 5 | 60 | 300 | 0 | 0 | 0 | 180 | 480 | -300
5.0 | Project Testing | Person 1 | 2 | 1 | 95 | 95 | 0 | 0 | 0 | 670 | 525 | 145
6.0 | Process | Person 2 | 3 | 1.5 | 70 | 105 | 0 | 0 | 0 | 300 | 225 | 75
7.0 | Data model | Person 3 | 8 | 4 | 65 | 260 | 0 | 0 | 0 | 200 | 350 | -150
8.0 | Project Deliver | Person 7 | 6 | 0 | 72 | 0 | 0 | 0 | 0 | 690 | 0 | 690
9.0 | Define server | Person 10 | 4 | 0 | 78 | 0 | 0 | 0 | 0 | 340 | 0 | 340
10.0 | Configure server | Person 8 | 1 | 0 | 80 | 0 | 0 | 0 | 0 | 200 | 0 | 200
11.0 | Task 7 | Person 2 | 3 | 0 | 70 | 0 | 0 | 0 | 0 | 230 | 0 | 230
12.0 | Project Completion | Person 1 | 6 | 0 | 95 | 0 | 0 | 0 | 0 | 770 | 0 | 770
13.0 | Prepare PROD | Person 8 | 4 | 2 | 80 | 160 | 0 | 0 | 0 | 200 | 310 | -110
14.0 | Create Guest List | Person 3 | 2 | 2 | 65 | 130 | 0 | 0 | 0 | 50 | 180 | -130
15.0 | Create Invitations | Person 4 | 6 | 3 | 60 | 180 | 0 | 0 | 0 | 250 | 260 | -10
16.0 | Finalize Other Hires | Person 5 | 3 | 3 | 75 | 225 | 0 | 0 | 0 | 310 | 535 | -225
17.0 | Hire Event | Person 6 | 2 | 2 | 55 | 110 | 0 | 0 | 0 | 200 | 310 | -110
18.0 | Lock In Guest List | Person 2 | 3 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19.0 | Party! | Person 9 | 1 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20.0 | Plan Event Details | Person 4 | 7 | 7 | 60 | 420 | 0 | 0 | 0 | 290 | 710 | -420
SUBTOTAL |  |  | 71 | 34.5 |  | 2315 | 0 | 150 | 0 | 5370 | 4705 | 665
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Critical Path Method
CRITICAL PATH METHOD TEMPLATE
Task Name | Preceding Tasks | Estimated Duration | ES | EF | LS | LF | Slack | Critical | Start | Finish | Status
Meet Client | 0 | 4 | 0 | 4 | 22 | 26 | 22 | No | 2024-08-01 | 2024-08-04 | Complete
Requirements | 1 | 2 | 1 | 3 | 24 | 26 | 23 | No | 2024-08-01 | 2024-08-02 | Complete
Inputs | 2 | 1 | 2 | 3 | 25 | 26 | 23 | No | 2024-08-05 | 2024-08-05 | Overdue
Design | 3 | 7 | 3 | 10 | 19 | 26 | 16 | No | 2024-08-06 | 2024-08-12 | Complete
Project Testing | 4 | 1 | 4 | 5 | 25 | 26 | 21 | No | 2024-08-12 | 2024-08-12 | In Progress
Process | 5 | 3 | 5 | 8 | 23 | 26 | 18 | No | 2024-08-13 | 2024-08-15 | In Progress
Data model | 6 | 10 | 6 | 16 | 16 | 26 | 10 | No | 2024-08-06 | 2024-08-15 | In Progress
Project Deliver | 7 | 1 | 7 | 8 | 25 | 26 | 18 | No | 2024-08-15 | 2024-08-15 | Not Started
Define server | 8 | 6 | 8 | 14 | 20 | 26 | 12 | No | 2024-08-16 | 2024-08-21 | Not Started
Configure server | 9 | 3 | 9 | 12 | 23 | 26 | 14 | No | 2024-08-22 | 2024-08-24 | Not Started
Task 7 | 10 | 5 | 10 | 15 | 21 | 26 | 11 | No | 2024-08-22 | 2024-08-26 | Not Started
Project Completion | 11 | 1 | 11 | 12 | 25 | 26 | 14 | No | 2024-08-26 | 2024-08-26 | Not Started
Prepare PROD | 12 | 6 | 12 | 18 | 20 | 26 | 8 | No | 2024-08-27 | 2024-09-01 | In Progress
Create Guest List | 13 | 4 | 13 | 17 | 22 | 26 | 9 | No | 2024-08-03 | 2024-08-06 | Complete
Create Invitations | 14 | 12 | 14 | 26 | 14 | 26 | 0 | Yes | 2024-08-07 | 2024-08-18 | In Progress
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## PERT Chart
PERT CHART TEMPLATE
Task Name | Predecessor | Optimistic Time | Most Likely Time | Pessimistic Time | Expected Time | Variance | Start | Finish | Owner | Status | Node
Meet Client | 0 | 3 | 4 | 5 | 4 | 0.11111 | 2024-08-01 | 2024-08-04 | Person 1 | Complete | Node 1
Requirements | 1 | 1 | 2 | 3 | 2 | 0.11111 | 2024-08-01 | 2024-08-02 | Person 2 | Complete | Node 2
Inputs | 2 | 1 | 1 | 2 | 1.1667 | 0.027778 | 2024-08-05 | 2024-08-05 | Person 3 | Overdue | Node 3
Design | 3 | 6 | 7 | 8 | 7 | 0.11111 | 2024-08-06 | 2024-08-12 | Person 4 | Complete | Node 4
Project Testing | 4 | 1 | 1 | 2 | 1.1667 | 0.027778 | 2024-08-12 | 2024-08-12 | Person 1 | In Progress | Node 5
Process | 5 | 2 | 3 | 4 | 3 | 0.11111 | 2024-08-13 | 2024-08-15 | Person 2 | In Progress | Node 6
Data model | 6 | 9 | 10 | 11 | 10 | 0.11111 | 2024-08-06 | 2024-08-15 | Person 3 | In Progress | Node 7
Project Deliver | 7 | 1 | 1 | 2 | 1.1667 | 0.027778 | 2024-08-15 | 2024-08-15 | Person 7 | Not Started | Node 8
Define server | 8 | 5 | 6 | 7 | 6 | 0.11111 | 2024-08-16 | 2024-08-21 | Person 10 | Not Started | Node 9
Configure server | 9 | 2 | 3 | 4 | 3 | 0.11111 | 2024-08-22 | 2024-08-24 | Person 8 | Not Started | Node 10
Task 7 | 10 | 4 | 5 | 6 | 5 | 0.11111 | 2024-08-22 | 2024-08-26 | Person 2 | Not Started | Node 11
Project Completion | 11 | 1 | 1 | 2 | 1.1667 | 0.027778 | 2024-08-26 | 2024-08-26 | Person 1 | Not Started | Node 12
Prepare PROD | 12 | 5 | 6 | 7 | 6 | 0.11111 | 2024-08-27 | 2024-09-01 | Person 8 | In Progress | Node 13
Create Guest List | 13 | 3 | 4 | 5 | 4 | 0.11111 | 2024-08-03 | 2024-08-06 | Person 3 | Complete | Node 14
Create Invitations | 14 | 11 | 12 | 13 | 12 | 0.11111 | 2024-08-07 | 2024-08-18 | Person 4 | In Progress | Node 15
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## WBS TREE Diagram
WBS TREE DIAGRAM
Olympic 2026
Initiation | Planning |  | Execution | Control | Close
Hardware | Task |  | Task | Task | Task
Install | Subtask |  | Subtask | Subtask | Subtask
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Calendar
Project Calendar
[7 empty] | Project Name | Olympic 2026
|  |  |  | Aug. 2024 |  |  | Project Manager | Template22
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
1 Meet Client | 1 Requirements | 5 Inputs | 6 Design | 12 Project Testing | 13 Process | 6 Data model |  | Initiation
15 Project Deliver | 16 Define server | 22 Configure server | 22 Task 7 | 26 Project Completion | 27 Prepare PROD | 3 Create Guest List |  | Planning
7 Create Invitations | 8 Finalize Other Hires | 10 Hire Event | 11 Lock In Guest List | 28 Party! | 4 Plan Event Details | 18 Purchase Invitation |  | Execution
Monitoring/Control
Close
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Estimate
Estimate Template
Company Name | Olympic International Events |  | Date | 45641
Street Address | 450 Sunset Blvd |  | Quote # | EST-2024-001
City, State, Zip | Los Angeles, CA 90028 |  | Customer ID | CUS-1042
Website | TEMPLATE22.COM |  | Valid Until | 46275
Prepared By | Template22
Line Items
Project Phase | Vendor/Contractor | Labor ($) | Materials ($) | Total ($) | Notes
Initiation | Person 1 | 190 | 150 | 340 | Kickoff approved
Planning | Person 2 | 140 | 140 | 280 | Requirements draft
Planning | Person 3 | 65 | 200 | 265 | Missing vendor input
Planning | Person 4 | 300 | 180 | 480 | Design reviewed
Execution | Person 1 | 190 | 670 | 860 | Testing ongoing
Execution | Person 2 | 210 | 300 | 510 | Workflow updates
Execution | Person 3 | 520 | 200 | 720 | Data mapping
Execution | Person 7 | 432 | 690 | 1122 | Delivery pending
|  |  | Subtotal | 4577
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Action Plan
Action Plan Template
Project Name: | Olympic 2026 |  |  |  | Goal: | Deliver event successfully on time and within budget
Priority | Task (Action Item) | Phase | Assigned | Status | Start Date | Due Date | Planned Hours | Department | Materials Required
Low | Meet Client | Initiation | Person 1 | Complete | 45505 | 45508 | 2 | PMO | General Supplies
Low | Requirements | Planning | Person 2 | Complete | 45505 | 45506 | 2 | PMO | General Supplies
High | Inputs | Planning | Person 3 | Overdue | 45509 | 45509 | 1 | Data | General Supplies
Low | Design | Planning | Person 4 | Complete | 45510 | 45516 | 5 | Design | General Supplies
Medium | Project Testing | Execution | Person 1 | In Progress | 45516 | 45516 | 2 | PMO | General Supplies
Medium | Process | Execution | Person 2 | In Progress | 45517 | 45519 | 3 | PMO | General Supplies
Medium | Data model | Execution | Person 3 | In Progress | 45510 | 45519 | 8 | Data | General Supplies
Low | Project Deliver | Execution | Person 7 | Not Started | 45519 | 45519 | 6 | QA | General Supplies
Low | Define server | Execution | Person 10 | Not Started | 45520 | 45525 | 4 | IT | General Supplies
Low | Configure server | Execution | Person 8 | Not Started | 45526 | 45528 | 1 | IT | General Supplies
Low | Task 7 | Control | Person 2 | Not Started | 45526 | 45530 | 3 | PMO | General Supplies
Low | Project Completion | Close | Person 1 | Not Started | 45530 | 45530 | 6 | PMO | General Supplies
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Update Template
Project Update Template
Project Name | Olympic 2026
Reporting Period | Week of Dec 15, 2024
Report Date | 45641
Project Manager | Template22
Project Sponsor | Olympic International
Project Status Summary
Key Accomplishments
Meet Client completed / advanced by Person 1
Requirements completed / advanced by Person 2
Inputs completed / advanced by Person 3
Completed Work
Action Item | Date | RAG | Owner | Comments
Meet Client | 45508 | Green | Person 1 | Kickoff approved
Requirements | 45506 | Green | Person 2 | Requirements draft
Inputs | 45509 | Red | Person 3 | Missing vendor input
Design | 45516 | Green | Person 4 | Design reviewed
Upcoming Work
Action Item | Date | RAG | Owner | Comments
Project Testing | 45516 | Green | Person 1 | Testing ongoing
Process | 45517 | Green | Person 2 | Workflow updates
Data model | 45510 | Green | Person 3 | Data mapping
Project Deliver | 45519 | Amber | Person 7 | Delivery pending
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Planning Basis
Planning Basis Template
1 Planning Basis
1.1 Scope
Activities for Olympic 2026 are controlled under the approved charter and baseline schedule.
1.2 Milestones
Key milestones driven from Data sheet:
Milestone | Description | Delivery Date | Status | Owner
Business Case Approved | Approved by sponsor | 2024-07-28 | Done | Person 1
Project Charter Approved | Signed charter | 2024-08-01 | Done | Person 1
Team Appointed | Core team assigned | 2024-08-02 | Done | Person 1
Project Office Established | Workspace/tools ready | 2024-08-03 | Done | Person 6
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Risk Tracking
Risk Tracking Template
Date of last review: | 45641
ID | Description of Risk | Impact | Risk Response | Risk Level | Risk Owner | Status | Target Date | Notes
1 | Supplier delay | Timeline slip | Expedite alternate vendor | High | Person 5 | Open | 2024-08-12 | Monitor daily
2 | Budget overrun | Cost increase | Cost freeze and review | Medium | Person 1 | Open | 2024-08-20 | Weekly review
3 | Server issue | System downtime | Add backup environment | High | Person 10 | Open | 2024-08-18 | Infra team
4 | Low attendance | Event impact | Marketing push | Low | Person 9 | Mitigated | 2024-08-25 | Comms plan
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ISSUE MASTER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Issue ID | Description | Potential Impact | Priority | Date Opened | Date Closed | Owner | Status | Notes
1 | Website loading slow | Lag in registration | High | 2024-08-03 | 0 | Person 10 | Open | Investigating
2 | Guest list mismatch | Duplicate invites | Medium | 2024-08-04 | 0 | Person 3 | Open | Clean file
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Timesheet
Timesheet Template
Employee Name | Person 1
Department | PMO
Supervisor | Template22
Hourly Rate | 95
Day | Date | Start Time | Lunch Start | Lunch End | End Time | Regular Hours | Overtime Hours | Total Work Hours
Monday | 45509 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 8 | 1 | 9
Tuesday | 45510 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 8 | 0 | 8
Wednesday | 45511 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 8 | 0 | 8
Thursday | 45512 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 8 | 0 | 8
Friday | 45513 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 8 | 0 | 8
Saturday | 45514 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 0 | 0 | 0
Sunday | 45515 | 8:00 AM | 12:00 PM | 1:00 PM | 5:00 PM | 0 | 0 | 0
[7 empty] | Total Regular Hours | 40
[7 empty] | Total Overtime Hours | 1
[7 empty] | Total Pay | 3942.5
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## RACI Matrix
RACI Matrix Template
Project Tasks | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8
Meet Client | bar: Person 1; Person 8
Requirements | bar: Person 2; Person 8
Inputs | bar: Person 3; Person 8
Design | bar: Person 4; Person 8
Project Testing | bar: Person 1; Person 8
Process | bar: Person 2; Person 8
Data model | bar: Person 3; Person 8
Project Deliver | bar: Person 7 to Person 8
Define server | bar: Person 8
Configure server | bar: Person 8
Task 7 | bar: Person 2; Person 8
Project Completion | bar: Person 1; Person 8
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Issue Tracking
Issue Tracking Template
ID | Description | Potential Impact | Priority | Date Opened | Date Closed | Issue Owner | Department | Status | Notes
1 | Website loading slow | Lag in registration | High | 2024-08-03 | 0 | Person 10 | IT | Open | Investigating
2 | Guest list mismatch | Duplicate invites | Medium | 2024-08-04 | 0 | Person 3 | Data | Open | Clean file
3 | Vendor quote pending | Procurement delay | Low | 2024-08-06 | 2024-08-07 | Person 5 | Supply | Closed | Resolved
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
CHANGE LOG MASTER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Change # | Type | Description | Date Initiated | Status | Priority | Assigned | Expected Resolution | Action | Impact
1 | Product | Revise invite design | 2024-08-07 | Open | Medium | Person 4 | 3 days | Update artwork | Scope
2 | Schedule | Move rehearsal date | 2024-08-08 | Closed | High | Person 6 | 1 day | Rebook venue | Schedule
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Resource Plan
Resource Plan
Project Name | Olympic 2026
Project Manager | Template22
Client | Olympic International
Resource | Team | Task | Total Effort | Rate | Cost | Date | Project
Person 1 | PMO | Kickoff | 6 | 95 | 570 | 2024-08-01 | Olympic 2024
Person 3 | Data | Guest List | 8 | 65 | 520 | 2024-08-05 | Olympic 2024
Person 4 | Design | Invitation Design | 10 | 60 | 600 | 2024-08-06 | Olympic 2024
Person 9 | Comms | Reminders | 4 | 62 | 248 | 2024-08-20 | Olympic 2024
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE REQUEST MASTER | 0 | 0 | 0 | 0 | 0 | 0 | 0
CR # | Project Name | Change Name | Requested By | Contact |  | Date | Description
1 | Olympic 2024 | Add VIP seating | Person 1 | person1@olympicintl.com |  | 2024-08-09 | Add VIP rows near stage
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Change Log
Change Log Template
Project Name | Olympic 2026
Project Manager | Template22
Program Manager | Olympic International
Change # | Type | Description | Date Initiated | Status | Priority | Assigned | Expected Resolution | Action | Impact | Date Resolved
1 | Product | Revise invite design | 2024-08-07 | Open | Medium | Person 4 | 3 days | Update artwork | Scope | 0
2 | Schedule | Move rehearsal date | 2024-08-08 | Closed | High | Person 6 | 1 day | Rebook venue | Schedule | 2024-08-09
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
DOC MASTER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase | Document Name | Description | Owner | Status | Date Created | Last Updated | Location | 0 | 0 | 0
Initiation | Business Case | Need and value statement | Person 1 | Approved | 2024-07-25 | 2024-07-28 | SharePoint/Initiation/Business_Case.docx | 0 | 0 | 0
Initiation | Project Charter | Authorizes project | Person 1 | Approved | 2024-08-01 | 2024-08-01 | SharePoint/Initiation/Project_Charter.docx | 0 | 0 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Multiple Project Tracking
Multiple Project Tracking Template
Project Name | Olympic 2026 - A
Task Name/Description | Dependent Task | Assigned To | Priority | Start Date | Planned End Date | Actual End Date | Planned Cost | Actual Cost
Meet Client |  | Person 1 | Low | 45505 | 45508 |  | 150 | 150
Requirements |  | Person 2 | Low | 45505 | 45506 |  | 140 | 140
Inputs |  | Person 3 | High | 45509 | 45509 |  | 200 | 200
Design |  | Person 4 | Low | 45510 | 45516 |  | 180 | 180
Project Testing |  | Person 1 | Medium | 45516 | 45516 |  | 670 | 430
Project Name | Olympic 2026 - B
Task Name/Description | Dependent Task | Assigned To | Priority | Start Date | Planned End Date | Actual End Date | Planned Cost | Actual Cost
Data model |  | Person 3 | Medium | 45510 | 45519 |  | 200 | 90
Project Deliver |  | Person 7 | Low | 45519 | 45519 |  | 690 | 0
Define server |  | Person 10 | Low | 45520 | 45525 |  | 340 | 0
Configure server |  | Person 8 | Low | 45526 | 45528 |  | 200 | 0
Task 7 |  | Person 2 | Low | 45526 | 45530 |  | 230 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Timeline Detail
Project Timeline Template
Task Name | Start | End | Duration (Days) | Owner | Status
Meet Client | 45505 | 45508 | 4 | Person 1 | Complete
Requirements | 45505 | 45506 | 2 | Person 2 | Complete
Inputs | 45509 | 45509 | 1 | Person 3 | Overdue
Design | 45510 | 45516 | 7 | Person 4 | Complete
Project Testing | 45516 | 45516 | 1 | Person 1 | In Progress
Process | 45517 | 45519 | 3 | Person 2 | In Progress
Data model | 45510 | 45519 | 10 | Person 3 | In Progress
Project Deliver | 45519 | 45519 | 1 | Person 7 | Not Started
Define server | 45520 | 45525 | 6 | Person 10 | Not Started
Configure server | 45526 | 45528 | 3 | Person 8 | Not Started
Task 7 | 45526 | 45530 | 5 | Person 2 | Not Started
Project Completion | 45530 | 45530 | 1 | Person 1 | Not Started
Prepare PROD | 45531 | 45536 | 6 | Person 8 | In Progress
Create Guest List | 45507 | 45510 | 4 | Person 3 | Complete
Create Invitations | 45511 | 45522 | 12 | Person 4 | In Progress
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Kanban Board
Kanban Board
Project Name | Olympic 2026
Sprint Start | 45509
Sprint End | 46275
Backlog |  | To Do |  | Doing |  | Done
[6 empty] | Meet Client | Person 1
[6 empty] | Requirements | Person 2
[6 empty] | Design | Person 4
|  |  |  | Project Testing | Person 1
|  |  |  | Process | Person 2
|  |  |  | Data model | Person 3
Project Deliver | Person 7 | Project Deliver | Person 7
Define server | Person 10 | Define server | Person 10
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Handover Template
Project Handover Template
Project Name | Olympic 2026
Project Location | Los Angeles, Case
Project Start Date | 45509
Former Project Team | Role | Responsibilities | Contact
Person 1 | Project Manager | Delivered assigned work packages | person1@olympicintl.com
Person 2 | Business Analyst | Delivered assigned work packages | person2@olympicintl.com
Person 3 | Data Analyst | Delivered assigned work packages | person3@olympicintl.com
Person 4 | Designer | Delivered assigned work packages | person4@olympicintl.com
Receiving / Transition Team | Role | Responsibilities | Contact
Person 5 | Vendor Manager | Operate and support project outputs | person5@olympicintl.com
Person 6 | Coordinator | Operate and support project outputs | person6@olympicintl.com
Person 7 | QA Lead | Operate and support project outputs | person7@olympicintl.com
Person 8 | Engineer | Operate and support project outputs | person8@olympicintl.com
Task Completed | Deliverable | Milestone Achieved | Status
Meet Client | Initiation | Initiation | Complete
Requirements | Planning | Planning | Complete
Inputs | Planning | Planning | Overdue
Design | Planning | Planning | Complete
Project Testing | Execution | Execution | In Progress
Process | Execution | Execution | In Progress
Project Budget | 5500 |  | Actual Cost (to date) | 5300 | ETC | 200
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Documentation Templat
Project Documentation Template
Project Phase | Project Document Name | Project Document Description | Project Document Owner | Status | Date Created | Last Updated | Location / Link
Initiation | Business Case | Need and value statement | Person 1 | Approved | 2024-07-25 | 2024-07-28 | SharePoint/Initiation/Business_Case.docx
Initiation | Project Charter | Authorizes project | Person 1 | Approved | 2024-08-01 | 2024-08-01 | SharePoint/Initiation/Project_Charter.docx
Planning | Schedule Management Plan | Planning baseline | Person 2 | Approved | 2024-08-02 | 2024-08-03 | SharePoint/Planning/Schedule_Plan.docx
Execution | Status Reports | Weekly updates | Person 9 | In Progress | 2024-08-10 | 2024-08-15 | SharePoint/Execution/Status_Report.xlsx
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
RESOURCE PLAN MASTER | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resource | Team | Task | Hours | Rate | Date | Project
Person 1 | PMO | Kickoff | 6 | 95 | 2024-08-01 | Olympic 2024
Person 3 | Data | Guest List | 8 | 65 | 2024-08-05 | Olympic 2024
Person 4 | Design | Invitation Design | 10 | 60 | 2024-08-06 | Olympic 2024
Person 9 | Comms | Reminders | 4 | 62 | 2024-08-20 | Olympic 2024
0 | 0 | 0 | 0 | 0 | 0 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Master Production Schedule
Master Production Schedule
Work Center | Event Ops
Shift | Day
Date | 45641
Order Status | Product Number | Customer | Product List | Variations | Total Qty | Starting Inventory | Ending Inventory | Start Date | End Date | Ship Date | Notes
Complete | ORD-001 | Olympic Intl | Meet Client | 0 | 1 | 10 | 9 | 45505 | 45508 | 45508 | Kickoff approved
Complete | ORD-002 | Olympic Intl | Requirements | 0 | 1 | 10 | 9 | 45505 | 45506 | 45506 | Requirements draft
Overdue | ORD-003 | Olympic Intl | Inputs | 0 | 1 | 10 | 9 | 45509 | 45509 | 45509 | Missing vendor input
Complete | ORD-004 | Olympic Intl | Design | 0 | 1 | 10 | 9 | 45510 | 45516 | 45516 | Design reviewed
In Progress | ORD-005 | Olympic Intl | Project Testing | 0 | 1 | 10 | 9 | 45516 | 45516 | 45516 | Testing ongoing
In Progress | ORD-006 | Olympic Intl | Process | 0 | 1 | 10 | 9 | 45517 | 45519 | 45519 | Workflow updates
In Progress | ORD-007 | Olympic Intl | Data model | 0 | 1 | 10 | 9 | 45510 | 45519 | 45519 | Data mapping
Not Started | ORD-008 | Olympic Intl | Project Deliver | 0 | 1 | 10 | 9 | 45519 | 45519 | 45519 | Delivery pending
Not Started | ORD-009 | Olympic Intl | Define server | 0 | 1 | 10 | 9 | 45520 | 45525 | 45525 | Infra pending
Not Started | ORD-010 | Olympic Intl | Configure server | 0 | 1 | 10 | 9 | 45526 | 45528 | 45528 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## To-Do List
To-Do List
My Tasks | Start Date | Due Date | % Complete | Progress | Notes | Done
Meet Client | 45505 | 45508 | 1 | 100% | Kickoff approved | Done
Requirements | 45505 | 45506 | 1 | 100% | Requirements draft | Done
Inputs | 45509 | 45509 | 0 | 0% | Missing vendor input
Design | 45510 | 45516 | 1 | 100% | Design reviewed | Done
Project Testing | 45516 | 45516 | 0.5 | 50% | Testing ongoing
Process | 45517 | 45519 | 0.5 | 50% | Workflow updates
Data model | 45510 | 45519 | 0.5 | 50% | Data mapping
Project Deliver | 45519 | 45519 | 0 | 0% | Delivery pending
Define server | 45520 | 45525 | 0 | 0% | Infra pending
Configure server | 45526 | 45528 | 0 | 0% | 0
Task 7 | 45526 | 45530 | 0 | 0% | 0
Project Completion | 45530 | 45530 | 0 | 0% | Go-live signoff
Prepare PROD | 45531 | 45536 | 0.5 | 50% | Deployment prep
Create Guest List | 45507 | 45510 | 1 | 100% | Event planning carryover | Done
Create Invitations | 45511 | 45522 | 0.5 | 50% | Draft ready
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Weekly Work Schedule Template
Weekly Work Schedule Template
Supervisor Name | Template22
Department | Event Operations area
Week of | 45509
Employee Name | Task | Project | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Total Hours
Person 1 | Meet Client | Olympic 2026 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 2
Person 2 | Requirements | Olympic 2026 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 2
Person 3 | Inputs | Olympic 2026 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 1
Person 4 | Design | Olympic 2026 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 5
Person 5 | Project Testing | Olympic 2026 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 2
Person 6 | Process | Olympic 2026 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 3
Person 7 | Data model | Olympic 2026 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 0 | 0 | 8
Person 8 | Project Deliver | Olympic 2026 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 0 | 0 | 6
Person 9 | Define server | Olympic 2026 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 4
Person 10 | Configure server | Olympic 2026 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 1
[9 empty] | TOTALS | 34
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Change Request Form
Change Request Form
Project Name | Olympic 2024
Change Name | Add VIP seating
Number | 1
Requested By | Person 1
Contact | person1@olympicintl.com
Date | 2024-08-09
Description of Change | Add VIP rows near stage
Reason for Change | Sponsor request
Priority | High
Impact on Deliverables | Layout + budget
Date Needed | 2024-08-20
Approval of Request | Pending
Change Impact
Tasks/Scope Affected
Cost Evaluation
Risk Evaluation
Quality Evaluation
Additional Resources
Duration
Additional Effort
Impact on Deadline
Alternative and Recommendations
Comments
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Prioritization Matrix
Project Prioritization Matrix
Project | Olympic 2026 | Manager | Template22 | Date | 2024-12-15
| DO NOW |  | DO LATER
| Must be done immediately |  | Schedule for the near future
CRUCIAL
| Fix athlete check-in system |  | Fix athlete check-in system
| Finalize sponsor deck |  | Finalize sponsor deck
| Archive old media files |  | Archive old media files
| Delegate badge printing QA |  | Delegate badge printing QA
NOT CRUCIAL
Archive old media files
Delegate badge printing QA
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Gap Analysis
Gap Analysis
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
Focus | Current State | Future State | Gap % | Action | Priority | Start | End | Owner | Status
Volunteer Capacity | 10 volunteers | 20 volunteers | 5000% | Recruiting | Medium | 2024-08-01 | 2024-08-21 | Person 6 | In Progress
Registration Tablets | 6 tablets | 12 tablets | 5000% | Purchase | High | 2024-08-05 | 2024-08-12 | Person 5 | Done
Parking Signage | 20 signs | 35 signs | 4300% | Print signs | Low | 2024-08-10 | 2024-08-24 | Person 4 | Not Started
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Stakeholder Analysis
Stakeholder Analysis
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
Stakeholder | Title | Email | Influence | Interest | Priority | SME? | Decision Maker | Comm Freq | Comm Method | Current | Required | Phase | Contact
David Johnson | Sponsor | david@olympicintl.com | High | High | High | Yes | Yes | Weekly | In Person | Neutral | Supporter | Planning | 555-0101
Sally Feldman | Finance Lead | sally@olympicintl.com | Medium | High | Medium | Yes | No | Biweekly | Email | Passive | Neutral | Execution | 555-0102
Mike McPadden | Operations Head | mike@olympicintl.com | High | Medium | High | Yes | Yes | Weekly | Phone | Supporter | Supporter | Execution | 555-0103
Joyce Van Patten | City Liaison | joyce@lacity.gov | Low | High | Medium | No | No | Monthly | Meeting | Neutral | Supporter | Control | 555-0104
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Cost Benefit Analysis
Cost Benefit Analysis
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
Category | Type | Year1 | Year2 | Year3 | Year4 | Year5 | Year6 | Total
Rent | Indirect Cost | 1000 | 1100 | 1200 | 1300 | 1400 | 1500 | 7500
Utilities | Indirect Cost | 200 | 220 | 240 | 260 | 280 | 300 | 1500
Production levels | Intangible Cost | 500 | 400 | 600 | 800 | 500 | 300 | 3100
Ticket Revenue | Benefit | 3500 | 4200 | 4600 | 5100 | 5300 | 5600 | 28300
Sponsor Revenue | Benefit | 2000 | 2400 | 2600 | 2800 | 3000 | 3200 | 16000
Total Costs | [7 empty] | 12100
Total Benefits | [7 empty] | 44300
Net Benefit | [7 empty] | 32200
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Budget Dashboard
Budget Dashboard Template
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
Category | Planned Cost | Actual Cost | Variance |  | Total Planned | 40022
Planning | 860 | 860 | 0 |  | Total Actual | 5150
Execution | 2400 | 640 | 1760 |  | Balance | 34872
Procurement | 1070 | 1070 | 0
Communications | 34492 | 2430 | 32062
Control | 230 | 0 | 230
Close | 970 | 150 | 820
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Task Tracker Dashboard
Task Tracker Dashboard
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
ID | Task | Category | Owner | Status | Start | Due | Days | Est Hours | Planned Cost ($) | Actual Cost ($) | Notes
1 | Meet Client | Initiation | Person 1 | Complete | 45505 | 45508 | 4 | 2 | 150 | 150 | Kickoff approved
2 | Requirements | Planning | Person 2 | Complete | 45505 | 45506 | 2 | 2 | 140 | 140 | Requirements draft
3 | Inputs | Planning | Person 3 | Overdue | 45509 | 45509 | 1 | 1 | 200 | 200 | Missing vendor input
4 | Design | Planning | Person 4 | Complete | 45510 | 45516 | 7 | 5 | 180 | 180 | Design reviewed
5 | Project Testing | Execution | Person 1 | In Progress | 45516 | 45516 | 1 | 2 | 670 | 430 | Testing ongoing
6 | Process | Execution | Person 2 | In Progress | 45517 | 45519 | 3 | 3 | 300 | 120 | Workflow updates
7 | Data model | Execution | Person 3 | In Progress | 45510 | 45519 | 10 | 8 | 200 | 90 | Data mapping
8 | Project Deliver | Execution | Person 7 | Not Started | 45519 | 45519 | 1 | 6 | 690 | 0 | Delivery pending
9 | Define server | Execution | Person 10 | Not Started | 45520 | 45525 | 6 | 4 | 340 | 0 | Infra pending
10 | Configure server | Execution | Person 8 | Not Started | 45526 | 45528 | 3 | 1 | 200 | 0 | 0
Task Status |  |  |  | Task Categories
Not Started | 3 | 30% |  | Planning | 3
In Progress | 3 | 30% |  | Execution | 6
Complete | 3 | 30% |  | Procurement | 0
Overdue | 1 | 10% |  | Communications | 0
On Hold | 0 | 0% |  | Control | 0
|  |  |  | Close | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Stakeholder Map
Stakeholder Map
Project | Olympic 2026 |  | Manager | Template22 | Date | 2024-12-15
ID | Name | Influence (1-3) | Interest (1-3) | Category | Name | Category
1 | David Johnson | 3 | 3 | Manage Closely | David Johnson | Manage Closely
2 | Sally Feldman | 2 | 3 | Manage Closely | Sally Feldman | Manage Closely
3 | Mike McPadden | 3 | 2 | Manage Closely | Mike McPadden | Manage Closely
4 | Joyce Van Patten | 1 | 3 | Keep Informed | Joyce Van Patten | Keep Informed
| Keep Satisfied |  | Manage Closely
| Monitor |  | Keep Informed
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Risk Matrix
Risk Matrix
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
|  | Insignificant | Minor | Moderate | Major | Severe |  | Risk | Level | Owner
| Almost Certain | Medium | High | Very High | Very High | Very High |  | Supplier delay | High | Person 5
| Likely | Medium | High | High | Very High | Very High |  | Budget overrun | Medium | Person 1
| Possible | Low | Medium | High | High | Very High |  | Server issue | High | Person 10
| Unlikely | Low | Low | Medium | Medium | High |  | Low attendance | Low | Person 9
| Rare | Low | Low | Low | Low | Medium
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## RAID Log
RAID Log
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
ID | RAID Category | Description | Impact | Response | Priority | Owner | Status | Notes
ID | Category | Description | Impact | Response | Priority | Owner | Status | Notes
1 | Risk | Machinery breakdown | Delay schedule | Backup supplier | High | Joyce | Open | SAMPLE
2 | Assumption | Machine uptime 95% | Cost variance | Monitor weekly | High | Dan | Open | SAMPLE
3 | Issue | Late permit review | Schedule slip | Escalate city office | Low | Helen | In Progress | SAMPLE
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Stakeholder Register
Stakeholder Register
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
Stakeholder Name | Role | Category | Power/Influence | Interest | Expectation | Communication | Contact
David Johnson | Sponsor | Planning | High | High | Supporter | In Person | 555-0101
Sally Feldman | Finance Lead | Execution | Medium | High | Neutral | Email | 555-0102
Mike McPadden | Operations Head | Execution | High | Medium | Supporter | Phone | 555-0103
Joyce Van Patten | City Liaison | Control | Low | High | Supporter | Meeting | 555-0104
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Lessons Learned Template
Lessons Learned Template
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
WIN or ISSUE | What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items | Owner
Type | Description | Impact | Future Change | Action Items | Owner
WIN | Daily standups improved coordination | Saved 20 hours | Standardize for all events | Publish playbook | Person 1
ISSUE | Late vendor onboarding | Two-day delay | Prequalify vendors earlier | Create vendor checklist | Person 5
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Decision Matrix
Decision Matrix
Project | Olympic 2026 |  | Manager | Template22 |  | Date | 2024-12-15
Criteria | Weight | Option A |  | Option B |  | Option C
|  | Rating | Weighted | Rating | Weighted | Rating | Weighted
Quality | 2 | 3 | 6 | 2 | 4 | 2 | 4
Cost | 5 | 3 | 15 | 3 | 15 | 5 | 25
Value to Customer | 3 | 4 | 12 | 3 | 9 | 5 | 15
Safety/Environment | 1 | 3 | 3 | 3 | 3 | 5 | 5
Support to Solution | 3 | 4 | 12 | 4 | 12 | 5 | 15
Training Factors | 2 | 3 | 6 | 2 | 4 | 4 | 8
Total Value |  |  | 54 |  | 47 |  | 72
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Communication Plan
Communication Plan
Project Name: | Olympic 2026 |  | Date: | 45641
Project Manager: | Template22
Communication Activity
Communication Activity | Objective | Audience | Frequency | Owner | Channel | Key Message
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Project Kickoff Meeting | Introduce project goals | Project Team, Stakeholders | One-time | Project Manager | In-Person Meeting | Overview of project scope and objectives
Communication Matrix
Roles | Kickoff Meeting | Status Update Emails | Steering Committee | Team Meetings | Client Reports | Project Newsletter | Notes
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Project Manager | R | R | R | R | C | R
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Cost Estimation Template
Cost Estimation Template
Project Name: | Olympic 2026 |  |  | Client: | Olympic International
Prepared By: | Template22 |  |  | Date: | 45641
Project Deadline: | 46275
Task / Item | Description | Hours/Qty | Unit Cost | Total Cost | Dependencies | Notes
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
Research & Planning | Initial project research | 20 | 50 | 1000 | Review materials
|  | Subtotal: | 9000
|  | Contingency (10%): | 900
|  | Taxes (8%): | 792
|  | Total Estimated Cost: | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Quality Management Plan
Quality Management Plan
Project Information | Quality Objectives | Quality Standards & Criteria | Quality Assurance Activities | Approval & Reviews
Project Name: | Olympic 2026 | Responsive Design | Design Reviews | Prepared By: | John Smith
Project Manager: | Template22 | Load Time <3 Seconds | Code Inspections | Reviewed By: | Jane Doe
Start Date: | 45509 | No Critical Defects | Documentation Audits | Approval Date: | 2024-01-20
End Date: | 46275 |  | Team Training Sessions | Next Review Date: | 2024-05-15
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Procurement Management Plan
Procurement Management Plan
Project Name: | Olympic 2026 | Project Manager: | Template22 | Date: | 45641
Procurement Requirements
Item / Service | Description | Procurement Method | Supplier | Est. Cost | Timeline
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Office Furniture | Desks, chairs, cabinets | Competitive Bidding | ABC Furniture Co. | 50000 | Q1 2024
Risk Management
Risk | Mitigation Strategy
Delays in Delivery | Set clear timelines and penalties for late delivery
Delays in Delivery | Set clear timelines and penalties for late delivery
Delays in Delivery | Set clear timelines and penalties for late delivery
Delays in Delivery | Set clear timelines and penalties for late delivery
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Budget Tracker
Project Budget Tracker
Total Budget: | 5500 |  |  |  |  | Metric | Value
Amount Spent: | 37450 |  |  |  |  | Total Budget | 5500
Remaining Budget: | -31950 |  |  |  |  | Spent | 37450
% Spent: | 6.8091 |  |  |  |  | Remaining | -31950
Expense Details
Date | Category | Description | Vendor | Cost | Status
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved | Equipment | 156000
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved | Marketing | 0
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved | Travel | 0
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved | Materials | 0
2024-01-10 | Equipment | Laptops | Tech World | 12000 | Approved | Consultants | 0
[6 empty] | Software | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Initiation Checklist
Project Initiation Checklist
Done | Task | Description | Owner | Due Date | Status | Progress
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
☑ | Define Project Objectives | Outline the project goals and objectives. | Alice | 2024-01-15 | Complete | 100
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Kickoff Agenda
Project Kickoff Agenda
Date: | 45641 | Time: | 10:00 AM - 12:00 PM
Time | Agenda Item | Presenter | Details
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
10:00 AM - 10:15 AM | Welcome & Introductions | Project Manager | Team introductions and meeting objectives
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## One Page Project Plan
ONE PAGE PROJECT PLAN
Project Overview
Project Name: | Olympic 2026 |  |  | Project Sponsor: | Olympic International
Project Manager: | Template22 |  |  | Project Budget: | 5500
Start Date: | 45509
End Date: | 46275
Project Goals |  |  |  | Key Milestones
• Goal | Objective 1 |  |  | Meet Client |  | Due Date: | 45508
• Goal | Objective 2 |  |  | Requirements |  | Due Date: | 45506
• Goal | Objective 3 |  |  | Inputs |  | Due Date: | 45509
|  |  |  | Design |  | Due Date: | 45516
|  |  |  | Project Testing |  | Due Date: | 45516
Project Timeline
Task | Owner | Week1 | Week2 | Week3 | Week4 | Week5 | Status
Meet Client | Person 1 | [5 empty] | Complete
Requirements | Person 2 | [5 empty] | Complete
Inputs | Person 3 | [5 empty] | Overdue
Design | Person 4 | [5 empty] | Complete
Project Testing | Person 1 | [5 empty] | In Progress
Risk & Issues |  |  |  |  | On-Track?
Risk / Issue | Impact | Mitigation Plan |  |  | ☑ On Track
Machinery breakdown | Delay schedule | Backup supplier |  |  | ⚠ At Risk
Machine uptime 95% | Cost variance | Monitor weekly |  |  | ❗ Behind Schedule
Late permit review | Schedule slip | Escalate city office
Next Steps / Comments
Next milestone: Project Testing
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Risk Management Plan
Risk Management Plan
Risk ID | Risk Description | Likelihood | Impact | Risk Level | Mitigation Strategy | Responsible Person | Status
R-01 | Machinery breakdown | High | High | Red | Backup supplier | Template22 | Open
R-02 | Machine uptime 95% | High | High | Red | Monitor weekly | Template22 | Open
R-03 | Late permit review | Low | Low | Yellow | Escalate city office | Template22 | Open
R-04 | Venue access approval | Medium | Medium | Amber | Confirm date | Template22 | Open
R-05 | 0 | 0 | 0 | Yellow | 0 | Template22 | Open
R-06 | 0 | 0 | 0 | Yellow | 0 | Template22 | Open
R-07 | 0 | 0 | 0 | Yellow | 0 | Template22 | Open
R-08 | 0 | 0 | 0 | Yellow | 0 | Template22 | Open
R-09 | 0 | 0 | 0 | Yellow | 0 | Template22 | Open
R-10 | 0 | 0 | 0 | Yellow | 0 | Template22 | Open
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Scope Management Plan
Scope Management Plan
Project Information
Project Name: | Olympic 2026
Project Manager: | Template22
Project Sponsor: | Olympic International
Date Created: | 45641
Scope Management Approach
Scope Definition Process | Define project scope, objectives, and deliverables
Scope Verification | Process for reviewing and approving scope
Work Breakdown Structure (WBS)
WBS Code | Task Name | Description
1.0 | Meet Client | Initiation task
1.1 | Requirements | Planning task
1.2 | Inputs | Planning task
1.3 | Design | Planning task
1.4 | Project Testing | Execution task
1.5 | Process | Execution task
Scope Change Management
Change Control Process | Procedure for handling scope changes
Change Request Form | Template for submitting change requests
Roles & Responsibilities
Role | Responsibility
Project Manager | Oversee scope management and execution
Business Analyst | Define requirements and scope
Team Lead | Validate deliverables against scope
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Change Management Plan
Change Management Plan
Summary |  |  |  | Change Objectives
Project Name: | Olympic 2026 |  |  | - Minimize disruption to operations.
Project Manager: | Template22 |  |  | - Ensure staff are prepared for changes.
Date: | 45641 |  |  | - Improve system efficiency.
Change Identification |  |  | Impact Assessment |  |  | Action Plan
ID | Change Description |  | Area Affected | Impact Level | Comments | Task | Owner | Status
C-001 | Upgrade Software Platform |  | IT Department | High | System downtime | Software Installation | Michael | In Progress
C-001 | Upgrade Software Platform |  | IT Department | High | System downtime | Software Installation | Michael | In Progress
C-001 | Upgrade Software Platform |  | IT Department | High | System downtime | Software Installation | Michael | In Progress
C-001 | Upgrade Software Platform |  | IT Department | High | System downtime | Software Installation | Michael | In Progress
C-001 | Upgrade Software Platform |  | IT Department | High | System downtime | Software Installation | Michael | In Progress
Timeline & Milestones
Phase | Start Date | End Date | Milestone
Planning | 2024-01-20 | 2024-01-30 | Change Plan Approved
Implementation | 2024-02-01 | 2024-02-20 | System Upgrade Completed
Review | 2024-02-21 | 2024-02-28 | Post-Implementation Review
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Team Roles Responsibilities
Team Roles & Responsibilities Matrix
Task / Project Phase | Alice | Bob | Carol | David | Emma | Legend
Project Planning | R | A | C | I | I | R
Requirements Gathering | A | C | R | I |  | A
Design & Development |  | R | A |  |  | C
Testing | C | R | A |  |  | I
Documentation | R | I | C
Deployment | I
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Meeting Minutes Template
MEETING MINUTES TEMPLATE
Meeting Date: | 2024-02-15 |  |  |  | Time: | 10:00 AM
Meeting Location: | Los Angeles HQ |  |  |  | Meeting Leader: | John Smith
Attendees / Agenda / Notes
Attendees | Agenda Items | Presenter | Discussion & Notes | Action Item | Responsible | Due Date | Status
John Smith | Project Timeline | John Smith | Reviewed updated project schedule. | Finalize timeline and share with team | John Smith | 2024-02-18 | Open
Sarah Lee | Budget Update | Sarah Lee | Discussed budget adjustments needed. | Prepare revised budget report | Sarah Lee | 2024-02-17 | Open
Michael Brown | Design Review | Michael Brown | Reviewed design concepts and feedback. | Update design based on feedback | Michael Brown | 2024-02-20 | Open
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Due Date | Status | Progress | 0 | 0 | 0 | 0 | 0
2024-05-10 | In Progress | 45 | 0 | 0 | 0 | 0 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Task Assignment Sheet
Task Assignment Sheet
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Progress
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
T001 | Develop Project Plan | John Smith | High | 2024-05-10 | In Progress | 45
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Deliverables Tracker
Deliverables Tracker
Task | Assigned To | Due Date | Status | Priority | Comments
Develop Project Plan | John Smith | 2024-05-10 | In Progress | High
Design Website Mockup | Emma Davis | 2024-05-12 | Not Started | Medium
Write Marketing Report | Michael Brown | 2024-05-08 | Completed | High
Client Meeting | Sara Lee | 2024-05-07 | Scheduled | High
Code Review | David Wilson | 2024-05-09 | Completed | Low
Prepare Presentation | Laura Clark | 2024-05-11 | In Progress | Medium
Data Analysis | James Miller | 2024-05-13 | Not Started | High
Test Software | Linda Harris | 2024-05-10 | In Testing | Medium
Create User Manual | Kevin Anderson | 2024-05-14 | In Review | Low
Finalize Budget Report | Rachel Green | 2024-05-10 | Pending | High
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Communication Log
Project Communication Log
Date | Time | Contact Person | Method | Subject / Topic | Discussion Summary | Action Items | Next Steps / Follow-Up
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
2024-02-15 | 10:00 AM | John Smith | Email | Project Timeline | Reviewed updated project schedule. | Finalize timeline and share with team. | Schedule team meeting for 2024-02-18
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Milestone Tracker
Milestone Tracker
Task | Owner | Start Date | Due Date | Status | Progress
Meet Client | Person 1 | 45505 | 45508 | Complete | 100
Requirements | Person 2 | 45505 | 45506 | Complete | 100
Inputs | Person 3 | 45509 | 45509 | Overdue | 25
Design | Person 4 | 45510 | 45516 | Complete | 100
Project Testing | Person 1 | 45516 | 45516 | In Progress | 60
Process | Person 2 | 45517 | 45519 | In Progress | 60
Data model | Person 3 | 45510 | 45519 | In Progress | 60
Project Deliver | Person 7 | 45519 | 45519 | Not Started | 0
Define server | Person 10 | 45520 | 45525 | Not Started | 0
Configure server | Person 8 | 45526 | 45528 | Not Started | 0
Task 7 | Person 2 | 45526 | 45530 | Not Started | 0
Project Completion | Person 1 | 45530 | 45530 | Not Started | 0
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure

## Project Closure Report
Project Closure Report
Project Name: | Olympic 2026 | Project Manager: | Template22 | Closure Date: | 46275
1. Project Overview
Project Objective: | PL2021-005 |  | Start Date: | 45509 | End Date: | 46275
2. Project Deliverables
Deliverable | Status | Comments
Develop Project Plan | In Progress
Design Website Mockup | Not Started
Write Marketing Report | Completed
Client Meeting | Scheduled
Code Review | Completed
3. Project Performance |  |  |  | 5. Lessons Learned
Criteria | Rating | Notes |  | What Went Well: | On Budget
Scope | 2024-12-15 |  |  | What Could Be Improved: | High Quality
Schedule | Successful launch of event to market
Budget | Met
Quality | Delayed
6. Final Approval
Approved By | Role | Signature | Date
Sarah Lee | Project Sponsor | Sarah Lee | 46275
David Brown | Operations Manager | David Brown | 46275
Michael Johnson | QA Lead | Michael Johnson | 46275
Main Dashboard
Data
Instructions
Benefits
Template22
Project Plan
Execution Plan
Charter
Task Tracking
Network Diagram
Status Report
Budget
Critical Path Method
PERT Chart
WBS Diagram
Calender
Cost Estimate
Action Plan
Update Template
Planning Basis
Risk Tracking
Timesheet
Raci Matrix
Issue Tracking
Resource Plan
Change Log
Multiple Project
Timeline Detail
Kanban Board
Handover Template
Documentation Template
Master Production
To-Do List
Weekly Work
Change Request
Prioritization Matrix
Gap Analysis
Stakeholder Analsis
Cost Benefit
Budget Dashboard
Task Tracker
Stakeholder Map
Risk Matrix
Raid Log
Stakeholder Register
Lessons Learned
Decision Matrix
Communication Plan
Cost Estimation
Qualtiy Management
Procurment Plan
Project Budget
Project Kickoff
One Page Project
Risk Managment
Scope Managment
Project Initiation
Change Managment
Team Roles
Meeting Minutes
Task Assigment
Deliverables Tracker
Communication Log
Milestone Tracker
Project Closure